## V3_Land Legal SA&C (hidden)
LAND LEGAL SCHEDULE OF ACTIVITIES AND COSTS - BP2020 TRANCHE 2 FUNDING
[7 empty] | DRAFT Date: | 2020-02-11
Item no. | Agenda Item | Description of activity | Activities required to bring about conclusion of matter | Budget breakdown & possible disbursement | Budget | Aprox. L/Legal Disbursements | Timeframe for completion | Comments
1 | Land Legal
1.1 | Land Legal: Specific Instructions
1.1.1 | DOHS Specific Instruction
1.1.1.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | 1. Review matter & Liase with Housing (DOHS) 2. Prepare report to DOHS & SMC |  | 8522 |  | 1 month
1.1.1.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | 1. Review evidence 2. Prepare report to DOHS & SMC |  | 8522 |  | 1 month
1.1.1.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | PSP to engage LMO department in dealing with the matter | 1. Review evidence 2. Prepare report to SMC |  | 8522 |  | 1 month
1.1.2 | DALARD
1.1.3 | GISC Specific Instructions
1.1.4 | 2018 /2019 GEVDI Specific Instructions
1.1.4.1 | Donation of land / upgrading of tenure
1.1.4.1 (a) | 22 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 12783 |  | 1 Month
1.1.4.1 (b) | 42 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 21305 |  | 1 Month
1.1.4.1 (c) | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. | 1. Review matter in the context of SPLUMA 2. Prepare SPLUMA application 3. Prepare report to SMC. | TBD - SPLUMA & Planning Costs | 12783 |  | 1 Month
1.1.4.1 (d) | Willowspruit - Donation of 7 properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 21305 |  | 1 Month
1.1.4.1 (e) | Musi Thuzi School: Ptn 7 of Erf 206 Edendale | Assist with the relayout, survey and subdivision of the property in order to accommodate the school, owner and the IRPTN | 1. Review status & Planning 2. Prepare report to SMC |  | 8522 |  | 1 Month
1.1.4.1 (f) | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | Completion of Donation agreement & submission to Municipality toward the opening of the township register & endorsment of Title Deeds | 1. Odwa to contact Thula Biyela and have the signing of agreement arranged 2. Prepare report to SMC to have donation confirmed 3. Instruct John Christie | R10 000.00 TBC - John Christie | 8522 |  | 3 Months
1.1.4.2 | Land Legal: Portions of Land being returned to Seller
1.1.4.2 (a) | Erf 198 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  | 2 months
1.1.4.2 (b) | Rem of Ptn 7 of Erf 15 Edendale | The property is owned by the Msunduzi Municipality and was acquired from Fred Tshablala. | 1. Engage Mdu (Legal) 2. Report to SMC | R10 000 Excluding Survey, SPLUMA, & Transfer | 8522 |  | 2 months
1.1.4.2 (c) | Ptn 11 of Erf 118 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Prepare SPLUMA Application 2. Obtain sub-divisional consent 3. Obtain approved SG Diagram 4. Transfer to "Owner" | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  | 2 months
1.1.4.2 (d) | Erf 22, 23 &24 Wilgefontein | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  | 2 months
1.1.4.2 (e) | Erf 142 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  | 2 months
1.1.4.2 (f) | Erf 52 & 53 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  | 2 months
1.1.4.3 | State Land/ Intergovernmental Relations
1.1.4.3.1 | Letter of KZN Public Works re: State Land | GEVDI requested that GeoAfrika prepare a letter for KZN Public Works with reference to the State Land Reversion transfers. | 1. Report to SMC for intervention |  | 4261 |  | 2 weeks
1.1.4.3.2 | Letter to DRDLR re: Business Plan & LTAC | GEVDI requested that GeoAfrika prepare a letter for DRDLR, it was deemed prudent that this letter address a number of issues that the project was facing & serve as the submission of the properties for the R20million funding as per the MOA with DRDLR | 1. Report to SMC for intervention |  | 8522 |  | 1 month
1.1.4.3.3 | Letter to HDA re: GISC Meetings, State Land & Implementation Protocol. | GEVDI requested that GeoAfrika prepare a report on all HDA land in Edendale. This was to be supported by maps from GIS. | 1. Report to SMC for intervention |  | 8522 |  | 1 month
1.1.4.3.4 | COGTA: Complaint Against Msunduzi - Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | 1. Once resolution from Council, the matter will be progressed via COGTA |  | 17044 |  | 2 months
1.1.4.3.5 | State Land: Request for Donation from HDA : Erf 207 Edendale | GEVDI requested assistance with the acquiring of this property from HDA. | Refer to item above re: Letter to HAD |  | 0
1.1.4.4 | Investigative & Legal Opinon/ Intervention
1.1.4.4.1 | Investigation: Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | 1. Review file and establish status 2. Establish facts with reference to LTAC 3. Report to SMC - Rates 4. Formalise matter with LTAC if appointed |  | 12783 |  | 2 months
1.1.4.4.2 | Investigation: Erf 519 &2754 Edendale N | Submit status report only | 1. Reivew file 2. Detail legal process to resolve 3. Report to SMC | R20 000 exluding court, survey, SPLUMA, & Transfer costs | 17044 |  | 2 months
1.1.4.4.3 | Erf 558 Ashdown | Mrs Muthwa claimed that she was the owner of the property which is currently occupied by Mr B Zondi. | 1. Review File 2. Prepare revised report to SMC |  | 12783 |  | 1 month
1.1.4.4.4 | Erf 855 Edendale N | Msunduzi Municipality is operating a quarry on Erf 855 Edendale without permission from the property owner. | 1. Review file 2. Prepare report to SMC 3. Detail which tranche CAPEX to come from 4. Lease |  | 21305 |  | 1 Month
1.1.4.4.5 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 17044 |  | 2 months
1.1.4.4.6 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landonwer being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. | 1. Review evidence and previous report 2. report to SMC |  | 8522 |  | 1 Month
1.1.4.4.7 | Erf 1655 Edendale S | Update report (including recommendations) and submit to Council for Approval | 1. Review file & claim 2. Detail legal process 3. report to SMC |  | 17044 |  | 1 Month
1.1.4.4.8 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 17044 |  | 2 months
1.1.4.4.9 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | 1. Review Title 2. Report to SMC |  | 8522
1.1.4.4.10 | Bhengu//Gabela Eviction | Completion of investigation and report for further legal process to follow. | 1. Reivew approach - planning intervention 2. Obtain POA from land owners 3. Submit SPLUMA | TBD - SPLUMA | 0
1.1.4.4.11 | Slangspruit Buffer: Tenure Rectification & Fraudulent Transfer | Attend to Slangspruit Buffer: Tenure Rectification & fraudulent Transfer | 1. Review status 2. Report to SMC |  | 21305 |  | 1 Month
1.1.4.4.12 | Investigation: Erf 1655 Edendale S: Inzozoyesizwe School | Completion of investigation and report for further legal process to follow. | 1. Review File 2. Report to SMC |  | 12783 |  | 2 months
1.1.4.4.13 | Erf 68 Unit J - Imbali - Mncwabe | Mr Z Mncwabe representing the Zaca family requested GEVDI's assistance in providing a brief history for the property due to receiving a rates bill for the property. | 1. This is complete 2. Agree with GEVDI to remove |  | 0 |  | N/A
1.1.4.4.14 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | GEVDI requested that an investigation be done following a query by the Khambule Family regarding their property & people selling portions of the property in question. | 1. Review File 2. Report to SMC |  | 8522 |  | 1 month
1.1.4.4.15 | Erf 1570 Edendale Housing Development Grant | GEVDI instructed PSP to respond to a query from the Public Protector relating to the problems that the owner was having developing her site. | 1. Review file 2,. Detail what further actions are required 3. If so, prepare report to SMC |  | 8522 |  | 1 month
1.1.4.4.16 | Erf 52 Plessis Laer - Cancellation of Expropriation. | Masons attorneys approached the Municipality for assistance with the removal of a expropriation interdict over Erf 52 Plessis Laer. | 1. Consult with John Christie 2. Make application for removal | R10000.00 TBD - John Christie costs | 8522 |  | 2 months
1.1.4.4.17 | Erf 601 Edendale N - Archdiocese of Dbn Catholic Church | Chazile (City Estates & Valuations) requested assistance with historical information with reference to the sale of said property from the Municipality to the church. | 1. This is complete 2. Agree with GEVDI to remove |  | 0 |  | N/A
1.1.4.4.18 | Eviction: Magudulela & Gazu 199 Mnsinisi Road - Erf 1018 Edendale DD. | GEVDI instructed PSP to investigate & respond to a query from the CM's office. The Property in question is: 199 Mnsinisi Road - Erf 1018 Edendale DD. | 1. Review File 2. Prepare revised report to SMC |  | 12783 |  | 1 Month
1.1.4.4.19 | Tshabalala Matter Report - Properties: Erf 238 Edendale, Erf 218 Edendale, Ptn 2 of Erf 8 Edendale | GEVDI requested assistance from GeoAfrika in dealing with this matter - known as the Tshabalala Matter. | 1. Review File 2. Prepare revised report to SMC |  | 12783 |  | 1 month
1.1.4.4.20 | Expropriation Transfer of : Ptn 16 & 17 of Erf 233 Edendale | Arising from the above query, it was noted that the properties Ptn 16 & 17 of Erf 233 Edendale have not been transferred to the Municipality. |  |  | 0
1.1.4.4.21 | Erf 198 Edendale Allocation of Portion of Property | GEVDI requested an investigation to be completed into building of a site on the property for Mr Sithole & the issuing of a permission to occupy for the same. |  |  | 0
1.1.5 | 2019/2020 GEVDI Specific Instructions
1.1.5.1 | Investigative & Reporting Matters
1.1.5.1.1 | Ptn 168 of Farm Wilgefontein No. 869 - FT (Bhoola Property) | This property is owned by the municipality and has 59 people residing on it according to the councillor. The structures that have been built are formal for the most part and appear orderly developed on the site. The remedy that the residents want is for the municipality to pass individual title of these properties to them and for them to be able to access municipal services that are currently not available to them. The site is municipal owned and the residents claim that they have resided over 30 years on the property, is there any merits for prescription on this site?- We request that GeoAfrika please advise the municipality on this matter in terms of how it can be resolved and what are the duties of the municipality in this situation. Further to that, we request that lines of responsibility in the municipality and government be clearly defined, in terms of the role that each individual department will play in resolving this issue. This is of critical importance as at times lines of individual functions become a grey area and at times departments abdicate their responsibility due to lack of clarity policy wise of their respective functions/ obligations. The setting out of steps that need to be taken to address will be of great help. The ultimate objective of this matter is simply to give people individual title and also give them access to services. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 | 2 monts
1.1.5.1.2 | Erf 159 Edendale J | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 | 2 monts
1.1.5.1.3 | Ptn 357 of the Farm Wilgefontein No. 869 - FT | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 | 2 monts
1.1.5.1.4 | Remainder of Erf 16454 Plessis Laer | The site is owned by the municipality and is part of the Edendale town centre radius adjacent to the Edendale Mall and it on Mount Partridge Road. The structure built on the site are formal and orderly developed. The Informal Settlements Relocation Strategy project was undertaken by the municipality and recommended that we formalise the structures. However, a policy position on this matter is not available on the steps needed to do this and the responsibility of each line department concerned in giving effect to individual title. The site has 236 structure on it, which have limited access to water and use pit latrines. 59 households which are situated on either side of mount partridge were built using a government grant that was given to people in 1993 by the Department of Development Aid (DDA), the grant was to the value of R750 and land was made available to the recipients of the grant to build formal structures, which they did. The remainder of the 184 settled on the land without any grant or consent and the structures grew organically albeit formally. The recipients of the grant have PTOs and there is an unregistered GP over these properties (Alan would have to confirm) We request that you please set out the legal procedures that would be needed to formalise the area and functions and responsibilities of the various departments. These legal procedures will certainly begin to set a policy context on these matters moving forward not only for GEVDI but also the municipality especially our Human Settlements Department. Also set out the difference aspects that apply to the resident that received government aid and PTOs , and the one that built on their own with this consent. | Actual property description -:16454 Farm Willow To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 | 2 monts
1.1.5.1.5 | Investigation: Expropriation Batch 1A: Ptn 15 of Erf 4 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 8522
1.1.5.1.6 | Investigation: Expropriation Batch 1A: Ptn 2 of Erf 101 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 8522
1.1.5.1.7 | Rates: Ptn 8 of Erf 292 Edendale (Mncwabe) | Mr Mncwabe was previously facilitated by Phili Tenza. Upon attempting to sign agreement designation to LTAC Peter Warner was discovered. Facilitation attempts were halted. Mr Mncwabe has rates owing over the property OD has met with Mr Mncwabe & explained the desingation to LTAC. Mr Mncwabe has met with rates & DALARD re: the appointement of the LTAC. (carried over from 2019) | 1. Meet with LTAC/ DRDLR 2. Formalise letter to LTAC / DRDLR |  | 8522 |  | 1 month
1.1.5.1.8 | Land Legal Opinion - Town Centre Legal Opinion from Advocate & Effect on Valuations Policy Amendment | GEVDI requested input from GeoAfrika on how the Advocate (Christison) opinion with respect to the relocations in the Town Centre, and its effect on the valuation policy. | 1. Peruse documentation & advocates Opinion 2. Compile Facts 3. If required request Counsel opinion on Valuation Policy 4. Compile report | R 150 000 incl. Possible Counsel opinion, External professional assistance. | 127830
[5 empty] | 796807 | 80000 | TOTAL | 876807

## V5.0 GEVDI L-Legal Priority (hidden)
GEVDI LAND LEGAL SCHEDULE OF PRIORITY ACTIVITIES AND COSTS - BP2020 TRANCHE 2 FUNDING
Colour Code: | [5 empty] | These are urgent matters that need to be prioritized
| Comments updated |  |  |  |  | Move to the next Tranche Funding
| Matter completed and/or closed |  |  |  |  | Matter completed Completed and/or Closed
Matter moved to next Trench Funding
Item no. | Agenda Item | Description of Activity | Activities required to bring about conclusion of matter | GEVDI Comments | Description of disbursements | Budget | Approx.. L/Legal Disbursements | Initial budget incl. Disbursements | Variance | Adjusted budget | Timeframe for completion | Comments | Hours incurred to date |  |  |  | Rate |  |  |  | Budget Remaining
1 | Land Legal | [11 empty] | PH | OD / JDV | JT | TC | PH | OD / JDV | JT | TC
1.1 | Land Legal: Specific Instructions
1.1.1 | DOHS Specific Instruction
1.1.1.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | 1. Review matter & Liaise with Housing (DOHS) 2. Prepare report to DOHS & SMC [Amend as per Gevdi Comments] | This is a historical matter on LLC. . Gevdi to engage DoHS to estblish status on matter Matter moved to next Tranche Funding - in the absence of an immediate and prevailing priority demand |  | 8522 |  | 8522 |  | 8522 | 1 Month
1.1.1.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | 1. Review evidence 2. Prepare report to DOHS & SMC [Amend as per Gevdi Comments] | This is a historical matter on LLC. . Gevdi to engage DoHS to establish status on matter.. Matter moved to next Tranche Funding - in the absence of an immediate and prevailing priority demand The concept of a Settlement Agreement [and the circumstances, context and contents thereof] still has to be developed and tested with SMC and provision has been made to undertake this task further in this Land Legal Schedule |  | 8522 |  |  |  |  | 1 Month
1.1.1.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | PSP to engage LMO department in dealing with the matter | 1. Review evidence 2. Prepare report to SMC [Amend as per Gevdi Comments] | This is an historical matter on LLC. No immediate and prevailing priority demand LMO unit has been engaged by way of email [March 2020] seeking an update on this matter. Subject to further engagement with LMO Unit including DoHS - Matter moved to next Tranche Funding |  | 8522 |  |  |  |  | 1 Month
1.1.2 | DALARD
1.1.3 | GISC Specific Instructions
1.1.4 | 2018 /2019 GEVDI Specific Instructions
1.1.4.1 | Donation of land / upgrading of tenure
1.1.4.1 (a) | 22 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction | Produce a consolidated report to SMC on both the transfer of the 22 and 42 properties to the Municipality. Review Budget in the context of a single consolidated report. The report should further defined what are the implication to the Municipality in conclude this transaction |  | 12783 |  |  |  |  | 1 Month
1.1.4.1 (b) | 42 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction [Amend as per Gevdi Comments] | See comments above. The report is also required to define a clear Action and Work Programme towards the conclusion of this matter, especially as this is only likely to happen in the next tranche. The Action and Work Programme allows us to follow and track the matter beyond this tranche and notwithstanding funding disruptions. |  | 21305 |  |  |  |  | 1 Month
1.1.4.1 (c) | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. This matter will be concluded by GEVDI and the Municipality. | 1. Review matter in the context of SPLUMA 2. Prepare SPLUMA application 3. Prepare report to SMC. [Amend as per Gevdi Comments] | This is a well documented historical matter and the properties vest in Municipal ownership. The project now needs to be pursued as an upgrade of an informal settlement . The Municipal Human Settlement Unit to make an application to DoHS towards the upgrading and establishment of the township. The Nedbank Properties forms part of the Town Centre Upgrade Strategy, recently adopted by Council. The Municipal Human Settlement Unit is actively implementing the above Council Resolution. Matter Completed and/or Closed - Remove from Land Legal Schedule |  | 12783 |  |  |  |  | 1 Month
1.1.4.1 (d) | Willowspruit - Donation of 7 properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction [Amend as per Gevdi Comments] | This is a historical matter where the descriptive elements are set out in a letter To be consolidated with the 22 and 42 report submission to SMC. Like in the case of the 22 and 42 properties, all that is sought at this stage is an SMC resolution to grant authority to the Municipality to conclude the transaction Review Budget |  | 21305 |  |  |  |  | 1 Month
1.1.4.1 (e) | Moved to New Section: State Land Reversion/Addendum and Support to Works 1.1.5.3
1.1.4.1 (f) | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | Completion of Donation agreement & submission to Municipality toward the opening of the township register & endorsement of Title Deeds. Mac is appointed to transfer the state land to the Municipality. John Christie is appointed to submit application in terms of ULTRA. | 1. Odwa to contact Thula Biyela and have the signing of agreement arranged 2. Prepare report to SMC to have donation confirmed 3. Instruct Conveyancer | This is an historical matter, which is sustainably documented with signifanct progress The Donation Agreement was misplaced in the General Managers Office The matter and way forward as set out in the Description of Activities is noted While the SMC report to confirm the donation is achievable within this tranche period, the ensuing activities associated with this matter may only be concluded in the next Tranche | R10 000.00 TBC - Conveyancer | 8522 |  |  |  |  | 3 Months
1.1.4.2 | Land Legal: Portions of Land being returned to Seller |  |  | Please confirm with our Land Survey Section which of these matters relating to subdivision, conveyancing and transfer has been concluded. These Items and Budget may then be removed from the Schedule.
1.1.4.2 (a) | Erf 198 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC [Amend as per Gevdi Comments] | The owner undertook to proceed with the subdivision as per the Settlement Agreement. This matter was facilitated by Municipal Land Survey Unit - Gevdi to confirm status of matter Matter has been Completed and/or Closed Remove Budget |  | 12783 |  |  |  |  | 2 Months
1.1.4.2 (b) | Rem of Ptn 7 of Erf 15 Edendale | The property is owned by the Msunduzi Municipality and was acquired from Fred Tshablala. This matter is being dealt with by MFI and is on that schedule. This is therefore closed. | 1. Engage Mdu (Legal) 2. Report to SMC [Amend as per Gevdi Comments] | Senior Manager has instructed MFI to proceed with the registration of the subdivision Remove Budget - GeoAfrika has already billed for this matter under historical cost |  | 8522 |  |  |  |  | 2 Months
1.1.4.2 (c) | Ptn 11 of Erf 118 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Prepare SPLUMA Application 2. Obtain sub-divisional consent 3. Obtain approved SG Diagram 4. Transfer to "Owner" Amend as per Gevdi Comments | These are all well dcoumented historical subdivision matters. Reference in made to a report on part shares and subdivisions prepared by Geoafrika to AG and as such required limited further investigation to detail an action plan to conclusion..Review Budget. In the first instance, and as previously requested, engage with Municipal Survey Unit and establish way forward, espically as a similar case has been experdiated by that Unit A consolidated SPLUMA may be considered dealing with all subdivisions [with a substantially amended budget and eliminate duplication of costs] Senior Manager to advise on the preparation and co-ordination of the preparation of the SPLUMA application and process Where required meet with LTAC- establish what award was made on the property | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  |  |  |  | 2 Months
1.1.4.2 (d) | Erf 22, 23 &24 Wilgefontein | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC [Amend] | See comments above | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  |  |  |  | 2 Months
1.1.4.2 (e) | Erf 142 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC [Amend] | See comments above | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  |  |  |  | 2 Months
1.1.4.2 (f) | Erf 52 & 53 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC [Amend] | See comments above | R15 000 Excluding Survey, SPLUMA, & Transfer | 12783 |  |  |  |  | 2 Months
1.1.4.3 | State Land/ Intergovernmental Relations
1.1.4.3.1 | Letter of KZN Public Works re: State Land | GEVDI requested that GeoAfrika prepare a letter for KZN Public Works with reference to the State Land Reversion transfers. | 1. Report to SMC for intervention [amend] | Gevdi to prepare report - Remove Budget |  | 4261 |  |  |  |  | 2 Weeks
1.1.4.3.2 | Letter to DRDLR re: Business Plan & LTAC | GEVDI requested that GeoAfrika prepare a letter for DRDLR, it was deemed prudent that this letter address a number of issues that the project was facing & serve as the submission of the properties for the R20million funding as per the MOA with DRDLR | 1. Report to SMC for intervention [Amend] | Gevdi to prepare report - Remove Budget |  | 8522 |  |  |  |  | 1 Month
1.1.4.3.3 | Letter to HDA re: GISC Meetings, State Land & Implementation Protocol. | GEVDI requested that GeoAfrika prepare a report on all HDA land in Edendale. This was to be supported by maps from GIS. | 1. Report to SMC for intervention [Amend] | In the main, this is the Other State Land matter that requires the intervention of HDA. This exercise has already been mapped in GIS and is a historical matter on LLC Prepare a letter from GM to HDA In general, the GM requires that before we approach SMC, we first demonstrate that we have engaged and were unsuccessful in which case we can then shown evidence is support of the resolution sought Matters relating to attendance at GISC and Implementation Protocol must be included in Report prepared by Odwa |  | 8522 |  |  |  |  | 1 Month
1.1.4.3.4 | COGTA: Complaint Against Msunduzi- Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | 1. Once resolution from Council, the matter will be progressed via COGTA | Full Council is only likely to consider this matter at its meeting in June 2020 Therefore the conclusion of this matter must be moved to next Tranche Funding Review Budget - GeoAfrika has already billed for this matter under historical cost |  | 17044 |  |  |  |  | 2 Months
1.1.4.3.5 | State Land: Request for Donation from HDA : Erf 207 Edendale | GEVDI requested assistance with the acquiring of this property from HDA. | Refer to item above re: Letter to HAD [Amend] | Prepare a separate letter from GM to HAD as this is a critical property in a Priority Housing Project Area. |  | 0
1.1.4.4 | Investigative & Legal Opinion/ Intervention
1.1.4.4.1 | Investigation: Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | 1. Review file and establish status 2. Establish facts with reference to LTAC 3. Report to SMC - Rates 4. Formalise matter with LTAC if appointed [Amend] | Refer to historically emails from Jane on this matter. • Gevdi to confirm the status of rates clerance on this matter as it appear on the municipal system - noting that this matter goes back to 2015 • Pending the above finding - a reassessment of this matter will be made • This action must be concluded prior to the meeting Geoafrika is arranging with RD&LR and LTAC – if needs be, carry this file to that meeting - if this is indeed an LTAC matter • On Rates – we are doing one single report – once the legal opinion is at hand. |  | 12783 |  |  |  |  | 2 Months
1.1.4.4.2 | Investigation: Erf 519 &2754 Edendale N | Submit status report only | 1. Review file 2. Detail legal process to resolve 3. Report to SMC [Amend] | This is a historical matter - See minutes of LLC….Conflict of Title, Double registration -with Erf 2754 and 519 Edendale N - Report to be tabled end of Jan/ Feb 2019 This matter is unlikely to be resolved in this tranche - Please move matter and budget to next tranche | R20 000 excluding court, survey, SPLUMA, & Transfer costs | 17044 |  |  |  |  | 2 Months
1.1.4.4.3 | Mrs Muthwa Erf 558 Ashddown |  |  | This matter has been investigated by Geofrika and a letter was written to the municipality advising of the sitution at had. A letter was also written to the lady and signed by the GM advising that there is no evidence of the matter.The matter is Completed and/or Closed |  | Closed
1.1.4.4.4 | Erf 855 Edendale N | The property has been materially compromised by a Quarry historically used by the Municipality. The landowner's claim seems valid. Peter to set out legal position and recommendation which will involve an acquisition of the property by the Municipality. | 1. Receive Lease for Quarry 2. Receive clarity on Housing Project 3. Memorandum to be drafted. Once 1 & 2 received. [Amend] | This is the wrong Quarry site matter. This is an old excavation site for building materials. The property concerned was compromised during that process. Not certain even if the municipality was involved.. .LLC has considered this matter and resolved not to purchase the property Prepare a letter from GM to Owner indicating the above position and his right to persue a compensation claim against the Municipality Review Budget - Geoafrika has already billed as per historic cost |  | 21305 |  |  |  |  | 1 Month
1.1.4.4.5 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. This matter will be addressed in the next Tranche Funding. | 1, Review file 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) [Amend] | . Here are file notes: • Report dated 7 April 2016 was tabled with the LLC – 06/05/2016 • This matter will require funding for a High Court application • Report to be distributed again • Budget to be drafted for High Court Application • Funding to be secured • Instruction from GEVDI to continue with the High Court Application to be given in writing • High Court Application Remove from this Tranche – to be dealt with in the Next Tranche |  | 17044 |  |  |  |  | 2 Months
1.1.4.4.6 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landowner being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. This matter will be dealt with by GEVDI and accordingly closed. | 1. Review evidence and previous report 2. report to SMC [Amend] | This matter to be dealt with by Gevdi. This is more an internal matter and we must be able to work the system to resolve. Write to Jane – she refers to a …. previous report…. obtain a copy of that and let’s see how we go. Remove from Schedule. Remove Budget |  | 8522 |  |  |  |  | 1 Month
1.1.4.4.7 | Moved to New Section: State Land Reversion/Addendum and Support to Works 1.1.5.3
1.1.4.4.8 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval. •Conflict of title previously reported at LLC. • A budget was tabled at LLC in order to deal with the rectification of titled this included the; Appointment of a professional surveyor for the survey and drafting of the necessary in terms of KZN Planning and Development Act No. 6 of 2008 • Insufficient funding to proceed with this rectification in previous tranche • Budget to be readjusted & tabled • Secure funding in order to continue with rectify conflict of title • PSP (MHP) to undertake Survey work & PDA application as per tabled budget. This matter will be addressed in the next Tranche funding. | 1, Review file 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) [Amend] | • Conflict of title previously reported at LLC. • A budget was tabled at LLC in order to deal with the rectification of titled this included the; Appointment of a professional surveyor for the survey and drafting of the necessary in terms of KZN Planning and Development Act No. 6 of 2008 • Insufficient funding to proceed with this rectification in previous tranche • Budget to be readjusted & tabled • Secure funding in order to continue with rectify conflict of title • PSP (MHP) to undertake Survey work & PDA application as per tabled budget. No further action required in this Tranche. Carry over to the next Tranche Remove Budget applicable to this tranche - Geoafrika has already billed under historical cost |  | 17044 |  |  |  |  | 2 Months
1.1.4.4.9 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | 1. Review Title 2. Report to SMC [Amend] | This was a high court matter Unless it is a finding of the High Court or a resolution of a SMC report and that it can be dealt with in this trance - Move to next Tranche Funding |  | 8522 |  |  |  |  | To be determined
1.1.4.4.10 | Bhengu//Gabela Eviction | Completion of investigation and report for further legal process to follow. | 1. Review approach - planning intervention 2. Obtain POA from land owners 3. Submit SPLUMA [Amend] | Gevdi to deal with the land acquisition component only The SPLUMA must be reconciled with the work that is being done on Unit H In fact it must be carried and be billed against that project as the cause of the myham Remove from Land Legal Schedule | To be determined - SPLUMA | 0 |  |  |  |  | To be determined
1.1.4.4.11 | Slangspruit Buffer: Tenure Rectification & Fraudulent Transfer | Attend to Slangspruit Buffer: Tenure Rectification & fraudulent Transfer | 1. Review status 2. Report to SMC | It is unfournate that this matter has been part of LLC forever and ever and unresolved. It is s clearly documented [see Item 10.5.1 (b)] What would be the recommendation to SMC .that while we have a frudulent transactionthat would leave the old lady in a no better position, We need to recommend that our Human Settlement in terms of OSS allocate a site to her |  | 21305 |  |  |  |  | 1 Month
1.1.4.4.12 | Investigation: Erf 1655 Edendale S: Inzozoyesizwe School | Completion of investigation and report for further legal process to follow. | 1. Review File 2. Report to SMC [Amend] | Duplication of item |  | 12783 |  |  |  |  | 2 Months
1.1.4.4.13 | Erf 68 Unit J - Imbali - Mncwabe | Mr Z Mncwabe representing the Zaca family requested GEVDI's assistance in providing a brief history for the property due to receiving a rates bill for the property. | 1. This is complete 2. Agree with GEVDI to remove | Agreed. This item may now be removed |  | 0 |  |  |  |  | N/A
1.1.4.4.14 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | GEVDI requested that an investigation be done following a query by the Khambule Family regarding their property & people selling portions of the property in question. | 1. Review File 2. Report to SMC [Amend] | This item has been investigated by Geoafrika and a report to SMC with recommendation was prepared by Odwa. The municpality has tried to advance the matter with legal but has not received a lot of success as we were instructred to write a universal report for the matter. the action required on the matter is for GeoAfrika to meet with legal on the report and explain as the legal merits of the recommendations are not easily communicated by GEVDI. A letter has been requested [Nkululeko you make this comment - what letter has been request and from whom] |  | 8522 |  |  |  |  | 1 Month
1.1.4.4.15 | Erf 1570 Edendale Housing Development Grant | GEVDI instructed PSP to respond to a query from the Public Protector relating to the problems that the owner was having developing her site. | 1. Review file 2,. Detail what further actions are required 3. If so, prepare report to SMC [Amend] | Odwa has prepared a response [letter to Public Protector's Office] and to date…I am not aware of any feedback from the PP office. Please can you incorporate and include this matter as part of the Unit H project, which involves re-planning and so on. Accordingly, this matter may now be removed from the GEVDI Land Legal Schedule. Item billed under Geoafrika's historic cost - remove budget |  | 8522 |  |  |  |  | 1 Month
1.1.4.4.16 | Erf 52 Plessis Laer - Cancellation of Expropriation. | This matter has received substantial intervention. The matter should be resolved within the next two weeks provided the Deeds Office accepts the documents/application prepared by the specialist conveyancer, John Christie. | 1. Consult with John Christie 2. Make application for removal | Remove and Review Budget | R10000.00 To be determined - John Christie costs | 8522 |  |  |  |  | 2 Months
1.1.4.4.17 | Erf 601 Edendale N - Archdiocese of Dbn Catholic Church | Chazile (City Estates & Valuations) requested assistance with historical information with reference to the sale of said property from the Municipality to the church. | 1. This is complete 2. Agree with GEVDI to remove [Amend] | While the church has requested a refund , the matter may be removed pending further assistance required from GEVDI . Zie to direct the matter to Chazile for further attention. |  | To be determined |  |  |  |  | Further Queries have arisen on this matter. Budget to be determined.
1.1.4.4.18 | Eviction: Magudulela & Gazu 199 Mnsinisi Road - Erf 1018 Edendale DD. | GEVDI instructed PSP to investigate & respond to a query from the CM's office. The Property in question is: 199 Mnsinisi Road - Erf 1018 Edendale DD. | 1. Review File 2. Prepare revised report to SMC [Amend] | If this is a City Manager Office query and also an eviction – why has it not been attending to? How old is this matter? Is this on MFI’s DD Case File Schedule? Mtho – please speak to Nkululeko – get the latest case file list from MFI. Have we been cited as a Respondent? Is this matter before court? Do we need to adopt a principle position around Evictions and present to SMC? |  | 12783 |  |  |  |  | 1 Month
1.1.4.4.19 | Tshabalala Matter Report - Properties: Erf 238 Edendale, Erf 218 Edendale, Ptn 2 of Erf 8 Edendale | GEVDI requested assistance from GeoAfrika in dealing with this matter - known as the Tshabalala Matter. Odwa has passed this onto Peter who will update Zi and Nkululeko. | 1. Review File 2. Prepare revised report to SMC [Amend] | What is the outcome that theTshabalala family.seeks in order to define the action and way forward. |  | 12783 |  |  |  |  | 1 Month
1.1.4.4.20 | Expropriation Transfer of : Ptn 16 & 17 of Erf 233 Edendale | Arising from the above query, it was noted that the properties Ptn 16 & 17 of Erf 233 Edendale have not been transferred to the Municipality. This matter is on MFI Schedule and requires specific attention as per the schedule. This matter is therefore closed. |  | Remove – This matter is on MFI List | [6 empty] | Further Queries have arisen on this matter. Budget to be determined.
1.1.4.4.21 | Erf 198 Edendale Allocation of Portion of Property | GEVDI requested an investigation to be completed into building of a site on the property for Mr Sithole & the issuing of a permission to occupy for the same. |  | Duplication - Remove |  | 0
1.1.5 | 2019/2020 GEVDI Specific Instructions
1.1.5.1 | Investigative & Reporting Matters
1.1.5.1.1 | Ptn 168 of Farm Wilgefontein No. 869 - FT (Bhoola Property) | The above matters have been thoroughly investigated. A meeting with GEVDI on 13th March traversed these matters. It was agreed that the advice sought would be approached holistically across all the properties with the objective of tabling a response and development strategy having regard to the complex land/legal on site circumstances evident. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | This is a priority matter that has been discussed in recent meetings and needs to be resolved to the degree that all the obligations of GEVDI are exstinguished. The remedy sought is explained in the letter sent to GeoAfrika by GEVDI and the procedural elements need to be set out in order to resolve the matter. Consolidate into one application 1.1.5.1.1 to 1.1.5.1.4 Prepare a Development Framework and report to SMC defining roles and responsibilities and implications on various and relevant Business Units Make adequate provision for social faciltation | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 |  |  |  | 2 Months
1.1.5.1.2 | Erf 159 Edendale J | The above matters have been thoroughly investigated. A meeting with GEVDI on 13th March traversed these matters. It was agreed that the advice sought would be approached holistically across all the properties with the objective of tabling a response and development strategy having regard to the complex land/legal on site circumstances evident. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | This is a priority matter that has been discussed in recent meetings and needs to be resolved to the degree that all the obligations of GEVDI are exstinguished. The remedy sought is explained in the letter sent to GeoAfrika by GEVDI and the procedural elements need to be set out in order to resolve the matter. | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 |  |  |  | 2 Months
1.1.5.1.3 | Ptn 357 of the Farm Wilgefontein No. 869 - FT | The above matters have been thoroughly investigated. A meeting with GEVDI on 13th March traversed these matters. It was agreed that the advice sought would be approached holistically across all the properties with the objective of tabling a response and development strategy having regard to the complex land/legal on site circumstances evident. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | See Comment Above | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 |  |  |  | 2 Months
1.1.5.1.4 | Remainder of Erf 16454 Plessis Laer | The above matters have been thoroughly investigated. A meeting with GEVDI on 13th March traversed these matters. It was agreed that the advice sought would be approached holistically across all the properties with the objective of tabling a response and development strategy having regard to the complex land/legal on site circumstances evident. | Actual property description -:16454 Farm Willow To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | See Comment Above | R40 000.00 Disbursement: R20 000 for legal opinion | 51132 | 20000 |  |  |  | 2 Months
1.1.5.1.5 | Moved to Section 1.1.5.5 LTAC
1.1.5.1.6 | Moved to Section 1.1.5.5 LTAC
1.1.5.1.7 | Moved to Section 1.1.5.5 LTAC
1.1.5.1.8 | Land Legal Opinion - Town Centre Legal Opinion from Advocate & Effect on Valuations Policy Amendment | GEVDI requested input from GeoAfrika on how the Advocate (Christison) opinion with respect to the relocations in the Town Centre, and its effect on the valuation policy. Peter has perused the legal opinions and requires a working session with GEVDI and Legal to unpack these properties. This affects transactions on MFI Schedule. | 1. Peruse documentation & advocates Opinion 2. Compile Facts 3. If required request Counsel opinion on Valuation Policy 4. Compile report | No further Work required - The relocation and potential claims is only likely to emerge after June - Move to next Tranche funding As discussed we will apply the Eastern Cape experience in respect of relocations and claims and compensation - As suggested we will apply the 80/20 rule and deal with individual compensation claims Review Budget | R 150 000 incl. Possible Counsel opinion, External professional assistance. | 127830 |  |  |  |  | To be determined
1.1.5.1.9 | Land Legal Opinion: Mduduzi Municipality SPLUMA Bylaws and the effect on GEVDI. | Comments and 'draft' amendments have been provided. This matter is closed. | 1. Peruse drafted bylaws 2. Provide comments on bylaws. If necessary, meeting with planning to discuss concerns. 3. Determine how bylaws will effect matters at hand. | Comments and Admendments submitted to Planning Unit Matter Completed andor Closed |  | To be determined
1.1.5.1.10 | Moved to Section 1.1.5.5 LTAC
1.1.5.1.11 | Moved to New Section: State Land Reversion/Addendum and Support to Works 1.1.5.3 1.1.5.3
1.1.5.1.12 | Legal Opinion: Loss of Entitlements by Land Owners due to Municipality PSI Developments on Private Land | I have briefed Jacques from our office who will compile a formal brief for Advocate Randles. The legal opinion and/or memorandum pursuant to the opinion will then be workshopped with GEVDI and Mdu with the view to tabling a SMC report in early April. This will have a material impact on the private land acquisition initiative both with respect to historical transactions not yet concluded, the current Tranche 2 transactions. | 1. Brief HSG to compile a formal brief for Advocate 2. Workshop once legal opinion is compiled | Senior Manager to approve |  |  | 20000 |  | 10000
1.1.5.1.13 | Investigation: Erf 851 Edendale N | The matter was investigated and discussed at the meeting at GEVDI on the 13th March. A letter was transmitted to the Public Protector. The matter however requires further legal scrutiny in the context of the Expropriation Act, Act 63 of 1975 (Expro Act) Section 12. Peter will therefore propose that a settlement agreement be concluded and seek such authority via SMC. Carry into Tranche 3. Paragraph 7 of letter to Public Protector may create a problem for the Municipality. Instruction to be confirmed | 1. Investigate property 2. Draft report 3. Draft Settlement Agreement | Ho Odwa and Peter and Zie. A reply was submitted to the PP’s Office. Waiting a response – No further action at this stage required. |  |  |  |  | 10000
1.1.5.1.14 | Legal Opinion: Use of Servitude of Habitatio to address Retention of Land Owners Dwelling(s) | Given the need to steer clear from creating unnecessary sub divisions of properties being acquired and which then have a substantial prejudicial impact on the planned/affected housing project, an alternative legal and defendable solution is needed to address this issue going forward. A legal opinion will be sought from a specialist conveyancer. The opinion will be supported by a memorandum and which will then be workshopped with GEVDI and Mdu. It will be determined as to whether this then requires SMC approval. | 1. Instruction to conveyancer for legal opinion 2. Workshop opinion with GEVDI & Legal (Mdu) | Senior Manager was briefed. Atkins to approve |  |  | 40000 |  | 40000
1.1.5.1.15 | Vesting Transfers
1.1.5.1.16 | Legal Opinion: Use of Servitude of Habitatio to address Retention of Land Owners Dwelling(s)
1.1.5.1.17 | Legal Opinion: Rates
1.1.5.2 | 2019/2020 Reports
1.1.5.2.1 | SMC Report: Inception Report & SAC | Prepare report re: inception report and funds from DOHS. | 1. Prepare report 2. Forward to Municipality | Completed and billed |  |  |  |  | 10000
1.1.5.2.2 | COGTA: War Room: Land Acquisition Report & Presentation | GEVDI requested a report detailing the land acquisition under the Edendale Land acquisition Initiative utilising the DOHS Grant Funding. | Investigate properties acquired, compile report, compile presentation | Completed and billed |  |  |  |  | 15000
1.1.5.2.3 | Progress Meeting: Report re: GISC & LLC for SMC | As per War Room Meeting of 03/03/2020. Odwa to draft a report to SMC re: GISC meeting, the history of LLC and the Implementation Protocol. | 1. Prepare report, 2. Forward to Municipality | Completed and billed |  |  |  |  | 4500
1.1.5.3 | State Land Reversion/Addendum and Support to Works
1.1.5.3 (a) | Erf 1655 Edendale S | See Geoafrika email - 26 March 2020 The matter will require further discussion with KZN Works; What was considered was: (a) A Road across Erf 1655 must be provided for as a ‘Right of Way’ or the Road could form a boundary to a sub-division that would provide for the school; and (b) The informal settlement on the property and that within the ‘Main Road Corridor’. The option may be to relocate this settlement onto Erven 150 and 151 in terms of a housing project. Accordingly then these properties should be retained by the Municipality. | 1. Review file & claim 2. Detail legal process 3. report to SMC [Amend] | To be dealt with as part of the Reversion Addendum An item for the Reversion Addendum has been introduced All budgets [iro individual properties] to be clustered under that item |  | 17044 |  |  |  |  | 1 Month
1.1.5.3 (b) | Musi Thuzi School: Ptn 7 of Erf 206 Edendale | Whilst this was discussed at length at the pre-meeting, it was again discussed with the Representative from KZN Department of Social Development (“Social Development”) given that they have a particular interest in two of the unregistered portions covering their facility; It must be again noted that: (a) KZN Works’ interest in this matter lies with the fact that the School which is situated on an unregistered portion and the social facility (also situated on 2 unregistered portions , one which is a Road, were developed many years ago on privately owned land, and which is owned by the Late Estate Chief Minny family; and (b) The Municipality’s interest in the matter lies with the unregistered Road Portion which is also impacted on by the IRPTN; 6.3 The Chief Minny family is anxious to resolve all aspects as they relate to the original property; 6.4 The Town Planning scheme over the property confirms the Municipality’s interest with respect to the road requirements; 6.5 It is clear from the above that the current unregistered portions of the parent property cannot simply be registered/transferred in order to respond to the interests and requirements of the parties involved; The interests/requirements of the parties can only be fully realised if: (a) A new layout is produced and discussed and agreed to by the parties; (b) A Settlement Agreement is prepared and which ‘maps’ out the conclusion, costs and ‘who pays for what’ in order to enable the matter to be concluded and transfers effected; (c) A workshop of the Settlement Agreement in order to reach consensus; and (d) On reaching consensus, the aspect of ‘signing authority’ wrt the Settlement Agreement to be entered into is attended to. | [See Description of Activities and Gevdi Comments] | Prepare a Letter from GM to Works which presents a way forward on this matter [as per Description of Activities]. The letter must set out the obligations and estimated cost implications to all parties. It is also important that the milestones and deliverables are tied to a time line The letter must also indicate that we are available for further discussions [It is very likely that the letter would trigger a call/request for a meeting] Allow Work's to digest and consider the proposed Solution/Remedy and seek the necessary approvals from they end. [administrative structures - which is only likely to occur post this tranche funding]] The strategy is for Works to be pursuing the conclusion of the land transaction By way of the above letter we have effectively dealt with this matter - pending further actions/response from Work |  | 8522 |  |  |  |  | 1 Month
1.1.5.3 (c) | HDA & PW: Ptn 84 of Erf 5 Edendale : Kwahlengabantu Hospital | This matter will be managed in the "Master Schedule": Reversion of State Land with KZN Public Works. |  | The Kwahlengabantu Hospital sits on Municipal Land for which a subdivision application was created. This matter was driven by LLC. There has been a change in circumstances with the emergence of the Town Centre where the the extent of Kwahlengabantu Hospital land has now being defined as per the new Town Centre planning layout. The Municipalitynow seeks to retain the front section of the property onto Edendale Road given its high real estate value. This subdivision of the Hospital land and land use layout willl be formalised by way of the Town Centre Phase 2 Spluma application. Works now seeks clarity on the future use of the Hospital land. At this stage the extent and availability of the remaining land of the Hospital in the context of the planning and SPLUMA proposals needs to be communicated to Works. The SPLUMA Phase 2 application will be prusued by the Municipality after June |  | To be determined
1.1.5.3 (d) | Public Works Reversions | Previously item 2.2.3.1 on Land Acquisition Schedule | Complete review of properties with Municipality and Public Works. Receive formal acceptance from Public Works on those properties that can be transferred in the interim. Submit memo to Council. Instruct Conveyancer to proceed with transfers in batches as agreement is reached. |  |  | 25000 |  |  |  |  | March
1.1.5.3 (e) | Land Identification, Donation and Business Plans: Donation of Land [Government Dept: Public Works Reversions] | The general schedule was discussed and various changes agreed to in order to create a “Master Schedule” as the management tool going forward; and In the absence of KZN Works attendance, the outstanding tasks by KZN Works will be re-communicated to KZN Works via the updated Master Schedule and any relevant commentary thereto. |  |  |  | To be determined
1.1.5.3 (f) | Addendum to Reversion MOA | This will be prepared once consensus has been reached between the Municipality and KZN Works on all Reversion Properties in line with the Master Schedule. |  |  |  | To be determined
1.1.5.3 (g) | Sbongamandla Junior Primary School | The intervention/support required by Works is still to be defined |  |  |  | To be determined
1.1.5.3 (h) | Ward 13 - Proposed Community Hall | This matter will need further discussion with KZN Works and will inform the Addendum to the Reversion MOA still to be compiled. |  |  |  | To be determined
1.1.5.3 (i) | Edendale Hospital Entrance and Planned Road Network | This matter was discussed in the context of the Edendale Town Centre Layout; The above will impact upon the SPLUMA Phase 2 application; Consensus, if reached, with KZN Works will need to be recorded in an agreement; GeoAfrika to be instructed with respect to the Agreement; and This will be added to the Land/Legal Schedule |  | See comments above and tie into the SPLUMA Town Centre Phase 2 |  | To be determined
1.1.5.3 (j) | Pata Place of Safety | This matter is impacted upon by the Unit-H Restoration Grant Project which is underway; KZN Works and Social Development have an immediate need to undertake an upgrade project to the existing facility, situated on this Property; This matter will accordingly be added to the Land/Legal Schedule in order to provide for: (a) Preparation of and providing Social Development with the requisite Power of Attorney; (b) The expansion of the facility and determination of a ‘new outside figure’ to accommodate the extended facility; and (c) The above in the amended Unit H layout. The final transfer to KZN Works of the resulting property will be effected via the Unit H Project. KZN Works will be required to cover all the transfer costs as per Proclamation 84 |  |  |  | To be determined
1.1.5.4 | Land Legal: MFI Matters
1.1.5.4. (a) | Matthew Francis Inc (MFI) Matters requiring legal assistance | Management and Coordination of MFI Master Schedule and progressing matters until transfer. Matter previously item 2.1.7 on Land Acquisition Schedule. | As per Schedule |  | R15000 PM. | 60000 | 2000 |  |  |  | Monthly
1.1.5.4 (b) | Land Acquisition: Rates Clearance. Properties with MFI requiring transfer | GeoAfrika prepared a report re: the clearance of all rates (May 2019) Report has been provided to the legal department. Matter Previously item 2.1.7(a) on Land Acquisition Schedule | 1. Meet with legal confirming legislation & approval to rates write off 2. Amendments to report 3. Table report with SMC. |  |  | 15000 |  |  |  |  | March
1.1.5.5 | Land Legal: LTAC Matters
1.1.5.5 (a) | LTAC Matters | Management and Coordination of LTAC Master Schedule in order to progress the succesful acquisition and transfer of properties to the Municipality. | As per Schedule | [7 empty] | Monthly
1.1.5.5.(b) | Ptn 3 of Erf 351 Edendale TG Kunene LTAC: Thami Mabaso | The matter was traversed at the meeting at GEVDI on 13th March. Zi will provide Peter with the account. Peter to prepare a notice to Estates at CFO for GM to issue. Given that this was however also a property designated and assigned to LTAC. The matter will be raised at the proposed meeting with the LTACs via DRDLR. Notice still to be prepared Previously matter number1.1.5.1.10 | 1. Meeting with RDLR 2. Action arising from meeting | While an award has been made, the owner is still receiving a rates account.It was a simple matter to be resolved by GEVDI. |  | To be determined |  |  |  |  | To be determined
1.1.5.5 (c) | Investigation: Expropriation Batch 1A: Ptn 15 of Erf 4 Edendale | We are compiling a Master Schedule of all properties designated into separate categories. This will be used to inform the meeting with DRDLR and LTAs (still being arranged) Previously matter number1.1.5.1.5 | 1. Formal response to Attorney 2. Meeting with DRDLR & LTAC | Please compile a list of cases and matters from the Schedule we will be discussing with LTAC and RD&LR. Please compile into an Agenda. |  | 8522 |  |  |  |  | To be determined
1.1.5.5(d) | Investigation: Expropriation Batch 1A: Ptn 2 of Erf 101 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC. Previously matter number1.1.5.1.6 This matter will be tabled with DRDLR and LTACs at the meeting being arranged. | 1. Meet with LTAC 2. Formalise letter to LTAC | This is more than an LTAC matter – It involves the subdivision of a section of the property and the return of the property to owner. This is a classic example of the establishment of a road network as per the Scheme. We need to look at the entire road over many property and consider the acquisition and expropriation of those sections only. Carry into Land Acquisition 3 Year Business Plan. |  | 8522 |  |  |  |  | To be determined
1.1.5.5 (e) | Rates: Ptn 8 of Erf 292 Edendale (Mncwabe) | This matter was investigated and discussed at the meeting at GEVDI on 13th March. The property is also designated and assigned to a LTAC. The matter will be tabled at the meeting being championed with the LTACs via DRDLR. The matter however does not end there. This property impacts on future planning of the area and may require to be acquired. We are engaged with Mncwabe, the DRDLR and Peter Warner in order to establish the "Estate Transfer" Previously matter number1.1.5.1.7 | 1. Meet with LTAC/ DRDLR 2. Formalise letter to LTAC / DRDLR | This matter is at hand. It has been dealt with by Odwa There is an entire strip of properties [including the Mncwabe land], which must be considered for acquisition. Pradeep: The 3 Year Business Plan must include these properties. It might already be in there. Please confirm. |  | 8522 |  |  |  |  | 1 Month
Items from GEVDI [Zie] - details/ instruction to be confirmed in order to place on schedule.
| Property 238/0 and Property 283/35 | Narain to provide information |  |  |  | To be determined
| Erf 785/384 JG Shembe Family | There is an invasion on this property, the Shembe Family is receiving rates for a property that they have lost control. An investigation was requested, the municipality was further requested to intervene in assisting the family get control over their land/ possibly purchase the property. |  | Zie This the general edendale scenario [land invasion and rates matter] How does this property tie in and fit into the Land Acquisition Programme Have you interogated the property and established it feasibility and its inclusion into the Land Acquisition programme Does it need to be included in the 3 Year Land Acquisition Business Plan |  | To be determined
| Erf 2876 Edendale H - Princess Nonhlahla Mabele | A road goes through her property, there are two RDP houses on the site in question, however she has a tittle deed, but doesn't live there and she cant apply for another RDP House as shes listed as a beneficiary. She is represented by Singh Attorneys |  | To be refered to the Unit H project. Remove from Gevdi Land Legal Schedule |  | To be determined
| Erf Ptn 13, 16, 17, 20, 22, 25 and 23 | I don't have any details relating to this property, however we were told by the owner of Ptn 2 of ERF 292 that they have a rates issue as well. An investigation is needed, on whether this matter was it deal |  | Zie Establish if rates are being paid on these properties Is there a Settlement Agreement Are there LTAC involved Social facilitation required to indicate to owners that they are still liable for rates and service charges Are these properties identified for acquisition in the 3 Year Land Acquisition Business Plan |  | To be determined
| Ptn 1 of Erf 292 | Ptn 5 of ERF 292 is a similar case to Ptn 2 of ERF 292, whereby the family was approached by the Municipality to purchase the property, the issue of rates was further discussed the family was then under the impression that they shouldn't pay rates since the municipality will buying the property. |  | See comment above |  | To be determined
| Erf 227 |  |  |  |  | To be determined
| Erf 206 |  |  |  |  | To be determined
Ptn 27, 28, 29 of Erf 21

## V5.2 GEVDI L-Legal Priority
MSUNDUZI MUNICIPALITY
Sustainable Development & City Enterprises
GEVDI: Greater Edendale Vulindlela Development Initiative
GEVDI LAND LEGAL SCHEDULE OF PRIORITY ACTIVITIES - BP2020 TRANCHE FUNDING
Item no. | Agenda Item | Description of Activity | Activities
1 | Land Legal
1.1 | Land Legal: Specific Instructions
1.1.1 | DOHS Specific Instruction
1.1.1.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | 1. Desktop analysis (Done) 2. Produce GIS Maps (Done) 2a. Obtain historical info from GA if available 2b. If historical info is not found then may need site visit 2a. Assessement by collectiveTeam 3. Site Visit if required 4. Recommendations 5. Final input from Service provider Legal Team if required
1.1.1.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | 1. Desktop analysis (Done) 2. Produce GIS Maps (Done) 2a. Obtain historical info from GA if available 2b. If historical info is not found then may need site visit 2a. Assessement by collective Team 4. Recommendations 5. Final input from Peter if required
1.1.1.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | 1. Matter concluded 2. This matter has now been handed over to Real Estate department to take further
1.1.4 | 2018 /2019 GEVDI Specific Instructions
1.1.4.1 | Donation of land / upgrading of tenure
1.1.4.1 (a) | Assistance from HDA to Transfer State Land to Municipality”. 1.1.4.1 (a) 22 Properties 1.1.4.1 (b) 42 Properties 1.1.4.1 (d) Willowspruit 1.1.5.1.15 Vesting Transfers | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | (a & b) 1. Prepare a report to accept donation 2. Provide Legal input for the report 3. Prepare a draft donation agreement 4. Submit to Council for approval 5. Contact DoHS to facilitate the signing of the donation agreement 6. DoHS to appoint Conveyancers and facilitate the transfers (d) 1. Create a master schedule for HDA properties (Done) 2. Follow up with HDA on propeties to be transfered to the TMM from the master schedule 3). HDA to engage with DoHS on donations to reach agreement Thereafter follow process as listed above 1. Prepare a report to accept donation 2. Submit finalised report for legal input 3.Prepare a draft donation agreement 4. Submit to Council for approval 5. Contact DoHS to facilitate the signing of the donation agreement 6. DoHS to appoint Conveyancers and facilitate the transfers
1.1.4.1 (c) | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. This matter will be concluded by GEVDI and the Municipality. | 1. To source info on Nedbank properties from GEVDI 2. Prepare a draft SMC report 3. Add legal input 4. Submit report to SMC
1.1.4.1 (f) | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | 1. Registration of ESKOM servitude delayed - Prepare letter from MM by **date** 2. Registration of underlying properties - delayed due to rates - Mac 19/02/2021 3. Resolution of the above will enable the Township register to be opened - No date as yet 4. On opening of Township Register need to issue certificates by MM
1.1.4.3 | State Land/ Intergovernmental Relations
1.1.4.3.4 | COGTA: Complaint Against Msunduzi- Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | 1. P&S agreement for the remaining 1/3rd share is being concluded 2. Valuers to confirm valuation of compensation 3. Claify compensation offer with family and give them a period of 7 days to revert 4. If accepted then proceed with exchange agreement. If not accepted then ...... 5. Draft settlement agreement
1.1.4.4 | Investigative & Legal Opinion/ Intervention
1.1.4.4.1 | Investigation: Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | 1. Follow up with Rates 2. This property was included as an LTAC case file matter in error 3. Reassess this matter to take forward and may need to include in the single report on rates that will be submiited
1.1.4.4.2 | Investigation: Erf 519 & 2754 Edendale N | Submit status report only | 1. To get information on this matter 2. Check if theres any existing infiormation on this matter.
1.1.4.4.4 | Erf 855 Edendale N | The property has been materially compromised by a Quarry historically used by the Municipality. The landowner's claim seems valid. Peter to set out legal position and recommendation which will involve an acquisition of the property by the Municipality. | 1. Prepare a report 2. Add egal input to report 3. Submit to internal legal and then SMC 4. If approved by Full Council then add to Tranche 3 land acquisition
1.1.4.4.5 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. This matter will be addressed in the next Tranche Funding. | 1. Move to next tranche
1.1.4.4.6 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landowner being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. This matter will be dealt with by GEVDI and accordingly closed. | 1. Source previous report 2. Provide GIS map and investigate matter 3. Make recommendations based on investigations
1.1.4.4.8 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval. This matter will be addressed in the next Tranche funding. | 1. Move to next tranche
1.1.4.4.9 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | 1. This matter was done as the report was submitted to SMC and in the process of gettin full Council resolution
1.1.4.4.11 | Slangspruit Buffer: Tenure Rectification & Fraudulent Transfer | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | 1. Report has been submitted to Mdu in Jul/Aug 2020 and await his comments before submitting to SMC 2. Continually follow up with Mdu by reforwarding email request to him
1.1.4.4.14 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | 1. This matter is linked to the review of the PTO policy and will be dealt with pursuant to the report 2. This report will be sent to the Municipal Human Settlements department to review 3. The report needs to be submitted to SMC by the Municipal Human Settlements department
#REF!
1.1.5 | 2019/2020 GEVDI Specific Instructions
1.1.5.1 | Investigative & Reporting Matters
1.1.5.1.1 | Land redevelopment Interventions- Complex land Legal matters - Ptn 168 of Farm Wilgefontein No. 869 - FT (Bhoola Property) | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality.
1.1.5.1.2 | Land redevelopment Interventions- Complex land Legal matters - Erf 159 Edendale J | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality.
1.1.5.1.3 | Land redevelopment Interventions- Complex land Legal matters - Ptn 357 of the Farm Wilgefontein No. 869 - FT | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality.
1.1.5.1.4 | Land redevelopment Interventions- Complex land Legal matters- Remainder of Erf 16454 Plessis Laer | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality.
1.1.5.1.8 | Land Legal Opinion - Town Centre Legal Opinion from Advocate & Effect on Valuations Policy Amendment | GEVDI requested input from GeoAfrika on how the Advocate (Christison) opinion with respect to the relocations in the Town Centre, and its effect on the valuation policy. Peter has perused the legal opinions and requires a working session with GEVDI and Legal to unpack these properties. This affects transactions on MFI Schedule.
1.1.5.1.12 | Legal Opinion: Loss of Entitlements by Land Owners due to Municipality PSI Developments on Private Land | Report Finalised: Must now be discussed with Legal and Submitted to SMC | 1. Workshop Infrastructure 2. Submit amended PSI report to SMC
1.1.5.1.17 | Legal Opinion: Rates clearance & procedure | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. Report Finalised: Must now be discussed with Finance and Submitted to SMC | 1. Get detailed comments from Mdu and GEVDI to draft Memo from GM to CFO requesting a meeting to discuss the report 2. Channel the report to SMC via CFO's office
1.1.5.2 | 2019/2020 Reports
1.1.5.2.3 | Progress Meeting: Report re: GISC & LLC for SMC | Peter to draft revised and expanded Report for SMC AFFECTED BY COVID 19 THIS WILL BE WORKED ON IN JUNE AT THE GEVDI LAND LEGAL WORKING SESSIONS | 1. Organise consultations with our communication unit
1.1.6 | Master Schedules
1.1.6.1 | State Land Reversion/Addendum and Support to Works | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality.
1.1.6.1 (a) | Management and Co-ordination of Master Schedule for State Land | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | 1. Work programe for state land reversion completed 2. GEVDI to meet with Land Survey to discuss technical details around reversion properties 16/11/2020 3. Do site verifications between Public Works and GEVDI 4. Finalise list of properties to be transfered 5. Instruct conveyancer to start with transfers
1.1.6.1 (b) | Addendum to Reversion Transfers. | The Addendum can only prepared once the the revised schedule has been adopted by the Municoaplity and KZN WORKS | 1. wait for conclusion of schedule
1.1.6.2 | Land Legal: MFI Matters
1.1.6.2. (a) | Matthew Francis Inc (MFI) Matters requiring legal assistance | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | 1. Get detailed comments from Mdu and GEVDI to draft Memo from GM to CFO requesting a meeting to discuss the report 2. Channel the report to SMC via CFO's office
1.1.6.2 (b) | Land Acquisition: Rates Clearance. Properties with MFI requiring transfer | Awaiting Council Resolution re Rates Write-Off See 1.1.5.1.17 above
1.1.6.3 | Land Legal: LTAC Matters
1.1.6.3 (a) | LTAC Matters | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. Meeting with DRDLR and LTACs : Hoping to have confirmation of meeting on Monday 22 June from DRDLR.
1.1.6.4 | Land Legal: Portions of Land being returned to Seller
1.1.6.4 (a) | Management of Master Schedule for matters where landowner has requested a sub-division. | 19 June 2020 Refer to various file notes from GEVDI working sessions which have set out what must be attended to to bring this matter to finality. | #REF!
1.1.6.5 | Land Legal Schedule review Tasks & costs
1.1.6.5.1 | Review of Land legal Schedule tasks & costs. (March 30-03 April) FIRST ROUND TO OBTAIN APPROVAL IS COMPLETE. NEED TO UPDATE THIS FOR MAY AND JUNE AND SO NEED ADDITIONAL 2HOURS PER UPDATE = R3000 TO BE ADDED TO BUDGET. | Updated 19 June 2020 | #REF!
1.1.6.6 | General
1.1.6.6 | General land legal advice and adhoc instructions. | A number of matters have been actioned in this regard by instruction from GEVDI :
(a) Nataional Treasury Guidelines Presentation - Input by Peter - Completed;
(b) Legal Opinion : Land Use Scheme on Ingonyama Land re Vulindlela - Completed;
(c) Non Delegated Municipalities Legal Advice - Completed
(d) Legal adice and drafting of memo and draft response re Un-Solicitted Offer to Purchase Ptn 37 of Erf 15 - Complete;
(e) Transfer of CAPEX and OPEX Balance of Funds to Conveyancer Trust Account - Obtain Legal Opinion and prepare draft report To MM - Complete;
(f) PSI Encroachment - Sewer Encroachment over Rem 46 Plessis Laer - Email engagement have been made with the Land Owner's daughter, Mike Greatwood, Sibonelo. This will be informed by the Legal Opinion, Memo and SMC Report once approved. The matter is however being progressed based on the advice from the Advocate.
(g) Legal Consequences in applying the Valuation Guidelines - Completed
(h) GEVDI Working Sessions : At Planning Boardroom or GEVDI Ongoing
(i) Legal Advice : Erf 457 Exchange and Matters Related Thereto- completed
(j) Erf 383 Legal Advice re Issues wrt Ownership
(k) Generic Exchange Agreement- circulated by PH
(l) Land Legal Support GEVDI : Retainer
(m) Eviction Bongi Mthethwa- ZC to update
(n) Unregistered Erf 455 Ithala Bank matter- completed
(p) SMC Report Benchmark report- completed
(q) Media Query Erf 47 Edendale T (Imbali unit 18)- refer to file note
(r) Revenue Enhancement initiative GEVDI- completed
(s) Presentation on Expros to councillors-completed
(t) Cancellation Charge Bond Erf 136 Edendale unit N- legal advise sent to real estate and the matter is now considered closed by GEVDI
(u) PTO policy SMC Report- refer to PTO policy item above
(v) Erf 851 Edendale N- Public Protector matter- completed
(w) Hand Over of land to M Human Settlement and Assets- outstanding PH to finalise report linked to (b) Section 26 Land Survey Act
|  | (x) Erf 1848 Edendale DD Micheal Nene (matter added on 12/02/2021 - PH to check email from Nkululeko sent on same date for detail) | This matter will be progressed under the PTO report, further discussion are needed on this as there is no clarity on progress
Items from GEVDI [Zie] - details/ instruction to be confirmed in order to place on schedule.
| Property 238/0 and Property 283/35 | GEVDI to provide information
| Erf 785/384 JG Shembe Family | There is an invasion on this property, the Shembe Family is receiving rates for a property that they have lost control. An investigation was requested, the municipality was further requested to intervene in assisting the family get control over their land/ possibly purchase the property.
| Erf 2876 Edendale H - Princess Nonhlahla Mabele | A road goes through her property, there are two RDP houses on the site in question, however she has a tittle deed, but doesn't live there and she cant apply for another RDP House as shes listed as a beneficiary. She is represented by Singh Attorneys
| Erf Ptn 13, 16, 17, 20, 22, 25 and 23 | I don't have any details relating to this property, however we were told by the owner of Ptn 2 of ERF 292 that they have a rates issue as well. An investigation is needed, on whether this matter was it deal
| Ptn 1 of Erf 292 | Ptn 5 of ERF 292 is a similar case to Ptn 2 of ERF 292, whereby the family was approached by the Municipality to purchase the property, the issue of rates was further discussed the family was then under the impression that they shouldn't pay rates since the municipality will buying the property.
Erf 227
Erf 206
Ptn 27, 28, 29 of Erf 21

## Sheet2
10311

## V2_Land Legal SA&C (2) (hidden)
LAND LEGAL SCHEDULE OF ACTIVITIES AND COSTS - BP2020 TRANCHE 2 FUNDING
[8 empty] | DRAFT Date: | 2020-02-11
Item no. | Agenda Item | Description of activity | Activities required to bring about conclusion of matter | Budget breakdown & possible disbursement | Budget figure | Budget reduction | Aprox. L/Legal Disbursements | Timeframe for completion | Comments
1 | Land Legal
1.1 | Land Legal: Specific Instructions
1.1.1 | DOHS Specific Instruction
1.1.1.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | 1. Review matter & Liase with Housing (DOHS) 2. Prepare report to DOHS & SMC |  | 10000 | 8522 |  | 1 month
1.1.1.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | 1. Review evidence 2. Prepare report to DOHS & SMC |  | 10000 | 8522 |  | 1 month
1.1.1.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | PSP to engage LMO department in dealing with the matter | 1. Review evidence 2. Prepare report to SMC |  | 10000 | 8522 |  | 1 month
1.1.2 | DALARD
1.1.3 | GISC Specific Instructions
1.1.4 | 2018 /2019 GEVDI Specific Instructions
1.1.4.1 | Donation of land / upgrading of tenure
1.1.4.1 (a) | 22 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 15000 | 12783 |  | 1 Month
1.1.4.1 (b) | 42 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 25000 | 21305 |  | 1 Month
1.1.4.1 (c) | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. | 1. Review matter in the context of SPLUMA 2. Prepare SPLUMA application 3. Prepare report to SMC. | TBD - SPLUMA & Planning Costs | 15000 | 12783 |  | 1 Month
1.1.4.1 (d) | Willowspruit - Donation of 7 properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 25000 | 21305 |  | 1 Month
1.1.4.1 (e) | Musi Thuzi School: Ptn 7 of Erf 206 Edendale | Assist with the relayout, survey and subdivision of the property in order to accommodate the school, owner and the IRPTN | 1. Review status & Planning 2. Prepare report to SMC |  | 10000 | 8522 |  | 1 Month
1.1.4.1 (f) | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | Completion of Donation agreement & submission to Municipality toward the opening of the township register & endorsment of Title Deeds | 1. Odwa to contact Thula Biyela and have the signing of agreement arranged 2. Prepare report to SMC to have donation confirmed 3. Instruct John Christie | R10 000.00 TBC - John Christie | 10000 | 8522 |  | 3 Months
1.1.4.2 | Land Legal: Portions of Land being returned to Seller
1.1.4.2 (a) | Erf 198 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 12783 |  | 2 months
1.1.4.2 (b) | Rem of Ptn 7 of Erf 15 Edendale | The property is owned by the Msunduzi Municipality and was acquired from Fred Tshablala. | 1. Engage Mdu (Legal) 2. Report to SMC | R10 000 Excluding Survey, SPLUMA, & Transfer | 10000 | 8522 |  | 2 months
1.1.4.2 (c) | Ptn 11 of Erf 118 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Prepare SPLUMA Application 2. Obtain sub-divisional consent 3. Obtain approved SG Diagram 4. Transfer to "Owner" | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 12783 |  | 2 months
1.1.4.2 (d) | Erf 22, 23 &24 Wilgefontein | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 12783 |  | 2 months
1.1.4.2 (e) | Erf 142 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 12783 |  | 2 months
1.1.4.2 (f) | Erf 52 & 53 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 12783 |  | 2 months
1.1.4.3 | State Land/ Intergovernmental Relations
1.1.4.3.1 | Letter of KZN Public Works re: State Land | GEVDI requested that GeoAfrika prepare a letter for KZN Public Works with reference to the State Land Reversion transfers. | 1. Report to SMC for intervention |  | 5000 | 4261 |  | 2 weeks
1.1.4.3.2 | Letter to DRDLR re: Business Plan & LTAC | GEVDI requested that GeoAfrika prepare a letter for DRDLR, it was deemed prudent that this letter address a number of issues that the project was facing & serve as the submission of the properties for the R20million funding as per the MOA with DRDLR | 1. Report to SMC for intervention |  | 10000 | 8522 |  | 1 month
1.1.4.3.3 | Letter to HDA re: GISC Meetings, State Land & Implementation Protocol. | GEVDI requested that GeoAfrika prepare a report on all HDA land in Edendale. This was to be supported by maps from GIS. | 1. Report to SMC for intervention |  | 10000 | 8522 |  | 1 month
1.1.4.3.4 | COGTA: Complaint Against Msunduzi - Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | 1. Once resolution from Council, the matter will be progressed via COGTA |  | 20000 | 17044 |  | 2 months
1.1.4.3.5 | State Land: Request for Donation from HDA : Erf 207 Edendale | GEVDI requested assistance with the acquiring of this property from HDA. | Refer to item above re: Letter to HAD |  |  | 0
1.1.4.4 | Investigative & Legal Opinon/ Intervention
1.1.4.4.1 | Investigation: Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | 1. Review file and establish status 2. Establish facts with reference to LTAC 3. Report to SMC - Rates 4. Formalise matter with LTAC if appointed |  | 15000 | 12783 |  | 2 months
1.1.4.4.2 | Investigation: Erf 519 &2754 Edendale N | Submit status report only | 1. Reivew file 2. Detail legal process to resolve 3. Report to SMC | R20 000 exluding court, survey, SPLUMA, & Transfer costs | 20000 | 17044 |  | 2 months
1.1.4.4.3 | Erf 558 Ashdown | Mrs Muthwa claimed that she was the owner of the property which is currently occupied by Mr B Zondi. | 1. Review File 2. Prepare revised report to SMC |  | 15000 | 12783 |  | 1 month
1.1.4.4.4 | Erf 855 Edendale N | Msunduzi Municipality is operating a quarry on Erf 855 Edendale without permission from the property owner. | 1. Review file 2. Prepare report to SMC 3. Detail which tranche CAPEX to come from 4. Lease |  | 25000 | 21305 |  | 1 Month
1.1.4.4.5 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 20000 | 17044 |  | 2 months
1.1.4.4.6 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landonwer being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. | 1. Review evidence and previous report 2. report to SMC |  | 10000 | 8522 |  | 1 Month
1.1.4.4.7 | Erf 1655 Edendale S | Update report (including recommendations) and submit to Council for Approval | 1. Review file & claim 2. Detail legal process 3. report to SMC |  | 20000 | 17044 |  | 1 Month
1.1.4.4.8 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 20000 | 17044 |  | 2 months
1.1.4.4.9 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | 1. Review Title 2. Report to SMC |  | 10000 | 8522
1.1.4.4.10 | Bhengu//Gabela Eviction | Completion of investigation and report for further legal process to follow. | 1. Reivew approach - planning intervention 2. Obtain POA from land owners 3. Submit SPLUMA | TBD - SPLUMA |  | 0
1.1.4.4.11 | Slangspruit Buffer: Tenure Rectification & Fraudulent Transfer | Attend to Slangspruit Buffer: Tenure Rectification & fraudulent Transfer | 1. Review status 2. Report to SMC |  | 25000 | 21305 |  | 1 Month
1.1.4.4.12 | Investigation: Erf 1655 Edendale S: Inzozoyesizwe School | Completion of investigation and report for further legal process to follow. | 1. Review File 2. Report to SMC |  | 15000 | 12783 |  | 2 months
1.1.4.4.13 | Erf 68 Unit J - Imbali - Mncwabe | Mr Z Mncwabe representing the Zaca family requested GEVDI's assistance in providing a brief history for the property due to receiving a rates bill for the property. | 1. This is complete 2. Agree with GEVDI to remove |  |  | 0 |  | N/A
1.1.4.4.14 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | GEVDI requested that an investigation be done following a query by the Khambule Family regarding their property & people selling portions of the property in question. | 1. Review File 2. Report to SMC |  | 10000 | 8522 |  | 1 month
1.1.4.4.15 | Erf 1570 Edendale Housing Development Grant | GEVDI instructed PSP to respond to a query from the Public Protector relating to the problems that the owner was having developing her site. | 1. Review file 2,. Detail what further actions are required 3. If so, prepare report to SMC |  | 10000 | 8522 |  | 1 month
1.1.4.4.16 | Erf 52 Plessis Laer - Cancellation of Expropriation. | Masons attorneys approached the Municipality for assistance with the removal of a expropriation interdict over Erf 52 Plessis Laer. | 1. Consult with John Christie 2. Make application for removal | R10000.00 TBD - John Christie costs | 10000 | 8522 |  | 2 months
1.1.4.4.17 | Erf 601 Edendale N - Archdiocese of Dbn Catholic Church | Chazile (City Estates & Valuations) requested assistance with historical information with reference to the sale of said property from the Municipality to the church. | 1. This is complete 2. Agree with GEVDI to remove |  |  | 0 |  | N/A
1.1.4.4.18 | Eviction: Magudulela & Gazu 199 Mnsinisi Road - Erf 1018 Edendale DD. | GEVDI instructed PSP to investigate & respond to a query from the CM's office. The Property in question is: 199 Mnsinisi Road - Erf 1018 Edendale DD. | 1. Review File 2. Prepare revised report to SMC |  | 15000 | 12783 |  | 1 Month
1.1.4.4.19 | Tshabalala Matter Report - Properties: Erf 238 Edendale, Erf 218 Edendale, Ptn 2 of Erf 8 Edendale | GEVDI requested assistance from GeoAfrika in dealing with this matter - known as the Tshabalala Matter. | 1. Review File 2. Prepare revised report to SMC |  | 15000 | 12783 |  | 1 month
1.1.4.4.20 | Expropriation Transfer of : Ptn 16 & 17 of Erf 233 Edendale | Arising from the above query, it was noted that the properties Ptn 16 & 17 of Erf 233 Edendale have not been transferred to the Municipality. |  |  |  | 0
1.1.4.4.21 | Erf 198 Edendale Allocation of Portion of Property | GEVDI requested an investigation to be completed into building of a site on the property for Mr Sithole & the issuing of a permission to occupy for the same. |  |  |  | 0
1.1.5 | 2019/2020 GEVDI Specific Instructions
1.1.5.1 | Investigative & Reporting Matters
1.1.5.1.1 | Ptn 168 of Farm Wilgefontein No. 869 - FT (Bhoola Property) | This property is owned by the municipality and has 59 people residing on it according to the councillor. The structures that have been built are formal for the most part and appear orderly developed on the site. The remedy that the residents want is for the municipality to pass individual title of these properties to them and for them to be able to access municipal services that are currently not available to them. The site is municipal owned and the residents claim that they have resided over 30 years on the property, is there any merits for prescription on this site?- We request that GeoAfrika please advise the municipality on this matter in terms of how it can be resolved and what are the duties of the municipality in this situation. Further to that, we request that lines of responsibility in the municipality and government be clearly defined, in terms of the role that each individual department will play in resolving this issue. This is of critical importance as at times lines of individual functions become a grey area and at times departments abdicate their responsibility due to lack of clarity policy wise of their respective functions/ obligations. The setting out of steps that need to be taken to address will be of great help. The ultimate objective of this matter is simply to give people individual title and also give them access to services. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 51132 | 20000 | 2 monts
1.1.5.1.2 | Erf 159 Edendale J | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 51132 | 20000 | 2 monts
1.1.5.1.3 | Ptn 357 of the Farm Wilgefontein No. 869 - FT | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 51132 | 20000 | 2 monts
1.1.5.1.4 | Remainder of Erf 16454 Plessis Laer | The site is owned by the municipality and is part of the Edendale town centre radius adjacent to the Edendale Mall and it on Mount Partridge Road. The structure built on the site are formal and orderly developed. The Informal Settlements Relocation Strategy project was undertaken by the municipality and recommended that we formalise the structures. However, a policy position on this matter is not available on the steps needed to do this and the responsibility of each line department concerned in giving effect to individual title. The site has 236 structure on it, which have limited access to water and use pit latrines. 59 households which are situated on either side of mount partridge were built using a government grant that was given to people in 1993 by the Department of Development Aid (DDA), the grant was to the value of R750 and land was made available to the recipients of the grant to build formal structures, which they did. The remainder of the 184 settled on the land without any grant or consent and the structures grew organically albeit formally. The recipients of the grant have PTOs and there is an unregistered GP over these properties (Alan would have to confirm) We request that you please set out the legal procedures that would be needed to formalise the area and functions and responsibilities of the various departments. These legal procedures will certainly begin to set a policy context on these matters moving forward not only for GEVDI but also the municipality especially our Human Settlements Department. Also set out the difference aspects that apply to the resident that received government aid and PTOs , and the one that built on their own with this consent. | Actual property description -:16454 Farm Willow To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 51132 | 20000 | 2 monts
1.1.5.1.5 | Investigation: Expropriation Batch 1A: Ptn 15 of Erf 4 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10000 | 8522
1.1.5.1.6 | Investigation: Expropriation Batch 1A: Ptn 2 of Erf 101 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10000 | 8522
1.1.5.1.7 | Rates: Ptn 8 of Erf 292 Edendale (Mncwabe) | Mr Mncwabe was previously facilitated by Phili Tenza. Upon attempting to sign agreement designation to LTAC Peter Warner was discovered. Facilitation attempts were halted. Mr Mncwabe has rates owing over the property OD has met with Mr Mncwabe & explained the desingation to LTAC. Mr Mncwabe has met with rates & DALARD re: the appointement of the LTAC. (carried over from 2019) | 1. Meet with LTAC/ DRDLR 2. Formalise letter to LTAC / DRDLR |  | 10000 | 8522 |  | 1 month
1.1.5.1.8 | Land Legal Opinion - Town Centre Legal Opinion from Advocate & Effect on Valuations Policy Amendment | GEVDI requested input from GeoAfrika on how the Advocate (Christison) opinion with respect to the relocations in the Town Centre, and its effect on the valuation policy. | 1. Peruse documentation & advocates Opinion 2. Compile Facts 3. If required request Counsel opinion on Valuation Policy 4. Compile report | R 150 000 incl. Possible Counsel opinion, External professional assistance. | 150000 | 127830
[5 empty] | 935000 | 796807 | 80000 | TOTAL | 1811807

## OG_Land Legal SA&C (hidden)
LAND LEGAL SCHEDULE OF ACTIVITIES AND COSTS - BP2020 TRANCHE 2 FUNDING
[7 empty] | DRAFT Date: | 2020-02-11
Item no. | Agenda Item | Description of activity | Activities required to bring about conclusion of matter | Budget breakdown & possible disbursement | Budget figure | Aprox. L/Legal Disbursements | Timeframe for completion | Comments
1 | Land Legal
1.1 | Land Legal: Specific Instructions
1.1.1 | DOHS Specific Instruction
1.1.1.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | 1. Review matter & Liase with Housing (DOHS) 2. Prepare report to DOHS & SMC |  | 10000 |  | 1 month
1.1.1.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | 1. Review evidence 2. Prepare report to DOHS & SMC |  | 10000 |  | 1 month
1.1.1.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | PSP to engage LMO department in dealing with the matter | 1. Review evidence 2. Prepare report to SMC |  | 10000 |  | 1 month
1.1.2 | DALARD
1.1.3 | GISC Specific Instructions
1.1.4 | 2018 /2019 GEVDI Specific Instructions
1.1.4.1 | Donation of land / upgrading of tenure
1.1.4.1 (a) | 22 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 15000 |  | 1 Month
1.1.4.1 (b) | 42 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 25000 |  | 1 Month
1.1.4.1 (c) | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. | 1. Review matter in the context of SPLUMA 2. Prepare SPLUMA application 3. Prepare report to SMC. | TBD - SPLUMA & Planning Costs | 15000 |  | 1 Month
1.1.4.1 (d) | Willowspruit - Donation of 7 properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 25000 |  | 1 Month
1.1.4.1 (e) | Musi Thuzi School: Ptn 7 of Erf 206 Edendale | Assist with the relayout, survey and subdivision of the property in order to accommodate the school, owner and the IRPTN | 1. Review status & Planning 2. Prepare report to SMC |  | 10000 |  | 1 Month
1.1.4.1 (f) | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | Completion of Donation agreement & submission to Municipality toward the opening of the township register & endorsment of Title Deeds | 1. Odwa to contact Thula Biyela and have the signing of agreement arranged 2. Prepare report to SMC to have donation confirmed 3. Instruct John Christie | R10 000.00 TBC - John Christie | 10000 |  | 3 Months
1.1.4.2 | Land Legal: Portions of Land being returned to Seller
1.1.4.2 (a) | Erf 198 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 |  | 2 months
1.1.4.2 (b) | Rem of Ptn 7 of Erf 15 Edendale | The property is owned by the Msunduzi Municipality and was acquired from Fred Tshablala. | 1. Engage Mdu (Legal) 2. Report to SMC | R10 000 Excluding Survey, SPLUMA, & Transfer | 10000 |  | 2 months
1.1.4.2 (c) | Ptn 11 of Erf 118 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Prepare SPLUMA Application 2. Obtain sub-divisional consent 3. Obtain approved SG Diagram 4. Transfer to "Owner" | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 |  | 2 months
1.1.4.2 (d) | Erf 22, 23 &24 Wilgefontein | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 |  | 2 months
1.1.4.2 (e) | Erf 142 Edendale | Conclude the formalities with respect to sub-division and transfer. | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 |  | 2 months
1.1.4.2 (f) | Erf 52 & 53 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 |  | 2 months
1.1.4.3 | State Land/ Intergovernmental Relations
1.1.4.3.1 | Letter of KZN Public Works re: State Land | GEVDI requested that GeoAfrika prepare a letter for KZN Public Works with reference to the State Land Reversion transfers. | 1. Report to SMC for intervention |  | 5000 |  | 2 weeks
1.1.4.3.2 | Letter to DRDLR re: Business Plan & LTAC | GEVDI requested that GeoAfrika prepare a letter for DRDLR, it was deemed prudent that this letter address a number of issues that the project was facing & serve as the submission of the properties for the R20million funding as per the MOA with DRDLR | 1. Report to SMC for intervention |  | 10000 |  | 1 month
1.1.4.3.3 | Letter to HDA re: GISC Meetings, State Land & Implementation Protocol. | GEVDI requested that GeoAfrika prepare a report on all HDA land in Edendale. This was to be supported by maps from GIS. | 1. Report to SMC for intervention |  | 10000 |  | 1 month
1.1.4.3.4 | COGTA: Complaint Against Msunduzi - Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | 1. Once resolution from Council, the matter will be progressed via COGTA |  | 20000 |  | 2 months
1.1.4.3.5 | State Land: Request for Donation from HDA : Erf 207 Edendale | GEVDI requested assistance with the acquiring of this property from HDA. | Refer to item above re: Letter to HAD
1.1.4.4 | Investigative & Legal Opinon/ Intervention
1.1.4.4.1 | Investigation: Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | 1. Review file and establish status 2. Establish facts with reference to LTAC 3. Report to SMC - Rates 4. Formalise matter with LTAC if appointed |  | 15000 |  | 2 months
1.1.4.4.2 | Investigation: Erf 519 &2754 Edendale N | Submit status report only | 1. Reivew file 2. Detail legal process to resolve 3. Report to SMC | R20 000 exluding court, survey, SPLUMA, & Transfer costs | 20000 |  | 2 months
1.1.4.4.3 | Erf 558 Ashdown | Mrs Muthwa claimed that she was the owner of the property which is currently occupied by Mr B Zondi. | 1. Review File 2. Prepare revised report to SMC |  | 15000 |  | 1 month
1.1.4.4.4 | Erf 855 Edendale N | Msunduzi Municipality is operating a quarry on Erf 855 Edendale without permission from the property owner. | 1. Review file 2. Prepare report to SMC 3. Detail which tranche CAPEX to come from 4. Lease |  | 25000 |  | 1 Month
1.1.4.4.5 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 20000 |  | 2 months
1.1.4.4.6 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landonwer being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. | 1. Review evidence and previous report 2. report to SMC |  | 10000 |  | 1 Month
1.1.4.4.7 | Erf 1655 Edendale S | Update report (including recommendations) and submit to Council for Approval | 1. Review file & claim 2. Detail legal process 3. report to SMC |  | 20000 |  | 1 Month
1.1.4.4.8 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 20000 |  | 2 months
1.1.4.4.9 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | 1. Review Title 2. Report to SMC |  | 10000
1.1.4.4.10 | Bhengu//Gabela Eviction | Completion of investigation and report for further legal process to follow. | 1. Reivew approach - planning intervention 2. Obtain POA from land owners 3. Submit SPLUMA | TBD - SPLUMA
1.1.4.4.11 | Slangspruit Buffer: Tenure Rectification & Fraudulent Transfer | Attend to Slangspruit Buffer: Tenure Rectification & fraudulent Transfer | 1. Review status 2. Report to SMC |  | 25000 |  | 1 Month
1.1.4.4.12 | Investigation: Erf 1655 Edendale S: Inzozoyesizwe School | Completion of investigation and report for further legal process to follow. | 1. Review File 2. Report to SMC |  | 15000 |  | 2 months
1.1.4.4.13 | Erf 68 Unit J - Imbali - Mncwabe | Mr Z Mncwabe representing the Zaca family requested GEVDI's assistance in providing a brief history for the property due to receiving a rates bill for the property. | 1. This is complete 2. Agree with GEVDI to remove |  |  |  | N/A
1.1.4.4.14 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | GEVDI requested that an investigation be done following a query by the Khambule Family regarding their property & people selling portions of the property in question. | 1. Review File 2. Report to SMC |  | 10000 |  | 1 month
1.1.4.4.15 | Erf 1570 Edendale Housing Development Grant | GEVDI instructed PSP to respond to a query from the Public Protector relating to the problems that the owner was having developing her site. | 1. Review file 2,. Detail what further actions are required 3. If so, prepare report to SMC |  | 10000 |  | 1 month
1.1.4.4.16 | Erf 52 Plessis Laer - Cancellation of Expropriation. | Masons attorneys approached the Municipality for assistance with the removal of a expropriation interdict over Erf 52 Plessis Laer. | 1. Consult with John Christie 2. Make application for removal | R10000.00 TBD - John Christie costs | 10000 |  | 2 months
1.1.4.4.17 | Erf 601 Edendale N - Archdiocese of Dbn Catholic Church | Chazile (City Estates & Valuations) requested assistance with historical information with reference to the sale of said property from the Municipality to the church. | 1. This is complete 2. Agree with GEVDI to remove |  |  |  | N/A
1.1.4.4.18 | Eviction: Magudulela & Gazu 199 Mnsinisi Road - Erf 1018 Edendale DD. | GEVDI instructed PSP to investigate & respond to a query from the CM's office. The Property in question is: 199 Mnsinisi Road - Erf 1018 Edendale DD. | 1. Review File 2. Prepare revised report to SMC |  | 15000 |  | 1 Month
1.1.4.4.19 | Tshabalala Matter Report - Properties: Erf 238 Edendale, Erf 218 Edendale, Ptn 2 of Erf 8 Edendale | GEVDI requested assistance from GeoAfrika in dealing with this matter - known as the Tshabalala Matter. | 1. Review File 2. Prepare revised report to SMC |  | 15000 |  | 1 month
1.1.4.4.20 | Expropriation Transfer of : Ptn 16 & 17 of Erf 233 Edendale | Arising from the above query, it was noted that the properties Ptn 16 & 17 of Erf 233 Edendale have not been transferred to the Municipality.
1.1.4.4.21 | Erf 198 Edendale Allocation of Portion of Property | GEVDI requested an investigation to be completed into building of a site on the property for Mr Sithole & the issuing of a permission to occupy for the same.
1.1.5 | 2019/2020 GEVDI Specific Instructions
1.1.5.1 | Investigative & Reporting Matters
1.1.5.1.1 | Ptn 168 of Farm Wilgefontein No. 869 - FT (Bhoola Property) | This property is owned by the municipality and has 59 people residing on it according to the councillor. The structures that have been built are formal for the most part and appear orderly developed on the site. The remedy that the residents want is for the municipality to pass individual title of these properties to them and for them to be able to access municipal services that are currently not available to them. The site is municipal owned and the residents claim that they have resided over 30 years on the property, is there any merits for prescription on this site?- We request that GeoAfrika please advise the municipality on this matter in terms of how it can be resolved and what are the duties of the municipality in this situation. Further to that, we request that lines of responsibility in the municipality and government be clearly defined, in terms of the role that each individual department will play in resolving this issue. This is of critical importance as at times lines of individual functions become a grey area and at times departments abdicate their responsibility due to lack of clarity policy wise of their respective functions/ obligations. The setting out of steps that need to be taken to address will be of great help. The ultimate objective of this matter is simply to give people individual title and also give them access to services. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 20000 | 2 monts
1.1.5.1.2 | Erf 159 Edendale J | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 20000 | 2 monts
1.1.5.1.3 | Ptn 357 of the Farm Wilgefontein No. 869 - FT | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 20000 | 2 monts
1.1.5.1.4 | Remainder of Erf 16454 Plessis Laer | The site is owned by the municipality and is part of the Edendale town centre radius adjacent to the Edendale Mall and it on Mount Partridge Road. The structure built on the site are formal and orderly developed. The Informal Settlements Relocation Strategy project was undertaken by the municipality and recommended that we formalise the structures. However, a policy position on this matter is not available on the steps needed to do this and the responsibility of each line department concerned in giving effect to individual title. The site has 236 structure on it, which have limited access to water and use pit latrines. 59 households which are situated on either side of mount partridge were built using a government grant that was given to people in 1993 by the Department of Development Aid (DDA), the grant was to the value of R750 and land was made available to the recipients of the grant to build formal structures, which they did. The remainder of the 184 settled on the land without any grant or consent and the structures grew organically albeit formally. The recipients of the grant have PTOs and there is an unregistered GP over these properties (Alan would have to confirm) We request that you please set out the legal procedures that would be needed to formalise the area and functions and responsibilities of the various departments. These legal procedures will certainly begin to set a policy context on these matters moving forward not only for GEVDI but also the municipality especially our Human Settlements Department. Also set out the difference aspects that apply to the resident that received government aid and PTOs , and the one that built on their own with this consent. | Actual property description -:16454 Farm Willow To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 20000 | 2 monts
1.1.5.1.5 | Investigation: Expropriation Batch 1A: Ptn 15 of Erf 4 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10000
1.1.5.1.6 | Investigation: Expropriation Batch 1A: Ptn 2 of Erf 101 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10000
1.1.5.1.7 | Rates: Ptn 8 of Erf 292 Edendale (Mncwabe) | Mr Mncwabe was previously facilitated by Phili Tenza. Upon attempting to sign agreement designation to LTAC Peter Warner was discovered. Facilitation attempts were halted. Mr Mncwabe has rates owing over the property OD has met with Mr Mncwabe & explained the desingation to LTAC. Mr Mncwabe has met with rates & DALARD re: the appointement of the LTAC. (carried over from 2019) | 1. Meet with LTAC/ DRDLR 2. Formalise letter to LTAC / DRDLR |  | 10000 |  | 1 month
1.1.5.1.8 | Land Legal Opinion - Town Centre Legal Opinion from Advocate & Effect on Valuations Policy Amendment | GEVDI requested input from GeoAfrika on how the Advocate (Christison) opinion with respect to the relocations in the Town Centre, and its effect on the valuation policy. | 1. Peruse documentation & advocates Opinion 2. Compile Facts 3. If required request Counsel opinion on Valuation Policy 4. Compile report | R 150 000 incl. Possible Counsel opinion, External professional assistance. | 150000
[5 empty] | 935000 | 80000 | TOTAL | 1015000

## Breakdown - OLD (hidden)
CLOSE OUT REPORT ON SCEDULES OF ACTIVITIES AND COST MATTERS FOR GEVDI PROJECT FOR PERIOD OF JULY 2018 TO JUNE 2019 |  |  |  |  | DRAFT
ITEMS ON INITIAL SCHEDULE OF ACTIVITIES AND COSTS (SAC)
Item no. | Agenda Item | Description of activity | Initial status | Description of activities completed during funding period | Status as at 30th June 2019 | Tasks Completed (to be deleted) | Matter Finalised (to be deleted) | Reason for non-completion of matter | Activities required to bring about conclusion of matter | Timeframe required for completion | Comments
1 | Land Legal
1.1 | Land Legal: Specific Instructions
1.1.1 | DOHS Specific Instruction
1.1.1.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | Mkhize family land used by the Municipality for a development by agreement. In terms of the agreement Mkhize family members who qualified for housing subsidies would be housed identified sites. The family claims they were never allocated sites. | A letter was compiled by the PSP providing an update from the report dated July 2015. To date no response has been received from the relevant implementing agent & the matter could not be progressed further. Cooperation from the implementing agent is required for matter to be finalised. | Partially completed |  | No | Input is requires from the Implementing Agent before the matter is able to reach completion. Intervention may be required from the Municipality. | In order to complete the investigation comment is required from the Implementing Agent. If this is submitted, the PSP will need to finalise the investigation to confirm the claim of the Mkhize matter& report on further recommendations. | TBD - based on input from the Implementing Agent. | Relevant recommendations will be quoted on in the report
1.1.1.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | This is a historical expropriation (EX203/1995), landowner claims to have never been compensated. No proof of compensation in files. | Advice provided to GEVDI, further instructions and allocation of funds required | Partially completed |  | No | Further instruction and allocation of funding required. | A GISC meeting or Sub-committee meeting with the DOHS is to be held in order for this matter to sit on the agenda. Thereafter further correspondence with the DOHS will be required to ensure finality. | TBD - based on funding & next GISC / GISC sub-committee meeting. | Relevant recommendations will be quoted on in the report
1.1.1.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | PSP to engage LMO department in dealing with the matter | Church built a structure in Municipal land without consent, has requested the Municipality to donate 0,34 HA of land where the structure is built to them. | Funding was reallocated. | Carried forward | No | No | Further instruction and allocation of funding required. | TBD | TBD | Relevant recommendations will be quoted on in the report
1.1.2 | DALARD
1.1.3 | LLC/ GISC Specific Instructions
1.1.4 | 2018 /2019 Specific Instructions
5.1.4 | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. | It is clear from the reports that the Municipality must intervene to resolve the situation including conducting the following tasks: Social beneficiary survey, Planning to relayout the area in order to accommodate as many households as possible, Planning & Development consents in terms of SPLUMA & the PDA to be sought, the basic conditions of NEMA to be adhered to., Consolidation * relayout of the properties and once one the ground situations have been rectified transfer of the newly created properties. | Funds reallocated. | Carried forward | No | No | Further instruction and allocation of funding required. | It is clear from the reports that the Municipality must intervene to resolve the situation including conducting the following tasks: Social beneficiary survey, Planning to relayout the area in order to accommodate as many households as possible, Planning & Development consents in terms of SPLUMA & the PDA to be sought, the basic conditions of NEMA to be adhered to., Consolidation * relayout of the properties and once one the ground situations have been rectified transfer of the newly created properties. | 2-3 years | Excluding conveyancing/ transfer fees
5.1.5 | Willowspruit - Donation of 7 properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | Despite telephonic & e-mail invites for the GISC meeting, the HDA have not attended the GEVDI GISC meeting or provided any insight into the transfers for these matters. | PSP prepared a letter for the HDA together with annexures & schedules & requested an urgent meeting in order to take the matter forward. High level intervention from Municipality may be requiredto ensure cooperation from HDA. | Carried forward | Yes | No | No ooperation from HDA | Further interaction with the DOHS & HDA may be required. Once the statutory formalities have been concluded, a conveyancer can be appointed & transfer can take place | TBD - based on response from the HDA | Excluding conveyancing/ transfer fees
5.1.6 | Musi Thuzi School: Ptn 7 of Erf 206 Edendale | Assist with the relayout, survey and subdivision of the property in order to accommodate the school, owner and the IRPTN | As at May 2016, there was a conflict between the layout of the school and the IRPTN. The Planning dept. undertook to have an urgent meeting with the stakeholders. | This property is being dealt with as part of the Dept. of Public Works reversion transfers | Partially completed (as part of reversion transfers) | N/A | No | Part of reversion transfers | This particular matter of the Muzi Thuzi School cannot be taken further until the matter with the IRPTN has been resolved and defined. A settlement agreement will then be concluded between KZN PW, the Mini Family and the Municipality. | 3 to 4 months
5.2.1 | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | Completion of Donation agreement & submission to Municipality toward the opening of the township register & endorsment of Title Deeds | Donation agreement was provided to the Municipality (Atkins) in July 2016 in order to facilitate the signing of the donation | PSP provided a report to the Municipality which explained the process of the opening of the township & the ULTRA upgrade. Subsequent to this the donation agreement & annexures were provided to the DOHS for signing. The DOHS responded with some queries which have been addressed & the agreement is being circulated through DOHS for signature. | Partially completed | Yes | No | Awaitng DOHS to sign Donation Agreement for matter to proceed. | Once the DOHS have returned the signed agreement, the Municipality is to sign the agreement. Thereafter the appointed conveyancer who has prepared the necessary documents is able to complete the necessary conveyancing tasks to open the Township Register & effect the ULTRA upgrade. | Within 6-8 months after the agreement is received from the DOHS & signed by the CM | Excluding Conveyancing & transfer costs
5.4.1 | Investigation: Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | ·A report dated 22/04/2016 was tabled at LLC · This is a historical matter where the rates clearance certificate has not been issued despite the conveyancer having paid for same Due to the property being designated in terms of the Land Titles Adjustment Act No. 111 of 1993 a conveyancer will need to be appointed | Due to the time which had elapsed since the matter was referred to the LLC, PSP requested confirmation from Trevor Cowie that the matter had not been concluded in the absence of the LLC meeting. PSP received no response to this e-mail and was later informed that Mr Cowie had retired. Status of the matter required from Municipality for it to be concluded. | Started |  | No | Uncertainty as to whether this matter was finalised in the absence of a sitting LLC. | N/A | N/A | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule. Excluding any PSP fees (survey/ Conveyancer etc.)
5.4.2 | Investigation: Erf 519 &2754 Edendale N | Submit status report only | · Conflict of title previously reported at LLC · Property is still under investigation with regards to the two sets of ownership which are reflecting on it. The project conveyancer (Mac) attended a meeting with Ithala and the Municipality | Funds reallocated. | Not started |  | No | Further instruction and allocation of funds to take place. |  |  | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule. Excluding any PSP fees (survey/ Conveyancer etc.)
5.4.3.1 | Erf 558 Ashdown | Mrs Muthwa claimed that she was the owner of the property which is currently occupied by Mr B Zondi. | PSP found no evidence to support Mrs Muthwa's claim. | Report submitted to GEVDI with proposed letter to Mrs Muthwa | Task completed but matter to be finalised | Yes | No | N/A | N/A | N/A | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule. Excluding any PSP fees (survey/ Conveyancer etc.)
5.4.3.2 | Erf 855 Edendale N | Msunduzi Municipality is operating a quarry on Erf 855 Edendale without permission from the property owner. | PSP to investigate | PSP has compiled a letter which maintains the recommendation from the reports tabled in June 2015. Which was submitted to GEVDI recommending acquisition of the property in question. | Task completed but matter to be finalised | Yes | No | N/A | Further instruction and allocation of funding. | TBD - based on confirmed funding from Council. | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule. Excluding any PSP fees (survey/ Conveyancer etc.)
5.4.3.3 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. | Instruction to investigate conflict. | Report recomending allocation of funds for a High Court Application submitted to GEVDI. | Task completed but matter to be finalised |  |  | Further instructions may arise agter consideration of the report by GEVDI. | High Court Application to remedy conflict required. | 2-3 years. | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule. Excluding any PSP fees (survey/ Conveyancer etc.)
5.4.3.4 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landonwer being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. | Erf 1173 may have been registered to the owner of Erf 1172 in error. | PSP has compiled a letter which maintains the recommendation from the reports tabled in April 2016. This will be submitted to the Municipality in due course for re-submission to Council and determination on the recommendations. | Task completed but matter to be finalised | Yes | No | Further instruction may arise after consideration of report by GEVDI. |  | TBD - based on the receipt of funding & availability of High Court Dates | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule. Excluding any PSP fees (survey/ Conveyancer etc.)
5.4.3.5 | Erf 1655 Edendale S | Update report (including recommendations) and submit to Council for Approval | PTO Investigation : Underlying Erf 1655 Edendale S | Funds reallocated. | Not started |  |  | Funds for this matter were reallocated | Investigation to determine way forward | TBD | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule. Excluding any PSP fees (survey/ Conveyancer etc.)
5.4.3.6 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval | Tenure Conflict investigation : Erf 1570 Edendale Unit CC | Funds reallocated. | Not started |  |  | Funds for this matter were reallocated | Investigation to determine way forward | TBD | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule
5.5.1 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | Property has been transferred to the Municipality – 12/10/2018. Property needs to be allocated to Mavundla and possible communication process. | Funds reallocated. | Not started |  |  | Funds for this matter were reallocated | Council resolution required for the reallocation of the property to the Mavundla family. Conveyancer to then conduct transfer to the family. | TBD | Upon Council feedback, further steps to be re-evaluated, budgeted and applied to the next schedule
5.5.2 | Bhengu//Gabela Eviction | Completion of investigation and report for further legal process to follow. | The PSP has corresponded with the relevant lawyers and stayed the impending court action. Property needs to urgently be dealt with. | The comprehensive activities needed to conclude this matter were not able to be funded from the available budget. A Comprehensive budget was provided to the Municipality. | To be completed when budget available | No | No | Sufficient funding was not allocated to this matter | Planning, SPLUMa, Survey, negotations with landowners, signing of agreements, registration & transfer | TBD | January 2019 figure includes Conveyancing & Survey fee (if needed) CAPEX -: R950 096.34
5.6.1 | Slangspruit Buffer: Tenure Rectification | Attend to Slangspruit Buffer: Tenure Rectification | Slangspruit Buffer: Tenure Rectification to be done | No activities were included in the current tranche funding for this matter. | Not started | N/A | N/A | N/A | N/A | N/A | GEVDI to determine when this is to be undertaken & tasks that are relevant
5.6.2 | Slangspruit Buffer: Land invasion. | Assess and attend to Slangspruit Buffer: Land invasion. | Land invasion in Slangspruit Buffer | No activities were included in the current tranche funding for this matter. | Not started | N/A | NA | N/A | N/A | N/A | GEVDI to determine when this is to be undertaken & tasks that are relevant
9.1 | Investigation: Erf 1655 Edendale S: Inzozoyesizwe School | Completion of investigation and report for further legal process to follow. | As per e-mail from Nkululeko Mkhungo, PSP has been requested to investigate this property | This matter is related to the State Land Transfers/ Reversion. | Partially completed | N/A | N/A | This matter forms part of the State Land Transfers & will be deal with under that section.
1.1.4 | Erf 68 Unit J - Imbali - Mncwabe | Mr Z Mncwabe representing the Zaca family requested GEVDI's assistance in providing a brief history for the property due to receiving a rates bill for the property. |  | GEVDI requested PSP investigate the property & provide history (06/09/2018). This was provided to Mr Mncwabe on the same date. | Completed | Yes | Yes | N/A | N/A | N/A
1.1.4 | Ptn 8 of erf 292 Edendale - Mncwabe | Arising from the Erf 68 Unit J query, Mr Mncwabe also queried about Ptn 8 of Erf 292 Edendale (04/10/2018) & the request for GEVDI's assistance with 1. Rates Clearance & 2. transferring of late estate ownership into the executors name. | During the previous tranche funding, the facilitators were instructed to attempt the acquisition of this property in the hopes that we would receive a confirmation by the Land Titles Adjustment Commissioner who was delegated to this property (Peter Warner). | As this property has been delegated to LTAC Peter Warner, we have been unable to assist with the transferring of Title into the executors ownership. We have however opened discussions with the DRDLR on the appointment of Peter Warner & the possibility of reappointing. | In progress | N/A | N/A | Unable to assist with the transfer to Mr Mncwabe due to the appointment of a LTAC over the property. | Confirmation required from DRDLR re: the appointment of Peter Warner. | TBD - Depending on DRDLR's confirmation of Peter Warner's appointment. | Odwa to draft letter/ report for Narain & possibly for Council re: write off of rates.
1.1.4 | Letter of KZN Public Works re: State Land | GEVDI requested that GeoAfrika prepare a letter for KZN Public Works with reference to the State Land Reversion transfers. |  | GeoAfrika prepared a report with necessary maps as annexures. This was provided to the Municipality for the GM's signature on 14/06/2019 | Completed - linked to reversion transfers | Yes | Yes | N/A | N/A | N/A
1.1.4 | Letter to DRDLR re: Business Plan & LTAC | GEVDI requested that GeoAfrika prepare a letter for DRDLR, it was deemed prudent that this letter address a number of issues that the project was facing & serve as the submission of the properties for the R20million funding as per the MOA with DRDLR |  | GeoAfrika prepared a letter for DRDLR, topics which were discussed in the letter were: Land Acquisition Funding, Funding for Land Tenure, GISC Meetings, Implementation Protocol, BP2020, Deceased Estates, LTAC appointments & LTAC Peter Warner. | Letter completed | Yes | No | N/A | N/A | N/A
1.1.4 | Letter to HDA re: GISC Meetings, State Land & Implementation Protocol. | GEVDI requested that GeoAfrika prepare a report on all HDA land in Edendale. This was to be supported by maps from GIS. |  | GeoAfrika prepared a report with necessary maps as annexures. This was provided to the Municipality for the GM's signature on 14/06/2019 | Letter completed | Yes | No | N/A | N/A | N/A
1.1.4 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | GEVDI requested that an investigation be done following a query by the Khambule Family regarding their property & people selling portions of the property in question. | PSP provided a report including facts & recommendations. | PSP conducted an investigation into the property & provided an e-mail response including the facts & recommendations of how to handle the matter. This 'report' was provided to the Municipalities legal team. Further instruction based on the recommended tasks is awaited | Await feedback from the Municipal legal department | Yes | No | N/A | N/A | N/A
1.1.4 | Erf 1570 Edendale Housing Development Grant | GEVDI instructed PSP to respond to a query from the Public Protector relating to the problems that the owner was having developing her site. | PSP investigated the ownership & land use of the site & prepared a report. | After conducting its investigation, PSP prepared a response for the GM to address the problems that the land owner was having with the community. | Letter prepared to Public Protector on behalf of Municipality | Yes | No | N/A | N/A | N/A
1.1.4 | Erf 52 Plessis Laer - Cancellation of Expropriation. | Masons attorneys approached the Municipality for assistance with the removal of a expropriation interdict over Erf 52 Plessis Laer. | After Investigation it was determined that the expropriation Interdict was mistakenly endorsed on this property by the Deeds Office. The Deeds Office have noted that this was completed in error. | GeoAfrika forwarded a letter to the Deeds Office including historical correspondence related to this matter. The Deeds Office confirmed that they have received the letter & we are awaiting confirmation on whether a further process is required to remove the incorrect interdict. | Feedback awaited | Yes | No | Awaiting confirmation from the Deeds Office. | Possibly formal application to be made for the removal of the interdict. | Dependant on Deeds Office processes.
1.1.4 | Erf 601 Edendale N - Archdiocese of Dbn Catholic Church | Chazile (City Estates & Valuations) requested assistance with historical information with reference to the sale of said property from the Municipality to the church. | The GeoAfrika team using the documents on our historical files assisted with this query. It is to be noted that the property is a State Owned property which has not been transferred to the Municipality as yet. | PSP provided a report to Chazile. GeoAfrika was then informed (through e-mail from Chazile) that the way forward was to transfer the property once it has been transferred to the Municipality. | Partially completed | Yes | Yes | Sale of the Property has been halted until the property has been transferred to the Municipality. | State Land Transfer to be completed. | TBC
1.1.4 | Eviction: Magudulela & Gazu 199 Mnsinisi Road - Erf 1018 Edendale DD. | GEVDI instructed PSP to investigate & respond to a query from the CM's office. The Property in question is: 199 Mnsinisi Road - Erf 1018 Edendale DD. | PSP investigate the property, reason for the Eviction and the Permission to Occupy claim and provided a report with relevant annexures & recommendations. | PSP provided a report to GEVDI with background, the legal status of Permission to Occupy documents, Upgrading of Land Tenure Rights & recommendations. No further instructions have arisen. | Partially completed | Yes | No | N/A | further instructions may arise based on recommendations. | N/A
1.1.4 | COGTA: Complaint Against Msunduzi - Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | After the initial investigation into the complaint, PSP met with COGTA & the Municipality in order to formalise tasks including the compiling of a report. GeoAfrika further investigated the various complaints that private owner had & compiled further report & recommendations for the Municipality. In addition, PSP has appointed an independent valuer to provide the current value of the properties, and the rental value of Municipal infrastructure over the properties as per the reports which have been provided. | PSP have provided a report & various other correspondence to the Municipality in order to assist with how this matter should be dealt with. | Partially completed | Yes | No | The Municipality was to fast-track a meeting with the Legal Department in order to secure their comments on the report & prepare the matter for Council. The Valuation amounts for the properties will be forwarded to the Municipality once they have been received from the Valuer. | Approval from Legal & Council. Negotiations with Khuzwayo family, Signing of Settlement & Sale Agreements, Registration and trasfer.
1.1.4 | State Land: Request for Donation from HDA : Erf 207 Edendale | GEVDI requested assistance with the acquiring of this property from HDA. | PSP assisted GEVDI by drafting a letter for HDA in which the Implementation Protocol was introduced & the request for the HDA to engage with the Municipality in order to donate/ transfer the property to the Municipality. | PSP assisted GEVDI by drafting a letter for HDA in which the Implementation Protocol was introduced & the request for the HDA to engage with the Municipality in order to donate/ transfer the property to the Municipality. This letter was forwarded to the Municipality for the GMs signature | Partially completed | Yes | No | Further instruction required to finalise matter. | Correspondence with the HDA still to be undertaken. | TBD - Dependant on the outcome of correspondence/ request with HDA
1.1.4 | Tshabalala Matter Report - Properties: Erf 238 Edendale, Erf 218 Edendale, Ptn 2 of Erf 8 Edendale | GEVDI requested assistance from GeoAfrika in dealing with this matter - known as the Tshabalala Matter. | PSP have investigated & surveyed the properties in order to provide an accurate report on the allegations from the Tshabalala family. | PSP have provided a report & various other correspondence to the Municipality in order to assist with how this matter should be dealt with. No further instruction has been provided. | Partially completed | Yes | No | Further instruction required to finalise matter. | Further instruction required to finalise matter. | N/A
1.1.4 | Expropriation Transfer of : Ptn 16 & 17 of Erf 233 Edendale | Arising from the above query, it was noted that the properties Ptn 16 & 17 of Erf 233 Edendale have not been transferred to the Municipality. | This matter was highlighted at a point when project funding was unavailable. Upon the security of funding, the LTAC is to be approached to determine why the Expropriation Transfer was not completed & transfer can be instructed. | Due to lack of funding this matter could not be taken any further with current funding, in addition, formal instruction from the Municipality has not been received. | Not Started | N/A | No | N/A | Funds to be transferred from MFI back to the Municipality. Correspondence with the LTAC to be undertaken in order to complete expropriation transfer. | N/A
1.1.4 | Erf 198 Edendale Allocation of Portion of Property | GEVDI requested an investigation to be completed into building of a site on the property for Mr Sithole & the issuing of a permission to occupy for the same. | GeoAfrika provided the previously signed settlement agreement with the LTAC & the Municipality which included a clause for sub-divisions to be transferred from the property. No further instruction was received. | GeoAfrika provided the previously signed settlement agreement with the LTAC & the Municipality which included a clause for sub-divisions to be transferred from the property. No further instruction was received. | Not Started | N/A | No | N/A | TBD. | N/A
5.3 | Land Legal: Portions of Land being returned to Seller
5.3.1 | Erf 198 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | As per the Settlement Agreement with the Municipality, the Land Titles Adjustment Commissioner is to conduct the survey & transfer for this property. GeoAfrika' s role was therefore to oversee this process & to ensure that this abided by Municipal procedures. | In progress |  | No | The LTAC has not appointed a surveyor for this matter, therefore our oversight of this process cannot be completed. | LTAC to appoint surveyor, provide necessary documentation to the Municipality as per the settlement agreement. Municipality to sign the Power of Attorney provided by the LTAC. Thereafter Surveyors to complete the necessary processes in line with the annexed image from the settlement agreement. | Dependant on when the LTAC appoints the surveyor & provides the necessary documentation to the Municipality as per the Settlement Agreement. | * EXCLUDING PSP Fees for Conveyancing & Survey*
5.3.2 | Rem of Ptn 7 of Erf 15 Edendale | The property is owned by the Msunduzi Municipality and was acquired from Fred Tshablala. | The signed agreement provided for Fred Tshabalala to retain the portion of the property he currently occupies. | Report & addendum to Deed of Sale prepared and submitted to GEVDI for legal vetting and approval. | In progress |  | No | Awaiting Legal & council approval. |  |  | * EXCLUDING PSP Fees for Conveyancing & Survey*
5.3.3 | Ptn 11 of Erf 118 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | This property is currently held up by the rates clearance matter - item 4.4.1 & has not been transferred to Municipal ownership. | Held up by rates clearance | N/A - Cannot be completed before transfer | N/A | Due to the property not being owned by the Municipality, the effecting of the sub-division & transfer could not be concluded. | Dependant on the rates clearance & transfer of the property to the Municipality | TBD - based on the rates clearance & transfer to the Municipality | * EXCLUDING PSP Fees for Conveyancing & Survey*
5.3.4 | Erf 22, 23 &24 Wilgefontein | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | This property is currently held up by the rates clearance matter - item 4.4.1 & has not been transferred to Municipal ownership. | Held up by rates clearance | N/A - Cannot be completed before transfer | N/A | Due to the property not being owned by the Municipality, the effecting of the sub-division & transfer could not be concluded. | Dependant on the rates clearance & transfer of the property to the Municipality | TBD - based on the rates clearance & transfer to the Municipality | * EXCLUDING PSP Fees for Conveyancing & Survey*
5.3.5 | Erf 142 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | This property is currently held up by the rates clearance matter - item 4.4.1 & has not been transferred to Municipal ownership. | Held up by rates clearance | N/A - Cannot be completed before transfer | N/a | Due to the property not being owned by the Municipality, the effecting of the sub-division & transfer could not be concluded. | Dependant on the rates clearance & transfer of the property to the Municipality | TBD - based on the rates clearance & transfer to the Municipality | * EXCLUDING PSP Fees for Conveyancing & Survey*
5.3.6 | Erf 52 & 53 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. Power of Attorney prepared and signed to enable surveyor to do subdivision. | As per the Settlement Agreement with the Municipality, the Land Titles Adjustment Commissioner is to conduct the survey & transfer for this property. PSP s role was therefore to oversee this process & to ensure that this abided by Municipal procedures. | Partially completed |  | No |  | LTAC dealing with the matter. | Dependant on the outcomes of the LTAC & Municipal Survey units. Discussions. | * EXCLUDING PSP Fees for Conveyancing & Survey*
1.1.5 | 2019/2020 Specific Instructions
| Ptn 168 of Farm Wilgefontein No. 869 - FT | This property is owned by the municipality and has 59 people residing on it according to the councillor. The structures that have been built are formal for the most part and appear orderly developed on the site. The remedy that the residents want is for the municipality to pass individual title of these properties to them and for them to be able to access municipal services that are currently not available to them. The site is municipal owned and the residents claim that they have resided over 30 years on the property, is there any merits for prescription on this site?- We request that GeoAfrika please advise the municipality on this matter in terms of how it can be resolved and what are the duties of the municipality in this situation. Further to that, we request that lines of responsibility in the municipality and government be clearly defined, in terms of the role that each individual department will play in resolving this issue. This is of critical importance as at times lines of individual functions become a grey area and at times departments abdicate their responsibility due to lack of clarity policy wise of their respective functions/ obligations. The setting out of steps that need to be taken to address will be of great help. The ultimate objective of this matter is simply to give people individual title and also give them access to services.
| Bhoola Property | The dynamics on this property are almost the same as the above property with slight nuances. The property is privately owned and the owner has not had any dealings with the property for a considerable period. The occupiers of the land have built formal structure on the land and have lived on the property for over 30 years which raises the issue of prescription and implications thereof on the remedy sought by the residents. The councillor was championing the cause of the people by bringing the matter forward and to get an understanding what role can the municipality play in helping the people to own individual title and also have proper connection to services. The other issue is the rates attached to the property and in prescribed land what happens. We request that you please provide us with the legal view on prescription as it relates to this matter and to also explain the role that the municipality can play to assist in the matter with the ultimate objective to bring the remedy that is sought to fruition. Also set out the steps that have to be taken by municipality if any.
| Erf 159 Edendale J | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter.
| Ptn 357 of the Farm Wilgefontein No. 869 - FT | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter.
| Remainder of Erf 16454 Plessis Laer | The site is owned by the municipality and is part of the Edendale town centre radius adjacent to the Edendale Mall and it on Mount Partridge Road. The structure built on the site are formal and orderly developed. The Informal Settlements Relocation Strategy project was undertaken by the municipality and recommended that we formalise the structures. However, a policy position on this matter is not available on the steps needed to do this and the responsibility of each line department concerned in giving effect to individual title. The site has 236 structure on it, which have limited access to water and use pit latrines. 59 households which are situated on either side of mount partridge were built using a government grant that was given to people in 1993 by the Department of Development Aid (DDA), the grant was to the value of R750 and land was made available to the recipients of the grant to build formal structures, which they did. The remainder of the 184 settled on the land without any grant or consent and the structures grew organically albeit formally. The recipients of the grant have PTOs and there is an unregistered GP over these properties (Alan would have to confirm) We request that you please set out the legal procedures that would be needed to formalise the area and functions and responsibilities of the various departments. These legal procedures will certainly begin to set a policy context on these matters moving forward not only for GEVDI but also the municipality especially our Human Settlements Department. Also set out the difference aspects that apply to the resident that received government aid and PTOs , and the one that built on their own with this consent. | Actual property description -: 16454 farm Willow
| Investigation: Expropriation Batch 1A: Ptn 15 of Erf 4 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. | Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC
| Investigation: Expropriation Batch 1A: Ptn 2 of Erf 101 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. | Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC
| Rates: Ptn 8 of Erf 292 Edendale (Mncwabe) | Mr Mncwabe was previously facilitated by Phili Tenza. Upon attempting to sign agreement designation to LTAC Peter Warner was discovered. Facilitation attempts were halted. Mr Mncwabe has rates owing over the property | OD has met with Mr Mncwabe & explained the desingation to LTAC. Mr Mncwabe has met with rates & DALARD re: the appointement of the LTAC.
2 | Land Acquisition
Note on A18: Jane Tennet: Odwa/ Hoffy to advise on wording for this matter. No work was completed.
Note on A51: Jane Tennet: Odwa to advise on wording for this matter as some work has been completed.

## Breakdown - Updates (hidden)
LAND LEGAL SCHEDULE OF ACTIVITIES AND COSTS - BP2020 TRANCHE 2 FUNDING
Item no. | Agenda Item | Description of activity | Activities required to bring about conclusion of matter | Budget Breakdown | Budget figure | Timeframe for completion | Champion | Date Started/ Completed | Further Actions | Report Submission Date / To whom | Comments
1 | Land Legal
1.1 | Land Legal: Specific Instructions
1.1.1 | DOHS Specific Instruction
1.1.1.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | 1. Review matter & Liase with Housing (DOHS) 2. Prepare report to DOHS & SMC |  | 10000 | 1 month
1.1.1.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | 1. Review evidence 2. Prepare report to DOHS & SMC |  | 10000 | 1 month
1.1.1.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | PSP to engage LMO department in dealing with the matter | 1. Review evidence 2. Prepare report to SMC |  | 10000 | 1 month
1.1.2 | DALARD
1.1.3 | LLC/ GISC Specific Instructions
1.1.4 | 2018 /2019 Specific Instructions
51.1 | 22 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 15000 | 1 Month
5.1.3 | 42 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 25000 | 1 Month
5.1.4 | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. | 1. this is now a housing matter. 2. The land legal matters were concluded 3. Propose a report to SMC |  | 10000 | 1 Month
5.1.5 | Willowspruit - Donation of 7 properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | 1. Based on letter, prepare report to SMC to recommend Municipality conclude the transaction |  | 25000 | 1 Month
5.1.6 | Musi Thuzi School: Ptn 7 of Erf 206 Edendale | Assist with the relayout, survey and subdivision of the property in order to accommodate the school, owner and the IRPTN | 1. Review status & Planning 2. Prepare report to SMC |  | 10000 | 1 Month
5.2.1 | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | Completion of Donation agreement & submission to Municipality toward the opening of the township register & endorsment of Title Deeds | 1. Odwa to contact Thula Biyela and have the signing of agreement arranged 2. Prepare report to SMC to have donation confirmed 3. Instruct John Christie | R10 000.00 TBC - John Christie | 10000 | 3 Months
5.4.1 | Investigation: Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | 1. Review file and establish status 2. Establish facts with reference to LTAC 3. Report to SMC - Rates 4. Formalise matter with LTAC if appointed |  | 15000 | 2 months
5.4.2 | Investigation: Erf 519 &2754 Edendale N | Submit status report only | 1. Reivew file 2. Detail legal process to resolve 3. Report to SMC | R20 000 exluding court, survey, SPLUMA, & Transfer costs | 20000 | 2 months
5.4.3.1 | Erf 558 Ashdown | Mrs Muthwa claimed that she was the owner of the property which is currently occupied by Mr B Zondi. | 1. Review File 2. Prepare revised report to SMC |  | 15000 | 1 month
5.4.3.2 | Erf 855 Edendale N | Msunduzi Municipality is operating a quarry on Erf 855 Edendale without permission from the property owner. | 1. Review file 2. Prepare report to SMC 3. Detail which tranche CAPEX to come from 4. Lease |  | 25000 | 1 Month
5.4.3.3 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 20000 | 2 months
5.4.3.4 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landonwer being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. | 1. Review evidence and previous report 2. report to SMC |  | 10000 | 1 Month
5.4.3.5 | Erf 1655 Edendale S | Update report (including recommendations) and submit to Council for Approval | 1. Review file & claim 2. Detail legal process 3. report to SMC |  | 20000 | 1 Month
5.4.3.6 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval | 1, Revuew fuke 2, Detail legal process 3. Obtain legal opinion 4. Report to SMC (to also secure funds from DRDLR) |  | 20000 | 2 months
5.5.1 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | 1. Review Title 2. Report to SMC |  | 10000
5.5.2 | Bhengu//Gabela Eviction | Completion of investigation and report for further legal process to follow. | 1. Reivew approach - reduce planning intervention 2. Obtain POA 3. Submit SPLUMA |  | TBC
5.6.1 | Slangspruit Buffer: Tenure Rectification | Attend to Slangspruit Buffer: Tenure Rectification | 1. Review status 2. Report to SMC | R15 000.00 (Invluce Funds from RDLR) | 15000 | 1 Month
5.6.2 | Slangspruit Buffer: Land invasion. | Assess and attend to Slangspruit Buffer: Land invasion. | 1. Review status 2. Report to SMC | R15 000.00 (Invluce Funds from RDLR) | 15000 | 1 Month
9.1 | Investigation: Erf 1655 Edendale S: Inzozoyesizwe School | Completion of investigation and report for further legal process to follow. | 1. Review File 2. Report to SMC |  | 15000 | 2 months
1.1.4 | Erf 68 Unit J - Imbali - Mncwabe | Mr Z Mncwabe representing the Zaca family requested GEVDI's assistance in providing a brief history for the property due to receiving a rates bill for the property. | 1. This is complete 2. Agree with GEVDI to remove |  | N/A | N/A
1.1.4 | Ptn 8 of erf 292 Edendale - Mncwabe | Arising from the Erf 68 Unit J query, Mr Mncwabe also queried about Ptn 8 of Erf 292 Edendale (04/10/2018) & the request for GEVDI's assistance with 1. Rates Clearance & 2. transferring of late estate ownership into the executors name. | 1. Engage DRDLR 2. Send Formal Letter to DRDLR |  | 10000 | 1 month
1.1.4 | Letter of KZN Public Works re: State Land | GEVDI requested that GeoAfrika prepare a letter for KZN Public Works with reference to the State Land Reversion transfers. | 1. Report to SMC for intervention |  | 5000 | 2 weeks
1.1.4 | Letter to DRDLR re: Business Plan & LTAC | GEVDI requested that GeoAfrika prepare a letter for DRDLR, it was deemed prudent that this letter address a number of issues that the project was facing & serve as the submission of the properties for the R20million funding as per the MOA with DRDLR | 1. Report to SMC for intervention |  | 10000 | 1 month
1.1.4 | Letter to HDA re: GISC Meetings, State Land & Implementation Protocol. | GEVDI requested that GeoAfrika prepare a report on all HDA land in Edendale. This was to be supported by maps from GIS. | 1. Report to SMC for intervention |  | 10000 | 1 month
1.1.4 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | GEVDI requested that an investigation be done following a query by the Khambule Family regarding their property & people selling portions of the property in question. | 1. Review File 2. Report to SMC |  | 10000 | 1 month
1.1.4 | Erf 1570 Edendale Housing Development Grant | GEVDI instructed PSP to respond to a query from the Public Protector relating to the problems that the owner was having developing her site. | 1. Review file 2,. Detail what further actions are required 3. If so, prepare report to SMC |  | 10000 | 1 month
1.1.4 | Erf 52 Plessis Laer - Cancellation of Expropriation. | Masons attorneys approached the Municipality for assistance with the removal of a expropriation interdict over Erf 52 Plessis Laer. | 1. Consult with John Christie 2. Make application for removal | R10000.00 TBD - John Christie costs | 10000 | 2 months
1.1.4 | Erf 601 Edendale N - Archdiocese of Dbn Catholic Church | Chazile (City Estates & Valuations) requested assistance with historical information with reference to the sale of said property from the Municipality to the church. | 1. This is complete 2. Agree with GEVDI to remove |  | N/A | N/A
1.1.4 | Eviction: Magudulela & Gazu 199 Mnsinisi Road - Erf 1018 Edendale DD. | GEVDI instructed PSP to investigate & respond to a query from the CM's office. The Property in question is: 199 Mnsinisi Road - Erf 1018 Edendale DD. | 1. Review File 2. Prepare revised report to SMC |  | 15000 | 1 Month
1.1.4 | COGTA: Complaint Against Msunduzi - Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | 1. Once resolution from Council, the matter will be progressed via COGTA |  | 20000 | 2 months
1.1.4 | State Land: Request for Donation from HDA : Erf 207 Edendale | GEVDI requested assistance with the acquiring of this property from HDA. | Refer to item above re: Letter to HAD
1.1.4 | Tshabalala Matter Report - Properties: Erf 238 Edendale, Erf 218 Edendale, Ptn 2 of Erf 8 Edendale | GEVDI requested assistance from GeoAfrika in dealing with this matter - known as the Tshabalala Matter. | 1. Review File 2. Prepare revised report to SMC |  | 15000 | 1 month
1.1.4 | Expropriation Transfer of : Ptn 16 & 17 of Erf 233 Edendale | Arising from the above query, it was noted that the properties Ptn 16 & 17 of Erf 233 Edendale have not been transferred to the Municipality.
1.1.4 | Erf 198 Edendale Allocation of Portion of Property | GEVDI requested an investigation to be completed into building of a site on the property for Mr Sithole & the issuing of a permission to occupy for the same.
5.3 | Land Legal: Portions of Land being returned to Seller
5.3.1 | Erf 198 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 2 months
5.3.2 | Rem of Ptn 7 of Erf 15 Edendale | The property is owned by the Msunduzi Municipality and was acquired from Fred Tshablala. | 1. Engage Mdu (Legal) 2. Report to SMC | R10 000 Excluding Survey, SPLUMA, & Transfer | 10000 | 2 months
5.3.3 | Ptn 11 of Erf 118 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 2 months | [5 empty] | Property not with a LTAC. HELD UP BY RATES CLEARANCE
5.3.4 | Erf 22, 23 &24 Wilgefontein | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 2 months | [5 empty] | Property not with a LTAC. HELD UP BY RATES CLEARANCE
5.3.5 | Erf 142 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC | R15 000 Excluding Survey, SPLUMA, & Transfer | 15000 | 2 months | [5 empty] | Property not with a LTAC. HELD UP BY RATES CLEARANCE
5.3.6 | Erf 52 & 53 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit | 1. Review settlement agreement 2. Detail costs to complete 3. Engage LTAC & Report to SMC |  | 15000 | 2 months
1.1.5 | 2019/2020 Specific Instructions
| Ptn 168 of Farm Wilgefontein No. 869 - FT | This property is owned by the municipality and has 59 people residing on it according to the councillor. The structures that have been built are formal for the most part and appear orderly developed on the site. The remedy that the residents want is for the municipality to pass individual title of these properties to them and for them to be able to access municipal services that are currently not available to them. The site is municipal owned and the residents claim that they have resided over 30 years on the property, is there any merits for prescription on this site?- We request that GeoAfrika please advise the municipality on this matter in terms of how it can be resolved and what are the duties of the municipality in this situation. Further to that, we request that lines of responsibility in the municipality and government be clearly defined, in terms of the role that each individual department will play in resolving this issue. This is of critical importance as at times lines of individual functions become a grey area and at times departments abdicate their responsibility due to lack of clarity policy wise of their respective functions/ obligations. The setting out of steps that need to be taken to address will be of great help. The ultimate objective of this matter is simply to give people individual title and also give them access to services. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Bhoola Property | The dynamics on this property are almost the same as the above property with slight nuances. The property is privately owned and the owner has not had any dealings with the property for a considerable period. The occupiers of the land have built formal structure on the land and have lived on the property for over 30 years which raises the issue of prescription and implications thereof on the remedy sought by the residents. The councillor was championing the cause of the people by bringing the matter forward and to get an understanding what role can the municipality play in helping the people to own individual title and also have proper connection to services. The other issue is the rates attached to the property and in prescribed land what happens. We request that you please provide us with the legal view on prescription as it relates to this matter and to also explain the role that the municipality can play to assist in the matter with the ultimate objective to bring the remedy that is sought to fruition. Also set out the steps that have to be taken by municipality if any. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Erf 159 Edendale J | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Ptn 357 of the Farm Wilgefontein No. 869 - FT | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Remainder of Erf 16454 Plessis Laer | The site is owned by the municipality and is part of the Edendale town centre radius adjacent to the Edendale Mall and it on Mount Partridge Road. The structure built on the site are formal and orderly developed. The Informal Settlements Relocation Strategy project was undertaken by the municipality and recommended that we formalise the structures. However, a policy position on this matter is not available on the steps needed to do this and the responsibility of each line department concerned in giving effect to individual title. The site has 236 structure on it, which have limited access to water and use pit latrines. 59 households which are situated on either side of mount partridge were built using a government grant that was given to people in 1993 by the Department of Development Aid (DDA), the grant was to the value of R750 and land was made available to the recipients of the grant to build formal structures, which they did. The remainder of the 184 settled on the land without any grant or consent and the structures grew organically albeit formally. The recipients of the grant have PTOs and there is an unregistered GP over these properties (Alan would have to confirm) We request that you please set out the legal procedures that would be needed to formalise the area and functions and responsibilities of the various departments. These legal procedures will certainly begin to set a policy context on these matters moving forward not only for GEVDI but also the municipality especially our Human Settlements Department. Also set out the difference aspects that apply to the resident that received government aid and PTOs , and the one that built on their own with this consent. | Actual property description -:16454 Farm Willow To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Investigation: Expropriation Batch 1A: Ptn 15 of Erf 4 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10000
| Investigation: Expropriation Batch 1A: Ptn 2 of Erf 101 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10001
| Rates: Ptn 8 of Erf 292 Edendale (Mncwabe) | Mr Mncwabe was previously facilitated by Phili Tenza. Upon attempting to sign agreement designation to LTAC Peter Warner was discovered. Facilitation attempts were halted. Mr Mncwabe has rates owing over the property OD has met with Mr Mncwabe & explained the desingation to LTAC. Mr Mncwabe has met with rates & DALARD re: the appointement of the LTAC. | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10002
855003
Note on A17: Jane Tennet: Separate file - not land legal
Note on A18: Jane Tennet: Pradeep to confirm
Note on A20: Jane Tennet: Odwa/ Hoffy to advise on wording for this matter. No work was completed.
Note on A53: Jane Tennet: Odwa to advise on wording for this matter as some work has been completed.

## 2020 New Matters (hidden)
CLOSE OUT REPORT ON SCEDULES OF ACTIVITIES AND COST MATTERS FOR GEVDI PROJECT FOR PERIOD OF JULY 2018 TO JUNE 2019
ITEMS ON INITIAL SCHEDULE OF ACTIVITIES AND COSTS (SAC)
Item no. | Agenda Item | Description of activity | Activities required to bring about conclusion of matter | Budget |  | Timeframe required for completion | Comments
1 | Land Legal
1.1 | Land Legal: Specific Instructions
1.1.5 | 2019/2020 Specific Instructions
| Ptn 168 of Farm Wilgefontein No. 869 - FT | This property is owned by the municipality and has 59 people residing on it according to the councillor. The structures that have been built are formal for the most part and appear orderly developed on the site. The remedy that the residents want is for the municipality to pass individual title of these properties to them and for them to be able to access municipal services that are currently not available to them. The site is municipal owned and the residents claim that they have resided over 30 years on the property, is there any merits for prescription on this site?- We request that GeoAfrika please advise the municipality on this matter in terms of how it can be resolved and what are the duties of the municipality in this situation. Further to that, we request that lines of responsibility in the municipality and government be clearly defined, in terms of the role that each individual department will play in resolving this issue. This is of critical importance as at times lines of individual functions become a grey area and at times departments abdicate their responsibility due to lack of clarity policy wise of their respective functions/ obligations. The setting out of steps that need to be taken to address will be of great help. The ultimate objective of this matter is simply to give people individual title and also give them access to services. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Bhoola Property | The dynamics on this property are almost the same as the above property with slight nuances. The property is privately owned and the owner has not had any dealings with the property for a considerable period. The occupiers of the land have built formal structure on the land and have lived on the property for over 30 years which raises the issue of prescription and implications thereof on the remedy sought by the residents. The councillor was championing the cause of the people by bringing the matter forward and to get an understanding what role can the municipality play in helping the people to own individual title and also have proper connection to services. The other issue is the rates attached to the property and in prescribed land what happens. We request that you please provide us with the legal view on prescription as it relates to this matter and to also explain the role that the municipality can play to assist in the matter with the ultimate objective to bring the remedy that is sought to fruition. Also set out the steps that have to be taken by municipality if any. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Erf 159 Edendale J | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Ptn 357 of the Farm Wilgefontein No. 869 - FT | These are privately owned properties that have people residing on them and have also built formal and informal structures. They also require individual title which means that the sites will have to be re-laid in order to give effect to that. However, we have the land acquisition programme which we can use to possibly explore the purchasing of these properties and give effect to this objective. The councillor has indicated that owners are willing to sell the properties as it has been invaded and they have no desire to regain control of the properties. Request that GeoAfrika sets forth ways to deal with this matter and if the municipality based on these site specific circumstances has any obligations. Once we have established that set out the steps that would need to be taken to resolve the matter. | To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Remainder of Erf 16454 Plessis Laer | The site is owned by the municipality and is part of the Edendale town centre radius adjacent to the Edendale Mall and it on Mount Partridge Road. The structure built on the site are formal and orderly developed. The Informal Settlements Relocation Strategy project was undertaken by the municipality and recommended that we formalise the structures. However, a policy position on this matter is not available on the steps needed to do this and the responsibility of each line department concerned in giving effect to individual title. The site has 236 structure on it, which have limited access to water and use pit latrines. 59 households which are situated on either side of mount partridge were built using a government grant that was given to people in 1993 by the Department of Development Aid (DDA), the grant was to the value of R750 and land was made available to the recipients of the grant to build formal structures, which they did. The remainder of the 184 settled on the land without any grant or consent and the structures grew organically albeit formally. The recipients of the grant have PTOs and there is an unregistered GP over these properties (Alan would have to confirm) We request that you please set out the legal procedures that would be needed to formalise the area and functions and responsibilities of the various departments. These legal procedures will certainly begin to set a policy context on these matters moving forward not only for GEVDI but also the municipality especially our Human Settlements Department. Also set out the difference aspects that apply to the resident that received government aid and PTOs , and the one that built on their own with this consent. | Actual property description -:16454 Farm Willow To be investigated -: 1. Evidence 2. Detail Municipality's responsibility 3. Public's Interest 4. Subsidy Instruments 5. Report to SMC | R40 000.00 Disbursement: R20 000 for legal opinion | 60000 | 2 monts
| Investigation: Expropriation Batch 1A: Ptn 15 of Erf 4 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10000
| Investigation: Expropriation Batch 1A: Ptn 2 of Erf 101 Edendale | Instruction forwarded by Narain. Land owner is disputing the expropriation of property due to not being communicated with. Property was expropriated in batch 1A. Facilitations were conducted and property was designated to LTAC | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10001
| Rates: Ptn 8 of Erf 292 Edendale (Mncwabe) | Mr Mncwabe was previously facilitated by Phili Tenza. Upon attempting to sign agreement designation to LTAC Peter Warner was discovered. Facilitation attempts were halted. Mr Mncwabe has rates owing over the property OD has met with Mr Mncwabe & explained the desingation to LTAC. Mr Mncwabe has met with rates & DALARD re: the appointement of the LTAC. | 1. Meet with LTAC 2. Formalise letter to LTAC |  | 10002

## 2019 Matters (hidden)
CLOSE OUT REPORT ON SCEDULES OF ACTIVITIES AND COST MATTERS FOR GEVDI PROJECT FOR PERIOD OF JULY 2018 TO JUNE 2019
ITEMS ON INITIAL SCHEDULE OF ACTIVITIES AND COSTS (SAC) |  |  |  | PROGRESS OF ITEMS AS AT END JUNE 2019
Item no. | Agenda Item | Description of activity | Initial status | Description of activities completed during funding period | Tasks Completed (to be deleted) | Matter Finalised (to be deleted) | Activities required to bring about conclusion of matter | Activities required to bring about conclusion of matter | Budget | Timeframe required for completion | Comments
2 | Finance and Compliance
2.5 | Policy: Valuations Policy | Further comments on Municipally drafted Valuations policy (if needed). Copies of policy to be included in ESITS | The PSP has been instructed to complete the valuations policy and proceed with the same through to Council for approval. | A draft valuation policy has been compiled after interaction with officials of the Municipality. | Yes - what was quoted for has been completed. | No | Draft valuation policy to be finalised and submitted to Council for approval
2.6 | Standard Operating Procedure / Policy: Acquisitions with portions of property to be retained by owner | Finalisation & submission of Standard Operating Procedure: Acquisitions with portions of property to be retained by owner | PSP to draft and finalise Standard Operating Procedures of the acquisition of land with a portion to be transferred to the owner. Once drafted, to be submitted to the relevant Municipal Departments and thereafter to Councils for approval. | This matter was not attended to due to the Municipality's policy & procedures requiring adoption before the end of June 2019. It was determined that a GEVDI specific policy & procedures still required drafting. Once drafted these would be included in the Municipality's policy & procedures. | No | No | N/A
2.7 | Standard Operating Procedure/ Policy: Acquisitions & Expropriations | Annual Review of the Standard Operating Procedures of the GEVDI Project. As Drafted by the (M) | PSP to draft and finalise Standard Operating Procedures of the acquisition and expropriate of land within the project. Once drafted, to be submitted to the relevant Municipal Departments and thereafter to Councils for approval. | This matter was not attended to due to the Municipality's policy & procedures requiring adoption before the end of June 2019. It was determined that a GEVDI specific policy & procedures still required drafting. Once drafted these would be included in the Municipality's policy & procedures. | No | No | N/A
3 | Grant Funding & IGR (Inter-Governmental Relations
3.2 | DOHS
3.2.1 | Property Investigation : Slangspruit Phase 6 : The Farm Willow No 16454 | PSP needs to determine who currently resides in the sites that were earmarked for the Mkhize family and advise the Municipality accordingly. | Mkhize family land used by the Municipality for a development by agreement. In terms of the agreement Mkhize family members who qualified for housing subsidies would be housed identified sites. The family claims they were never allocated sites. | A letter was compiled by the PSP providing an update from the report dated July 2015. To date no response has been received from the relevant implementing agent & the matter could not be progressed further. Cooperation from the implementing agent is required for matter to be finalised. |  | No | In order to complete the investigation comment is required from the Implementing Agent. If this is submitted, the PSP will need to finalise the investigation to confirm the claim of the Mkhize matter& report on further recommendations.
3.2.2 | Subs 239 & 388 of the farm Wilgefontein No. 869 | Enter into a settlement agreement with landowner | This is a historical expropriation (EX203/1995), landowner claims to have never been compensated. No proof of compensation in files. | Advice provided to GEVDI, further instructions and allocation of funds required |  | No | A GISC meeting or Sub-committee meeting with the DOHS is to be held in order for this matter to sit on the agenda. Thereafter further correspondence with the DOHS will be required to ensure finality.
3.2.3 | Land Investigation : Erf 277 Plessis-Laer Christ's Apostles Church | PSP to engage LMO department in dealing with the matter | Church built a structure in Municipal land without consent, has requested the Municipality to donate 0,34 HA of land where the structure is built to them. | Funding was reallocated. | No | No | TBD
5 | Land Legal
5.1 | Land Legal: State Land
51.1 | 22 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | Despite telephonic & e-mail invites for the GISC meeting, the HDA have not attended the GEVDI GISC meeting or provided any insight into the transfers for these matters. | GeoAfrika prepared a letter for the HDA together with annexures & schedules & requested an urgent meeting in order to take the matter forward. | Yes | No | Further interaction with the DOHS & HDA may be required. Once the statutory formalities have been concluded, a conveyancer can be appointed & transfer can take place
5.1.3 | 42 Properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | Despite telephonic & e-mail invites for the GISC meeting, the HDA have not attended the GEVDI GISC meeting or provided any insight into the transfers for these matters. | GeoAfrika prepared a letter for the HDA together with annexures & schedules & requested an urgent meeting in order to take the matter forward. | Yes | No | Further interaction with the DOHS & HDA may be required. Once the statutory formalities have been concluded, a conveyancer can be appointed & transfer can take place
5.1.3 | Public Works Reversions (from Exception report) | The Public Works reversion transfers were not finalised due the Municipality's investigation into rates over the properties. | GeoAfrika have consulted Public Works about these transfers, it was deemed necessary that the properties be re-confirmed due to the passage of time which has occurred since identification. | The properties identiied for reversion were reviewed by the Municipality and Dept. of Public Works to check for change of status and reach agrement on changes through various interactions. A report was compiled and submitted to the HOD of Public Works. Public Works are reviewing batches of properties to accept the reversion transfers and have to date paid most of the outstanding rates on properties | Yes | No | Complete review of properties with Municipality and Public Works. Receive formal acceptance from Public Works on those properties that can be transferred in the interim. Submit memo to Council. Instruct Conveyancer to proceed with transfers in batches as agreement is reached.
5.1.4 | Nedbank Properties | The transfer of the properties from Nedbank to the Municipality have been completed. The remaining tasks for this matter are determined by the reports previously tabled with the Municipality which state that the Municipality cannot simply transfer the properties to the current occupants because of the encroachments & various other 'on the ground' factors which affect the sites. | It is clear from the reports that the Municipality must intervene to resolve the situation including conducting the following tasks: Social beneficiary survey, Planning to relayout the area in order to accommodate as many households as possible, Planning & Development consents in terms of SPLUMA & the PDA to be sought, the basic conditions of NEMA to be adhered to., Consolidation * relayout of the properties and once one the ground situations have been rectified transfer of the newly created properties. | Funds reallocated. | No | No | It is clear from the reports that the Municipality must intervene to resolve the situation including conducting the following tasks: Social beneficiary survey, Planning to relayout the area in order to accommodate as many households as possible, Planning & Development consents in terms of SPLUMA & the PDA to be sought, the basic conditions of NEMA to be adhered to., Consolidation * relayout of the properties and once one the ground situations have been rectified transfer of the newly created properties.
5.1.5 | Willowspruit - Donation of 7 properties | The HDA & DOHS have not completed the statutory formalities for these properties to be transferred to the Municipality. | Despite telephonic & e-mail invites for the GISC meeting, the HDA have not attended the GEVDI GISC meeting or provided any insight into the transfers for these matters. | PSP prepared a letter for the HDA together with annexures & schedules & requested an urgent meeting in order to take the matter forward. High level intervention from Municipality may be requiredto ensure cooperation from HDA. | Yes | No | Further interaction with the DOHS & HDA may be required. Once the statutory formalities have been concluded, a conveyancer can be appointed & transfer can take place
5.1.6 | Musi Thuzi School: Ptn 7 of Erf 206 Edendale | Assist with the relayout, survey and subdivision of the property in order to accommodate the school, owner and the IRPTN | As at May 2016, there was a conflict between the layout of the school and the IRPTN. The Planning dept. undertook to have an urgent meeting with the stakeholders. | This property is being dealt with as part of the Dept. of Public Works reversion transfers | N/A | No | This particular matter of the Muzi Thuzi School cannot be taken further until the matter with the IRPTN has been resolved and defined. A settlement agreement will then be concluded between KZN PW, the Mini Family and the Municipality.
5.2 | Land Legal: Upgrading of Tenure
5.2.1 | Ashdown: Opening of Township Register and Upgrading of Tenure Rights in term of ULTRA, Act 112 of 1991 | Completion of Donation agreement & submission to Municipality toward the opening of the township register & endorsment of Title Deeds | Donation agreement was provided to the Municipality (Atkins) in July 2016 in order to facilitate the signing of the donation | PSP provided a report to the Municipality which explained the process of the opening of the township & the ULTRA upgrade. Subsequent to this the donation agreement & annexures were provided to the DOHS for signing. The DOHS responded with some queries which have been addressed & the agreement is being circulated through DOHS for signature. | Yes | No | Once the DOHS have returned the signed agreement, the Municipality is to sign the agreement. Thereafter the appointed conveyancer who has prepared the necessary documents is able to complete the necessary conveyancing tasks to open the Township Register & effect the ULTRA upgrade.
5.3 | Land Legal: Portions of Land being returned to Seller
5.3.1 | Erf 198 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | As per the Settlement Agreement with the Municipality, the Land Titles Adjustment Commissioner is to conduct the survey & transfer for this property. GeoAfrika' s role was therefore to oversee this process & to ensure that this abided by Municipal procedures. |  | No | LTAC to appoint surveyor, provide necessary documentation to the Municipality as per the settlement agreement. Municipality to sign the Power of Attorney provided by the LTAC. Thereafter Surveyors to complete the necessary processes in line with the annexed image from the settlement agreement.
5.3.2 | Rem of Ptn 7 of Erf 15 Edendale | The property is owned by the Msunduzi Municipality and was acquired from Fred Tshablala. | The signed agreement provided for Fred Tshabalala to retain the portion of the property he currently occupies. | Report & addendum to Deed of Sale prepared and submitted to GEVDI for legal vetting and approval. |  | No
5.3.3 | Ptn 11 of Erf 118 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | This property is currently held up by the rates clearance matter - item 4.4.1 & has not been transferred to Municipal ownership. | N/A - Cannot be completed before transfer | N/A | Dependant on the rates clearance & transfer of the property to the Municipality
5.3.4 | Erf 22, 23 &24 Wilgefontein | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | This property is currently held up by the rates clearance matter - item 4.4.1 & has not been transferred to Municipal ownership. | N/A - Cannot be completed before transfer | N/A | Dependant on the rates clearance & transfer of the property to the Municipality
5.3.5 | Erf 142 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit (to be dealt with upon full council policy approval as per 8.3) | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. | This property is currently held up by the rates clearance matter - item 4.4.1 & has not been transferred to Municipal ownership. | N/A - Cannot be completed before transfer | N/a | Dependant on the rates clearance & transfer of the property to the Municipality
5.3.6 | Erf 52 & 53 Edendale | Co-ordination and appointment of specialist service providers to deal with retained portion of land for owners benefit | · Diagram for the proposed retained section has been drafted and approved by both parties. · Settlement agreement with LTAC and Msunduzi has been finalized. Survey and transfer of the Sub-division to be undertaken to complete the process. Power of Attorney prepared and signed to enable surveyor to do subdivision. | As per the Settlement Agreement with the Municipality, the Land Titles Adjustment Commissioner is to conduct the survey & transfer for this property. PSP s role was therefore to oversee this process & to ensure that this abided by Municipal procedures. |  | No | LTAC dealing with the matter.
5.4 | Land Legal: Investigations
5.4.1 | Erf 177 Edendale | Rates Clearance Certificate has not been issued despite the conveyancer having paid for the same. | ·A report dated 22/04/2016 was tabled at LLC · This is a historical matter where the rates clearance certificate has not been issued despite the conveyancer having paid for same Due to the property being designated in terms of the Land Titles Adjustment Act No. 111 of 1993 a conveyancer will need to be appointed | Due to the time which had elapsed since the matter was referred to the LLC, PSP requested confirmation from Trevor Cowie that the matter had not been concluded in the absence of the LLC meeting. PSP received no response to this e-mail and was later informed that Mr Cowie had retired. Status of the matter required from Municipality for it to be concluded. |  | No | N/A
5.4.2 | Erf 519 &2754 Edendale N | Submit status report only | · Conflict of title previously reported at LLC · Property is still under investigation with regards to the two sets of ownership which are reflecting on it. The project conveyancer (Mac) attended a meeting with Ithala and the Municipality | Funds reallocated. |  | No
5.4.3 | Re-submit reports to Council
5.4.3.1 | Erf 558 Ashdown | Mrs Muthwa claimed that she was the owner of the property which is currently occupied by Mr B Zondi. | PSP found no evidence to support Mrs Muthwa's claim. | Report submitted to GEVDI with proposed letter to Mrs Muthwa | Yes | No | N/A
5.4.3.2 | Erf 855 Edendale N | Msunduzi Municipality is operating a quarry on Erf 855 Edendale without permission from the property owner. | PSP to investigate | PSP has compiled a letter which maintains the recommendation from the reports tabled in June 2015. Which was submitted to GEVDI recommending acquisition of the property in question. | Yes | No | Further instruction and allocation of funding.
5.4.3.3 | Erf 1700 Edendale BB | Conflicting General Plans as Erf 1780 overlays Erf 182. | Instruction to investigate conflict. | Report recomending allocation of funds for a High Court Application submitted to GEVDI. |  |  | High Court Application to remedy conflict required.
5.4.3.4 | Erf 1172 Edendale CC: Mahlobo Property - Twala Road | Landonwer being charged rates for Erf 1172 & 1173 while only resides in and owns Erf 1172. | Erf 1173 may have been registered to the owner of Erf 1172 in error. | PSP has compiled a letter which maintains the recommendation from the reports tabled in April 2016. This will be submitted to the Municipality in due course for re-submission to Council and determination on the recommendations. | Yes | No
5.4.3.5 | Erf 1655 Edendale S | Update report (including recommendations) and submit to Council for Approval | PTO Investigation : Underlying Erf 1655 Edendale S | Funds reallocated. |  |  | Investigation to determine way forward
5.4.3.6 | Erf 1570 Edendale CC | Update report (including recommendations) and submit to Council for Approval | Tenure Conflict investigation : Erf 1570 Edendale Unit CC | Funds reallocated. |  |  | Investigation to determine way forward
5.5 | Land Legal: Priority Individual Matters
5.5.1 | Mavundla - Erf 7974 Edendale DD | Completion of investigation and report for further legal process to follow. | Property has been transferred to the Municipality – 12/10/2018. Property needs to be allocated to Mavundla and possible communication process. | Funds reallocated. |  |  | Council resolution required for the reallocation of the property to the Mavundla family. Conveyancer to then conduct transfer to the family.
5.5.2 | Bhengu//Gabela Eviction | Completion of investigation and report for further legal process to follow. | The PSP has corresponded with the relevant lawyers and stayed the impending court action. Property needs to urgently be dealt with. | The comprehensive activities needed to conclude this matter were not able to be funded from the available budget. A Comprehensive budget was provided to the Municipality. | No | No | Planning, SPLUMa, Survey, negotations with landowners, signing of agreements, registration & transfer
5.6 | Municipality
5.6.1 | Slangspruit Buffer: Tenure Rectification | Attend to Slangspruit Buffer: Tenure Rectification | Slangspruit Buffer: Tenure Rectification to be done | No activities were included in the current tranche funding for this matter. | N/A | N/A | N/A
5.6.2 | Slangspruit Buffer: Land invasion. | Assess and attend to Slangspruit Buffer: Land invasion. | Land invasion in Slangspruit Buffer | No activities were included in the current tranche funding for this matter. | N/A | NA | N/A
8 | Special Projects and Land Development
8.1 | NDPG Programme | To be determined | To be determined | No activities were included in the current tranche funding for this matter. | N/A | N/A | N/A
8.2 | Project Focus: Disposal & Ennoblement of land in Edendale for purposes of generating income | Finalise and implement ennoblement plan | A draft ennoblement plan was created and needs to be finalised and implemented | No activities were included in the current tranche funding for this matter. | N/A | N/A | N/A
9 | Specific Tasks & Instructions
9.1 | Investigation: Erf 1655 Edendale S: Inzozoyesizwe School | Completion of investigation and report for further legal process to follow. | As per e-mail from Nkululeko Mkhungo, PSP has been requested to investigate this property | This matter is related to the State Land Transfers/ Reversion. | N/A | N/A
9.2 | Consolidated Edendale Report | A consolidated Edendale report is being compiled by GEVDI with input required on certain sections of the document by the PSP |  | Completion of parts of the consolidated Edendale report as highlighted by GEVDI. This includes write-up, maps, statistics and images |  |  | Completion of document
9.3 | Development Catalogue (Bankable Document) | Prepare a development catalogue (bankable document) that can be used to obtain funding from public and private funders |  | Preparation of development catalogue (bankable document) |  |  | Completion of document
9.4 | GEVDI Video | Produce a short video to market Edendale to potential funders |  | Initial research required for information for the video |  |  | Completion of video in future funding tranches depending on priorities
9.5 | Implementation Protocol. | Arising from the GISC meeting and discussions with Narain the need for a formalised Implementation Protocol between the Municipality and the government entitles contributing the GEVDI project was determined. | GeoAfrika has set up meetings with various GISC parties (DOHS, COGTA, DRDLR, KZN PW) in order to populate the terms and conditions within the Implementation Protocol. | GeoAfrika has drafted the Implementation Protocol. However due to the input which is required from the various Government entities, the document cannot be further completed without their input. |  | No | Further engagement with the Government Departments with respect to their available inputs to document is to take place.
9.6 | Edendale GISC Sub-Committee Meetings with various Government Departments | A by-product of the GISC meetings being raised to a higher level of meeting resulted in the need for GISC Sub-committee meetings with the various Government Departments - KZN PW, DRDLR, DOHS, HDA, COGTA, Treasury etc. | 2 Sets of GISC sub-committee meetings have been held for the periods of January 2019 - June 2019. | 2 sets of GISC sub-committees have been held. On-going meetings will deal with strategic matters so as to ensure GISC is a high level meeting. | Yes | N/A | N/A : Ongoing Matter
9.7 | Edendale Town Centre Built Form & Design Guide Portfolio Programme & Budget | GEVDI requested GeoAfrika assist with the preparation of the Built Form & Design Guide for the inclusion in the Bankable Document & the Edendale video. | Built form and design guide portfolio of Town Centre required | The necessary has been completed by the architect and provided to the Municipality |  |  | N/A
9.8 | GEVDI Risk Workshop | In support of the Development Catalogue of Interventions & the Bankable Document, a Risk Workshop was held to determine the current, future and priority risks that the project is facing. | A GEVDI risk profile required | Risk profile workshopped and documented in report provided to Municipality. This report is to be included with the development catalogue of interventions and assist with the bankable document. | Yes | Yes | N/A
9.9 | Town Centre: Preparation of Project Base Line Documents for Block 1,4 & 5 | Narain requested GeoAfrika assist with the preparation of the project base line documents for the Edendale Town Centre and specifically for black 1,4 & 5. This was completed by the Architect who has been working on the Town Centre. | Basline documents for blocks 1, 4 and 5 of the Edendale Town Centre required | The necessary has been completed by the architect and provided to the Municipality |  |  | N/A
9.1 | ICT Hub: Town Centre Precinct | Preparing a business plan for the review & development of an ICT Hub In Edendale Town Centre. | Concept revision of ICT hub required | Phase 1 including the Concept revision - The report has been drafted, required amendments have been made and forwarded to the Municiplaity |  |  | N/A
9.11 | Case Studies for Consolidated Report & Bankable Document | Case studies required for consolidated report and bankable document | Case studies required | Case study completed and presented to Municipality for inclusion into consolidated report and bankable document |  |  | N/A
1.1.4 Specific Instructions - *NEW ITEMS*
1.1.4 | Erf 68 Unit J - Imbali - Mncwabe | Mr Z Mncwabe representing the Zaca family requested GEVDI's assistance in providing a brief history for the property due to receiving a rates bill for the property. |  | GEVDI requested PSP investigate the property & provide history (06/09/2018). This was provided to Mr Mncwabe on the same date. | Yes | Yes | N/A
1.1.4 | Ptn 8 of erf 292 Edendale - Mncwabe | Arising from the Erf 68 Unit J query, Mr Mncwabe also queried about Ptn 8 of Erf 292 Edendale (04/10/2018) & the request for GEVDI's assistance with 1. Rates Clearance & 2. transferring of late estate ownership into the executors name. | During the previous tranche funding, the facilitators were instructed to attempt the acquisition of this property in the hopes that we would receive a confirmation by the Land Titles Adjustment Commissioner who was delegated to this property (Peter Warner). | As this property has been delegated to LTAC Peter Warner, we have been unable to assist with the transferring of Title into the executors ownership. We have however opened discussions with the DRDLR on the appointment of Peter Warner & the possibility of reappointing. | N/A | N/A | Confirmation required from DRDLR re: the appointment of Peter Warner.
1.1.4 | Town Centre - Relocations & Lack of Service Delivery | The town centre is facing various areas where assistance may be required by PSP who have extensive experience with relocations through their work on the SANRAL contract. |  | No tasks have been set for this matter with this tranche funding. | N/A | N/A | N/A
1.1.4 | Edendale Ward Councillor Workshop - 21 June 2019 | GEVDI requested support from GeoAfrika for the Edendale Ward Councillor meeting set for 21/06/2019. This included presenting information on the GEVDI Land Acquisition project, the amount of land currently purchased, the Town Centre etc. |  | The Edendale Ward Councillor workshop was held on 21/06/2019, the workshop was attended by the GeoAfrika team who prepared presentations on the GEVDI Land acquisition project touching on the Priority Housing projects, town centre etc. | Yes | Yes | N/A
1.1.4 | GEVDI Document Site | In support of the GISC meetings it was determined that a Document website should be created in order to store documents (e.g. GISC Minutes, resolutions, Council Resolutions, Council Reports etc.) In order for these documents to be viewable by the GISC members, auditors & GEVDI team. |  | There were no activities completed in this item as the requirement needs to be fully scoped with Municipality before starting | Yes | Yes | Scoping of requirements and then development of system
1.1.4 | Business Plans: Manye Hall, Heroes Precinct etc. as per presentation | GEVDI forwarded the Manaye Hall presentation by Zilungile to the GeoAfrika team requesting that discussion be entered into to convert each project into its own Business Plan. This was forwarded on 03/06/2019. | Due to the shortage of confirmed funding, this has not been taken further with this tranche funding. | There were not activities completed for this item which will be carried forward to the next funding tranche | N/A | N/A | N/A
1.1.4 | Letter of KZN Public Works re: State Land | GEVDI requested that GeoAfrika prepare a letter for KZN Public Works with reference to the State Land Reversion transfers. |  | GeoAfrika prepared a report with necessary maps as annexures. This was provided to the Municipality for the GM's signature on 14/06/2019 | Yes | Yes | N/A
1.1.4 | Letter to DRDLR re: Business Plan & LTAC | GEVDI requested that GeoAfrika prepare a letter for DRDLR, it was deemed prudent that this letter address a number of issues that the project was facing & serve as the submission of the properties for the R20million funding as per the MOA with DRDLR |  | GeoAfrika prepared a letter for DRDLR, topics which were discussed in the letter were: Land Acquisition Funding, Funding for Land Tenure, GISC Meetings, Implementation Protocol, BP2020, Deceased Estates, LTAC appointments & LTAC Peter Warner. | Yes | No | N/A
1.1.4 | Letter to HDA re: GISC Meetings, State Land & Implementation Protocol. | GEVDI requested that GeoAfrika prepare a report on all HDA land in Edendale. This was to be supported by maps from GIS. |  | GeoAfrika prepared a report with necessary maps as annexures. This was provided to the Municipality for the GM's signature on 14/06/2019 | Yes | No | N/A
1.1.4 | Capture in individual cases in Query System | GEVDI requested the individual case matters be uploaded into the Query system & mapped on the GIS. |  | GeoAfrika uploaded all individual matters into the query system. | Yes | N/A - Ongoing | N/A
1.1.4 | Schedule of Properties: including Land Legal individual case files & groups of properties | GEVDI requested a schedule of all properties which are/ have been dealt with through the project. PSP populated a schedule including all individual case file matters & groups of properties e.g. State Land Reversions, Business Plan Properties, Expropriation etc. |  | PSP provided a comprehensive list of properties speaking to the GEVDI request. This document has been updated as at 2 July 2019. | Yes | N/A - Ongoing | N/A
1.1.4 | Report/ Request to CM to sign GEVDI Deeds of Sale. | Report required because the CM would not sign Erf 54 Harewood agreement without Council Approval. | PSP prepared a report/ memo for the CM detailing the properties which require purchasing with the current tranche funding & requesting the CM to sign the necessary sale agreements The CM agreed to sign the agreements for Erf 54 Harewood. Other properties to be purchased using current funding were expropriations and did not require the CM's signature on a sales agreement. | PSP prepared a report/ memo for the GM detailing the properties which require purchasing with the current tranche funding & requesting the CM to sign the necessary sale agreements | Yes | Yes | N/A
1.1.4 | Report: Ministerial Representative | GEVDI requested assistance from PSP on creating a report on all land which have been bought, sold and bought for Human Settlement Purposes in the GEVDI area. | PSP prepared the report necessary for the Ministerial Representative.& forwarded same to GEVDI | PSP prepared a schedule & covering letter for this matter, in addition further queries were expanded upon in order to provide clarity on the methods of acquisition within the GEVDI Initiative (Purchase & Sale, Expropriation, Vesting, Donation Agreements, State Land Transfers etc.) | Yes | Yes | N/A
1.1.4 | Sub 25 of the Farm Wilgefontein No. 869 - Khambule Family | GEVDI requested that an investigation be done following a query by the Khambule Family regarding their property & people selling portions of the property in question. | PSP provided a report including facts & recommendations. | PSP conducted an investigation into the property & provided an e-mail response including the facts & recommendations of how to handle the matter. This 'report' was provided to the Municipalities legal team. Further instruction based on the recommended tasks is awaited | Yes | No | N/A
1.1.4 | Unit DD: Case Files | GEVDI requested a list of all Unit DD Case files. | The Unit DD case files that were known to PSP were included in the GEVDI Case files list, these were also uploaded into the query tracking system. | The Unit DD case files that were known to PSP were included in the GEVDI Case files list, these were also uploaded into the query tracking system. | Yes | Yes | N/A
1.1.4 | Business Plan - Dambuza Donga | GEVDI requested that an amendment be completed on the Tranche 2 DOHS Business Plan to include the properties within the environmentally sensitive area of Dambuza Donga. | Under the guidance & instruction of GEVDI. PSP sat with GEVDI to compile a list of properties which would speak to this amendment. | PSP prepared the list of properties with current values & necessary costs. This was then included with a covering letter and sent to the Municipality for signature and onward motion to the DOHS. | Yes | No | N/A
1.1.4 | Erf 1570 Edendale Housing Development Grant | GEVDI instructed PSP to respond to a query from the Public Protector relating to the problems that the owner was having developing her site. | PSP investigated the ownership & land use of the site & prepared a report. | After conducting its investigation, PSP prepared a response for the GM to address the problems that the land owner was having with the community. | Yes | No | N/A
1.1.4 | Erf 52 Plessis Laer - Cancellation of Expropriation. | Masons attorneys approached the Municipality for assistance with the removal of a expropriation interdict over Erf 52 Plessis Laer. | After Investigation it was determined that the expropriation Interdict was mistakenly endorsed on this property by the Deeds Office. The Deeds Office have noted that this was completed in error. | GeoAfrika forwarded a letter to the Deeds Office including historical correspondence related to this matter. The Deeds Office confirmed that they have received the letter & we are awaiting confirmation on whether a further process is required to remove the incorrect interdict. | Yes | No | Possibly formal application to be made for the removal of the interdict.
1.1.4 | Erf 601 Edendale N - Archdiocese of Dbn Catholic Church | Chazile (City Estates & Valuations) requested assistance with historical information with reference to the sale of said property from the Municipality to the church. | The GeoAfrika team using the documents on our historical files assisted with this query. It is to be noted that the property is a State Owned property which has not been transferred to the Municipality as yet. | PSP provided a report to Chazile. GeoAfrika was then informed (through e-mail from Chazile) that the way forward was to transfer the property once it has been transferred to the Municipality. | Yes | Yes | State Land Transfer to be completed.
1.1.4 | Eviction: Magudulela & Gazu 199 Mnsinisi Road - Erf 1018 Edendale DD. | GEVDI instructed PSP to investigate & respond to a query from the CM's office. The Property in question is: 199 Mnsinisi Road - Erf 1018 Edendale DD. | PSP investigate the property, reason for the Eviction and the Permission to Occupy claim and provided a report with relevant annexures & recommendations. | PSP provided a report to GEVDI with background, the legal status of Permission to Occupy documents, Upgrading of Land Tenure Rights & recommendations. No further instructions have arisen. | Yes | No | further instructions may arise based on recommendations.
1.1.4 | Expropriation: Ward 21 Properties (Peter Warner appointed Mtimkulu & Twala properties) | GEVDI instructed PSP to prepare an expropriation report for the following properties: Erf 19 Edendale, Ptn 1 of serf 15 Edendale, Rem of Erf 325 Edendale. These properties are located in ward 21 & have previously been delegated to the Land Titles Adjustment Commissioner Peter Warner by the DRDLR. | PSP have brought the Peter Warner delegation to the DRDLR & requested that the LTAC be reappointed OR for the properties to be designated to another LTAC. As yet, there has been no finalization of the LTAC appointment. Due to the high priority of these properties, PSP have compiled a report for Council for the expropriation of these properties, should the LTAC be confirmed, GEVDI will withdraw the Full Council report & the need for the expropriation. | PSP has prepared a Full Council report for the expropriation of these properties. As per the end of this tranche funding, this had not been approved by Full Council - GEVDI was aware of this & instruction was based on the Council Report being compiled with current tranche funding | Yes | No | While the Council report was compiled & submitted. The remaining expropriation processes will require funding from Tranche 2..
1.1.4 | Expropriation: Comments on Bill for CIGFARO | GEVDI requested PSP s assistance with providing comments on the Expropriation Bill which was circulated by CIGFARO. | PSP perused the supplied documents & provided comments. | PSP provided comments on the supplied document. | Yes | Yes | N/A
1.1.4 | Town Centre: Land Legal Report | GEVDI requested GeoAfrika to compile a Land Legal Report/ Audit for the properties which make up the Town Centre Expropriation. | GeoAfrika requested SG Diagrams, compiled GIS images, Title Deeds & Servitudes from the Deeds Office. This was then investigated & a report compiled. | GeoAfrika compiled a report based on documents from the Deeds Office, GIS aerial imagery etc. and provided same to the Municipality. | Yes | Yes | N/A
1.1.4 | Audit Query: Auditor General: Co-owned Properties within GEVDI region. | GEVDI requested PSP s assistance with responding to an Audit Query on 10 properties which are in shared ownership (Municipal owned shares & Privately Owned Shares) | PSP compiled a response to the auditor which included the Windeeds, Title Deeds & Sales Agreements for the relevant properties. | PSP forwarded a report & annexures relating to these properties as a response to the Auditor General. | Yes | Yes | N/A
1.1.4 | COGTA: Complaint Against Msunduzi - Khuzwayo Matter | GEVDI requested PSP's assistance with a complaint received from COGTA - referred to as the Khuzwayo Matter- and the joint ownership between the Municipality & the private owners. The properties are: Ptn's 31, 32, 34 & 36 of the Farm Wilgefontein No. 869 | After the initial investigation into the complaint, PSP met with COGTA & the Municipality in order to formalise tasks including the compiling of a report. GeoAfrika further investigated the various complaints that private owner had & compiled further report & recommendations for the Municipality. In addition, PSP has appointed an independent valuer to provide the current value of the properties, and the rental value of Municipal infrastructure over the properties as per the reports which have been provided. | PSP have provided a report & various other correspondence to the Municipality in order to assist with how this matter should be dealt with. | Yes | No | Approval from Legal & Council. Negotiations with Khuzwayo family, Signing of Settlement & Sale Agreements, Registration and trasfer.
1.1.4 | Historical LTAC Appointment by DRDLR : Peter Warner | Approx. 30 properties are still under the historical ('90's) delegation to Peter Warner in terms of the Land Titles Adjustment Act No. 111 of 1993. Due to the GEVDI project requiring these properties for development, GeoAfrika were instructed to liaise with DRDLR in order to address this matter. | Due to several of these properties falling into Priority Housing Project areas, GeoAfrika has opened communication with DRDLR in order to either 1. Confirm the appointment of LTAC Peter Warner or 2. have these properties reappointed to a different LTAC. | GeoAfrika has met with DRDLR in order to address this matter, The DRDLR understand the problem and were to reconfirm the appointment of Peter Warner. GeoAfrika have also included this matter in the letter for DRDLR that included the schedule of properties for acquisition. | Yes | No | Further cooperation is required from DRDLR in order for these properties to be dealt with & acquired.
1.1.4 | Policy: Land acquisition, Land Ennoblement & Land Disposal | GEVDI requested PSP to provide input & comments into various policies including the Immovable property disposal framework, land disposal policy etc. | PSP provided input into the Immovable Disposal Policy.PSP met with LMO regarding these policies and the incorporation of the GEVDI region. Due to the timeframe that the Municipality had to adhere to, it was determined that there was not enough time to amend the policy. It was decided that a GEVDI specific policy would be drafted and that this would then be included in the Municipality's policy at a latter date. | PSP met with LMO regarding these policies and the incorporation of the GEVDI region. Due to the timeframe that the Municipality had to adhere to, it was determined that there was not enough time to amend the policy. It was decided that a GEVDI specific policy would be drafted and that this would then be included in the Municipality's policy at a latter date. | Yes | No | N/A
1.1.4 | Policy: Land Invasion | Narain requested GeoAfrika to provide input & comments into various policies including the Immovable property disposal framework, land disposal policy etc. | GeoAfrika Met with Mthobisi & Nosihle regarding these policies and the incorporation of the GEVDI region. Due to the timeframe that the Municipality had to adhere to, it was determined that there was not enough time to amend the policy. It was decided that a GEVDI specific policy would be drafted and that this would then be included in the Municipality's policy at a latter date. | GeoAfrika Met with Mthobisi & Nosihle regarding these policies and the incorporation of the GEVDI region. Due to the timeframe that the Municipality had to adhere to, it was determined that there was not enough time to amend the policy. It was decided that a GEVDI specific policy would be drafted and that this would then be included in the Municipality's policy at a latter date. | Yes | No | N/A
1.1.4 | COGTA: Premier's Office -Nkululeko Development Project | Through the discussions at the GISC meetings, COGTA mentioned the possibility of putting forward GEVDI as a Premier's project. Following this discussion, Narain requested GeoAfrika assistance with this matter. | GeoAfrika have provided Kate (COGTA) with documents & presentations to highlight the GEVDI project to Mrs Mkhize from the Premier's Office. Further correspondence will be necessary to officially submit the project to the Premier. | GeoAfrika have provided Kate (COGTA) with documents & presentations to highlight the GEVDI project to Mrs Mkhize from the Premier's Office. | Yes | No | Necessary actions will arise from further communications with COGTA. Upon its completion, the Premier's Office will be supplied with a copy of the Development Catalogue of Interventions & the Bankable Document.
1.1.4 | State Land: Request for Donation from HDA : Erf 207 Edendale | GEVDI requested assistance with the acquiring of this property from HDA. | PSP assisted GEVDI by drafting a letter for HDA in which the Implementation Protocol was introduced & the request for the HDA to engage with the Municipality in order to donate/ transfer the property to the Municipality. | PSP assisted GEVDI by drafting a letter for HDA in which the Implementation Protocol was introduced & the request for the HDA to engage with the Municipality in order to donate/ transfer the property to the Municipality. This letter was forwarded to the Municipality for the GMs signature | Yes | No | Correspondence with the HDA still to be undertaken.
1.1.4 | Tshabalala Matter Report - Properties: Erf 238 Edendale, Erf 218 Edendale, Ptn 2 of Erf 8 Edendale | GEVDI requested assistance from GeoAfrika in dealing with this matter - known as the Tshabalala Matter. | PSP have investigated & surveyed the properties in order to provide an accurate report on the allegations from the Tshabalala family. | PSP have provided a report & various other correspondence to the Municipality in order to assist with how this matter should be dealt with. No further instruction has been provided. | Yes | No | Further instruction required to finalise matter.
1.1.4 | Query: Funds with MFI: Ptn 16 & 17 of Erf 233 Edendale | GEVDI requested GeoAfrika' s assistance with clarifying the funds held by MFI in relation to 2 properties - Ptn 16 & 17 of Erf 233 Edendale. | GeoAfrika have provided a response to the Municipality based on these funds. | GeoAfrika provided feedback in repsonse to GEVDI query | Yes | Yes | N/A
1.1.4 | Expropriation Transfer of : Ptn 16 & 17 of Erf 233 Edendale | Arising from the above query, it was noted that the properties Ptn 16 & 17 of Erf 233 Edendale have not been transferred to the Municipality. | This matter was highlighted at a point when project funding was unavailable. Upon the security of funding, the LTAC is to be approached to determine why the Expropriation Transfer was not completed & transfer can be instructed. | Due to lack of funding this matter could not be taken any further with current funding, in addition, formal instruction from the Municipality has not been received. | N/A | No | Funds to be transferred from MFI back to the Municipality. Correspondence with the LTAC to be undertaken in order to complete expropriation transfer.
1.1.4 | Erf 198 Edendale Allocation of Portion of Property | GEVDI requested an investigation to be completed into building of a site on the property for Mr Sithole & the issuing of a permission to occupy for the same. | GeoAfrika provided the previously signed settlement agreement with the LTAC & the Municipality which included a clause for sub-divisions to be transferred from the property. No further instruction was received. | GeoAfrika provided the previously signed settlement agreement with the LTAC & the Municipality which included a clause for sub-divisions to be transferred from the property. No further instruction was received. | N/A | No | TBD.
1.1.4 | Land acquisition: Properties with Shared Ownership ( Municipal & Private owners) | These properties were highlighted as a result of an audit query. These properties have shared / joint ownership between the Municipality and a private person. | These properties require acquisition/ expropriation in order for Municipality to fully acquire property. | Properties were not prioritised for acquisition. Instruction and allocation of funding will need to be given for matter to be actioned as part of future tranches |  |  | Further instruction and allocation of funds required to finalise the matter
1.1.4 | Land Acquisition: Possible purchases. | Various land owners have approached the Municipality with reference to the acquisition of their properties. | The acquisition of these properties require instruction from GEVDI in order to begin the formal acquisition process. | Properties to be prioritised for acquisition. Instruction and allocation of funding will need to be given for matter to be actioned. |  |  | Further instruction and allocation of funds required to finalise the matter
1.1.4 | Vesting Transfers:Various transfers from State to Msunduzi | GEVDI requested a report be compiled by PSP in order to appoint conveyancers MFI to complete the vesting transfer. | Report being compiled in order to provide MFI the correct facts on these matters | PSP is in the process of drafting a report for GEVDI. This instruction was provided in July 2019. |  |  | Report to be compiled & funding to be allocated in order to instruct conveyancer to transfer.
Note on A6: Jane Tennet: Land Acquisition 2.5-2.7
Note on A19: Jane Tennet: Separate file - not land legal
Note on A21: Jane Tennet: Pradeep to confirm
Note on A27: Jane Tennet: Odwa/ Hoffy to advise on wording for this matter. No work was completed.
Note on A32: Jane Tennet: Hoffy to deal with but not land legal matter
Note on A37: Jane Tennet: Odwa to advise on wording for this matter as some work has been completed.
Note on A112: Jane Tennet: Pradeep to confirm whether to keep this instruction
Note on A133: Jane Tennet: Discuss with Narain & Atkins