## SDBIP COVER
MSUNDUZI MUNICIPALITY
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2025/ 2026 FINANCIAL YEAR
ANNEXURE E
#VALUE!
ADJUSTMENT SDBIP - 2025 / 2026

## ANNEX C
ANNEXURE C: MONTHLY PROJECTION OF OPERATIONAL EXPENDITURE BY VOTE
DESCRIPTION | BUDGET YEAR 2024/2025
R THOUSAND | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | BUDGET YEAR 2025/ 2026 - TOTAL
Employee related costs | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 160057918.5326 | 1920695022.3918
Remuneration of councillors | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 5870803.9121 | 70449646.9448
Bulk purchases - electricity | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 293544430.6667 | 3522533168
Inventory consumed | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 84460520.1773 | 1013526242.1275
Debt impairment | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 56180000 | 674160000
Depreciation and amortisation | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 32521695.2117 | 390260342.54
Interest | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 4681666.6667 | 56180000
Contracted services | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 71319194.8737 | 855830338.4846
Transfers and subsidies | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 6038077.9732 | 72456935.6784
Operational costs | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 19895231.8995 | 238742782.7941
Total Expenditure | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 734569539.9134 | 8814834478.9612

## CAPEX 3 YEAR PLAN (2)
Functional area | Business Units | Functional area desc | Funded Program | subvotes | Current Budget | Actual GL | 2024/2025 | MOTIVATION
101011 | City Manager | CITY MANAGER | A/101011.BAH.A52 | 2 | 1000000 |  | 2500000
101011 | City Manager | CITY MANAGER | A/101011.BAH.A53 | 2 | 4000000 | 58998.1 | 2500000
202035 | City Finanace | G M - CFO | I/202035.001 | 1.4 - Strategic Planning | 30000000 |  | 25000000 | 27300625
304001 | Corporate Services | HR - SUSTAIN DEV | A/304001.BAH.A52 | 2.5 - Supply Chain Management | 0 | 0 | 0 | EVODIA 2 X LAPTOPS
304346 | Corporate Services | OCCUPATIONAL HEALTH | A/304346.BAH.A60 | 2.5 - Supply Chain Management | 0 | 0 | 50000 | ECG(R20K)AIRCON(R40K)GAZEBO X 5 (R20K)+2 GAZEBO MORETLO(R10K)
304346 | Corporate Services | OCCUPATIONAL HEALTH | A/304346.BAH.A52 | 2.5 - Supply Chain Management |  |  | 60000 | LAPTOPS 2X JABU ELCT +CE+3 X SAFETY+5X MORETLO+2X DESKTOPS
304346 | Corporate Services | OCCUPATIONAL HEALTH | A/304346.BAH.A61 | 2.5 - Supply Chain Management |  |  | 0 | SEDAN SAFETY OFFERS
304346 | Corporate Services | OCCUPATIONAL HEALTH | A/304346.BAH.A53 | 2.5 - Supply Chain Management | 0 | 0 |  | MORETLO (R500K)+SAFETY(PROJECTOR(R10K)CAMERA((R10K)WASHING MACH(R6K)FOLDABLE TAB X 5(R5K)
304506 | Corporate Services | PRINTING | I/304506.001 | 2.5 - Supply Chain Management |  |  | 400000 | PRINTING FLOORS
304507 | Corporate Services | SECRETARIAT | A/304507.BAH.A53 | 2.5 - Supply Chain Management |  |  | 40000 | DIGITAL RECORDERS | TBC
304526 | Corporate Services | ICT - PROJECTS | A/304526.BAH.A52 | 2.5 - Supply Chain Management | 17000000 | 12508225.12 | 8325000 | MKONDENI REFRESH EQUIPMENT/SERVERS/STORAGE | TBC
304526 | Corporate Services | ICT - PROJECTS | A/304526.BAH.A60 | 2.5 - Supply Chain Management | 3000000 | 240000 | 1500000 | WIFI ACCESS POINTS
304526 | Corporate Services | ICT - PROJECTS | I/304526.003 | 2.5 - Supply Chain Management |  |  | 4625000 | NETWORK REFESH
402284 | Community Services | GM - COMMUNITY_SERV | A/402284.BAH.A60 | 2.5 - Supply Chain Management |  |  | 65000 | for GM
402284 | Community Services | GM - COMMUNITY_SERV | A/402284.BZA.A52 | 2.5 - Supply Chain Management |  |  | 25000 | for GM
402284 | Community Services | GM - COMMUNITY_SERV | A/402284.BZA.A60 | 2.5 - Supply Chain Management |  |  | 10000 | SHREDDER
403243 | Community Services | COMMUNITY HALLS | I/403243.007 | 3.1 - Area Based Management | 1000000 | -68121.65
403243 | Community Services | COMMUNITY HALLS | I/403243.008 | 3.1 - Area Based Management | 3000000 | 1785284.18
403243 | Community Services | COMMUNITY HALLS | I/403243.009 | 3.1 - Area Based Management | 3000000 | 2288120.92
403243 | Community Services | COMMUNITY HALLS | I/403243.010 | 3.1 - Area Based Management | 1113250 |  | 4201115
403243 | Community Services | COMMUNITY HALLS | I/403243.011 | 3.1 - Area Based Management | 3000000 | 2060702.88 | 3708125.08
403243 | Community Services | COMMUNITY HALLS | I/403243.027 | 3.1 - Area Based Management |  |  | 2914387
403243 | Community Services | COMMUNITY HALLS | I/403243.012 | 3.1 - Area Based Management | 3000000 | 2273957.17
403243 | Community Services | COMMUNITY HALLS | I/403243.018 | 3.1 - Area Based Management |  |  | 81493
403243 | Community Services | COMMUNITY HALLS | I/403243.013 | 3.1 - Area Based Management | 1013250 | 37962.31 | 3000000 |  | MEC APPROVED PROJECT FUNDED BY MHOA RESERVE
403553 | Community Services | AREA BASED - MNGT | A/403553.BZA.A52 | 3.1 - Area Based Management |  | 25704 | 100000 | Laptops for newly appointed employees | MEC APPROVED PROJECT FUNDED BY MHOA RESERVE
403553 | Community Services | AREA BASED - MNGT | A/403553.BAH.A53 | 3.1 - Area Based Management |  |  | 100000 | Brushcutters for x5 areas | FUNDED BY DOHS SUBJECT TO ROLLOVER APPROVAL
403553 | Community Services | AREA BASED - MNGT | A/403553.BZA.A61 | 3.1 - Area Based Management |  |  | 400000 | Vehicle for ABM | FUNDED BY DOHS
404183 | Community Services | CONTAINER SERVICE | A/404183.BZA.A60 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | 10 x Bulk refuse collection containers (20 m3) | FUNDED BY DOHS SUBJECT TO ROLLOVER APPROVAL
404183 | Community Services | CONTAINER SERVICE | A/404183.BZA.A60 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | 20 X Wheeelie bins | FUNDED BY DOHS
404183 | Community Services | CONTAINER SERVICE | A/404183.BZA.A60 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | 50 x 1,7 Bulk refuse collection containers | FUNDED BY DOHS SUBJECT TO ROLLOVER APPROVAL
404185 | Community Services | LANDFILL SITE | A/404185.BZA.A60 | 3.2 - Public Safety, Emergency Services and Enforcement |  | 88678.8 |  |  | DELETED DUPLICATED
404185 | Community Services | LANDFILL SITE | I/404185.004 | 3.2 - Public Safety, Emergency Services and Enforcement | 2000000 | 123921.39 | 10000000 | Compliance | DELETED DUPLICATED
404185 | Community Services | LANDFILL SITE | A/404185.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Water tanker | DELETED DUPLICATED
404185 | Community Services | LANDFILL SITE | A/404185.BZA.A52 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Laptop | DELETED DUPLICATED
404185 | Community Services | LANDFILL SITE | A/404185.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Bakkie landfill | DELETED DUPLICATED
404186 | Community Services | GENERAL - WASTE MNGT | A/404186.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | 5 bakkies / vans | DELETED DUPLICATED
404186 | Community Services | GENERAL - WASTE MNGT | A/404186.BZA.A52 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 60000 | 2 x laptops | DELETED DUPLICATED
404243 | Community Services | COUNCIL HOUSE | A/404243.BAH.A53 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 300000 | Furniture for all halls for 5 zones | DELETED DUPLICATED
404243 | Community Services | COUNCIL HOUSE | A/404243.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 600000 | Truck for movement of chairs in the halls | DELETED DUPLICATED
404292 | Community Services | PLANT & VEHICLES | A/404292.BAH.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Major Pumper | DELETED DUPLICATED
404292 | Community Services | PLANT & VEHICLES | A/404292.BAH.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Major Pumper
404292 | Community Services | PLANT & VEHICLES | A/404292.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Airport Crash Fire Rescue Tender
404292 | Community Services | PLANT & VEHICLES | A/404292.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Special Appliances: Water Foam Carrier/ Tanker
404292 | Community Services | PLANT & VEHICLES | A/404292.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 800000 | Bakkie Sakkie/ Bush Fire Fighting
404292 | Community Services | PLANT & VEHICLES | A/404292.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  |  | 4*4 Bakkies ( Grass Fire Bakkie)
404292 | Community Services | PLANT & VEHICLES | A/404292.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  |  | Grass and Bush Fire Engine
404292 | Community Services | PLANT & VEHICLES | A/404292.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  |  | Hazardous Chemical Response Unit/ Trailer
404292 | Community Services | PLANT & VEHICLES | A/404292.BZA.A61 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 0 | Breathing Appartus Response Unit
404294 | Community Services | MNT & ADMIN - FIRE | A/404292.BZA.A52 | 3.2 - Public Safety, Emergency Services and Enforcement |  |  | 150000 | Upgrade Computer Equipment
404302 | Community Services | OPERATIONS | A/404302.BZA.A60 | 3.3 - Recreation and Facilities |  |  | 550000 | Jaws of Life
404302 | Community Services | OPERATIONS | A/404302.BZA.A60 | 3.3 - Recreation and Facilities |  |  | 600000 | Fire Fighting Equipment
404325 | Community Services | ADMIN - TRAFFIC | A/404325.BZA.A60 | 3.3 - Recreation and Facilities |  |  | 60000 | Franky Machine:The printing of notices before summons and summons
404327 | Community Services | TRFC CONT/LAW ENFCT | A/404327.BAH.A61 | 3.3 - Recreation and Facilities | 3000000 |  | 1000000 | The incoming back batch of traffic wardens from traffic college
404327 | Community Services | TRFC CONT/LAW ENFCT | A/404327.BAH.A60 | 3.3 - Recreation and Facilities |  |  | 500000 | New furniture for the new staff- traffic wardens mentioned above
404327 | Community Services | TRFC CONT/LAW ENFCT | A/404327.BZA.A60 | 3.3 - Recreation and Facilities |  | 443394 | 600000 | ANPR Automatic Recognition licence plate system and computers
404328 | Community Services | SECURITY | A/404328.BAH.A61 | 3.3 - Recreation and Facilities |  |  | 0 | The establishment of the new approved single law enforcement
404390 | Community Services | MNT & ADMN - SPRTS | A/404390.BZA.A60 | 3.3 - Recreation and Facilities |  |  | 500000 | Blowers
404390 | Community Services | MNT & ADMN - SPRTS | A/404390.BZA.A61 | 3.3 - Recreation and Facilities |  |  | 1000000 | Tractors
404390 | Community Services | MNT & ADMN - SPRTS | A/404390.BZA.A60 | 3.3 - Recreation and Facilities |  |  | 500000 | Brush Cuttors
404390 | Community Services | MNT & ADMN - SPRTS | A/404390.BZA.A61 | 3.3 - Recreation and Facilities |  |  | 1000000 | Bakkies
404390 | Community Services | MNT & ADMN - SPRTS | A/404390.BZA.A52 | 3.3 - Recreation and Facilities |  |  | 80000 | Computers
404392 | Community Services | CEMETERIES | I/404392.010 | 3.3 - Recreation and Facilities | 700000 |  | 8375031.12
404402 | Community Services | DISTRICT NORTH | A/404402.BAH.A61 | 3.3 - Recreation and Facilities |  |  | 1000000 | LVD cars : District North
404478 | Community Services | VULINDLEL SPRT FCLTY | I/404478.001 | 4.5 - General Manager: Corporate Service | 8000000 |  | 6952560
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.5AH.A52 | 4.5 - General Manager: Corporate Service | 400000
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.5AH.A53 | 4.5 - General Manager: Corporate Service | 500000
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.B5H.A52 | 4.5 - General Manager: Corporate Service
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.B5H.A53 | 4.5 - General Manager: Corporate Service
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.5AH.A52 | 4.5 - General Manager: Corporate Service | 300000 | 300000 | 350000
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.5AH.A53 | 4.5 - General Manager: Corporate Service | 500000 | 500000 | 550000
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.B5H.A52 | 4.5 - General Manager: Corporate Service
404513 | Community Services | BESSIE HEAD LIBRY | A/404513.B5H.A53 | 4.5 - General Manager: Corporate Service | 600000 | 600000 | 800000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | A/504125.BZA.A61 | 5.1 - Electricity | 5000000 |  | 4000000 | Puchasing of 1 TLB and 2 tipper trucks
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.006 | 5.1 - Electricity | 20000000 | 28009276.02 | 19150000 | Rehabilitation of roads to extend their life span and reduce pothole backlog
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.070 | 5.1 - Electricity |  |  | 10000000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.014 | 5.1 - Electricity | 6000000 | 867435.76 | 7300000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.029 | 5.1 - Electricity | 7000000 | 3324905.46 | 3000000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.031 | 5.1 - Electricity | 7700000 | 6262371.24
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.032 | 5.1 - Electricity | 500000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.033 | 5.1 - Electricity | 8200000 | 6146663.18
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.037 | 5.1 - Electricity | 500000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.042 | 5.1 - Electricity | 1500000 |  | 7378170.25
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.043 | 5.1 - Electricity | 1000000 |  | 7000000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.055 | 5.1 - Electricity | 6000000 | 4111730 | 7000000
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.071 | 5.1 - Electricity |  |  | 5402149
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.067 | 5.1 - Electricity | 750000 | 2011259.53
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.072 | 5.1 - Electricity |  |  | 500000 | Upgrading of stormwater system - to increase pipe sizes and culverts.
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.073 | 5.1 - Electricity |  |  | 800000 | Upgrading/rehab of gravel roads to adress stormwater issues in steep roads
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.074 | 5.1 - Electricity |  |  | 800000 | generators, trailers, cutting saw, jack hammers, pedestrian rollers for pothole patching
504125 | Infrastructure Services | ROADS SURFACE REPAIR | I/504125.064 | 5.1 - Electricity |  |  | 600000
504126 | Infrastructure Services | CANLISD RIVER & STRM | I/504126.007 | 5.3 - Roads and Transportation | 2000000 | 135074.76 | 2000000 | Bank protection for properties along Bynspruit river in Northdale and Dambuza Dongas
504126 | Infrastructure Services | CANLISD RIVER & STRM | I/504126.020 | 5.3 - Roads and Transportation |  |  | 3214000
504131 | Infrastructure Services | TRANSPORTATION | I/504131.006 | 5.4 - Water and Sanitation | 250000 | 179295.68 | 250000 | Construction of 15 speed humps and speed tables for road safety
504131 | Infrastructure Services | TRANSPORTATION | I/504131.006 | 5.4 - Water and Sanitation
504131 | Infrastructure Services | TRANSPORTATION | A/504125.BZA.A60 | 5.4 - Water and Sanitation |  |  | 600000 | Purchasing of new road marking machines
504131 | Infrastructure Services | TRANSPORTATION | I/504131.015 | 5.4 - Water and Sanitation |  |  | 500000 | Purchasing of software for inhouse intersections analysis
504131 | Infrastructure Services | TRANSPORTATION | I/504131.003 | 5.4 - Water and Sanitation |  |  | 2000000 | Upgrading of traffic signals system to change the old TYCO system as spares have become absolute
504137 | Infrastructure Services | GRDRAIL SFETY BARIER | I/504137.001 | 5.4 - Water and Sanitation |  |  | 800000 | Installation of new guardails and handrails for road safety
504143 | Infrastructure Services | IRPTN | I/504143.001 | 5.4 - Water and Sanitation |  |  | 20000000
504143 | Infrastructure Services | IRPTN | I/504143.005 | 5.4 - Water and Sanitation | 2000000 |  | 12370143.91
504202 | Infrastructure Services | SEWER RETCULTN MAINT | I/504202.009 | 5.4 - Water and Sanitation | 22000000 | 953173 | 14142668
504202 | Infrastructure Services | SEWER RETCULTN MAINT | I/504202.013 | 5.4 - Water and Sanitation |  |  | 15707790
504202 | Infrastructure Services | SEWER RETCULTN MAINT | I/504202.014 | 5.4 - Water and Sanitation |  |  | 4680000
504202 | Infrastructure Services | SEWER RETCULTN MAINT | I/504202.015 | 5.4 - Water and Sanitation | 1500000
504202 | Infrastructure Services | SEWER RETCULTN MAINT | I/504202.016 | 5.4 - Water and Sanitation | 15300000 | 4968874.31
504202 | Infrastructure Services | SEWER RETCULTN MAINT | I/504202.025 | 5.4 - Water and Sanitation | 65477640 | 5371135.31 | 62516176.7
504527 | Infrastructure Services | MNGT SERVICES | A/504527.HZ4.A52 | 5.4 - Water and Sanitation | 150000 |  | 100000
504527 | Infrastructure Services | MNGT SERVICES | TO BE CREATED | 5.4 - Water and Sanitation |  |  | 100000
504787 | Infrastructure Services | DISTRIBUTION | A/504787.BZA.A61 | 5.4 - Water and Sanitation | 15000000 |  | 5000000
504787 | Infrastructure Services | DISTRIBUTION | I/504787.008 | 5.4 - Water and Sanitation | 11064500 | 6996990.3 | 3000000
504787 | Infrastructure Services | DISTRIBUTION | I/504787.026 | 5.4 - Water and Sanitation | 22500000 | 1784983.93 | 18805000
504787 | Infrastructure Services | DISTRIBUTION | TO BE CREATED | 5.4 - Water and Sanitation
504787 | Infrastructure Services | DISTRIBUTION | TO BE CREATED | 5.4 - Water and Sanitation
504787 | Infrastructure Services | DISTRIBUTION | TO BE CREATED | 5.4 - Water and Sanitation |  |  | 23250000
504787 | Infrastructure Services | DISTRIBUTION | I/504787.030 | 5.4 - Water and Sanitation | 22860000 | 225984.73 | 5320000
504787 | Infrastructure Services | DISTRIBUTION | I/504787.036 | 5.4 - Water and Sanitation | 28055100 | 624845.1 | 12000000
504787 | Infrastructure Services | DISTRIBUTION | TO BE CREATED | 5.4 - Water and Sanitation |  |  | 20000000
504787 | Infrastructure Services | DISTRIBUTION | TO BE CREATED | 5.4 - Water and Sanitation |  |  | 8000000
504787 | Infrastructure Services | DISTRIBUTION | I/504787.040 | 5.4 - Water and Sanitation
504787 | Infrastructure Services | DISTRIBUTION | I/504787.040 | 5.4 - Water and Sanitation | 7000000 | 154742.13 | 5000000
504787 | Infrastructure Services | DISTRIBUTION | TO BE CREATED | 5.4 - Water and Sanitation
504787 | Infrastructure Services | DISTRIBUTION | I/504787.041 | 5.4 - Water and Sanitation | 8000000 | 5153872.48
504787 | Infrastructure Services | DISTRIBUTION | I/504787.042 | 5.4 - Water and Sanitation
602097 | Sustainable Development | GM - SUSTNBL DEV & C | A/602097.BZ4.A52 | 5.5 - General Manager: Infrastructure |  |  | 50000 | COUNCIL
602097 | Sustainable Development | GM - SUSTNBL DEV & C | A/602097.BAH.A53 | 5.5 - General Manager: Infrastructure |  |  | 50000 | COUNCIL
602097 | Sustainable Development | GM - SUSTNBL DEV & C | A/602097.BZ4.A52 | 5.5 - General Manager: Infrastructure |  |  | 0
602097 | Sustainable Development | GM - SUSTNBL DEV & C | A/602097.BAH.A53 | 5.5 - General Manager: Infrastructure |  |  | 0
603098 | Sustainable Development | DEVELOP SERVICES-MNG | A/603098.BAH.A52 | 5.5 - General Manager: Infrastructure |  |  | 210000 | COUNCIL
603098 | Sustainable Development | DEVELOP SERVICES-MNG | A/603098.BAH.A53 | 5.5 - General Manager: Infrastructure |  |  | 50000 | COUNCIL
603098 | Sustainable Development | DEVELOP SERVICES-MNG | A/603098.BAH.A60 | 5.5 - General Manager: Infrastructure |  |  | 90000 | COUNCIL
603098 | Sustainable Development | DEVELOP SERVICES-MNG | A/603098.BAH.A52 | 5.5 - General Manager: Infrastructure |  |  | 0
603098 | Sustainable Development | DEVELOP SERVICES-MNG | A/603098.BAH.A53 | 5.5 - General Manager: Infrastructure |  |  | 0
603098 | Sustainable Development | DEVELOP SERVICES-MNG | A/603098.BAH.A60 | 5.5 - General Manager: Infrastructure |  |  | 0
603114 | Sustainable Development | MUNICIPAL BUS ENT | A/603114.BAH.A52 | 6.1 - City Entities |  |  | 250000 | COUNCIL
603114 | Sustainable Development | MUNICIPAL BUS ENT | A/603114.BAH.A60 | 6.1 - City Entities |  |  | 100000 | COUNCIL
603114 | Sustainable Development | MUNICIPAL BUS ENT | A/603114.BAH.A52 | 6.1 - City Entities |  |  | 0
603114 | Sustainable Development | MUNICIPAL BUS ENT | A/603114.BAH.A60 | 6.1 - City Entities |  |  | 0
603116 | Sustainable Development | TOWN PLAN & ENV-MNGT | A/603116.BAH.A52 | 6.1 - City Entities |  |  | 350000 | COUNCIL
603116 | Sustainable Development | TOWN PLAN & ENV-MNGT | A/603116.BAH.A52 | 6.1 - City Entities |  |  | 350000
604241 | Sustainable Development | BEE | I/604241.021 | 6.3 - Human Settlement Development |  |  | 20000000 | NDPG
604241 | Sustainable Development | BEE | I/604241.007 | 6.3 - Human Settlement Development |  |  |  | NDPG
604241 | Sustainable Development | BEE | I/604241.008 | 6.3 - Human Settlement Development |  |  |  | NDPG
604241 | Sustainable Development | BEE | I/604241.009 | 6.3 - Human Settlement Development |  |  |  | NDPG
604241 | Sustainable Development | BEE | I/604241.010 | 6.3 - Human Settlement Development |  |  |  | NDPG
604241 | Sustainable Development | BEE | I/604241.006 | 6.3 - Human Settlement Development |  |  | 1000000 | EDTEA GRANT EMATSHENI
604241 | Sustainable Development | BEE | I/604241.024 | 6.3 - Human Settlement Development |  |  | 1000000 | COUNCIL TOP UP EMATSHENI
604241 | Sustainable Development | BEE | I/604241.024 | 6.3 - Human Settlement Development |  |  | 0
604270 | Sustainable Development | HOUSNG ACCREDITATION | A/604270.A9A.A60 | 6.3 - Human Settlement Development |  |  | 300000
604270 | Sustainable Development | HOUSNG ACCREDITATION | A/604270.A9H.A52 | 6.3 - Human Settlement Development |  |  | 200000
604270 | Sustainable Development | HOUSNG ACCREDITATION | A/604270.A9H.A53 | 6.3 - Human Settlement Development |  |  | 200000
604480 | Sustainable Development | ART GALLERY | A/604480.5Z4.A52 | 6.3 - Human Settlement Development |  |  | 80000 | DSAC GRANT
604480 | Sustainable Development | ART GALLERY | A/604480.5Z4.A60 | 6.3 - Human Settlement Development |  |  |  | DSAC GRANT
604480 | Sustainable Development | ART GALLERY | I/604480.008 | 6.3 - Human Settlement Development |  |  | 60000 | DSAC GRANT
604480 | Sustainable Development | ART GALLERY | I/604480.009 | 6.3 - Human Settlement Development |  |  | 25000 | DSAC GRANT
604560 | Sustainable Development | NEW HOUSING PROJECTS | A/604560.BAH.A53 | 6.3 - Human Settlement Development |  |  | 350000 | COUNCIL
604560 | Sustainable Development | NEW HOUSING PROJECTS | I/604560.024 | 6.3 - Human Settlement Development |  |  | 57800000
604560 | Sustainable Development | NEW HOUSING PROJECTS | I/604560.021 | 6.3 - Human Settlement Development
604560 | Sustainable Development | NEW HOUSING PROJECTS | I/604560.022 | 6.3 - Human Settlement Development |  |  | 13282976
604560 | Sustainable Development | NEW HOUSING PROJECTS | I/604560.006 | 6.3 - Human Settlement Development
604560 | Sustainable Development | NEW HOUSING PROJECTS | I/604560.026 | 6.3 - Human Settlement Development |  |  | 45973206.06
604560 | Sustainable Development | NEW HOUSING PROJECTS | A/604560.BAH.A53 | 6.3 - Human Settlement Development |  |  | 0
604560 | Sustainable Development | NEW HOUSING PROJECTS | TO BE CREATED | 6.3 - Human Settlement Development | 4000000 | 2617860.53 | 930559.01
604564 | Sustainable Development | HOUSING : GENERAL | I/604564.004 | 6.3 - Human Settlement Development |  |  | 6718472.58
604564 | Sustainable Development | HOUSING : GENERAL | I/604564.005 | 6.3 - Human Settlement Development |  |  | 3818316
604745 | Sustainable Development | MUNICIPAL MARKET | I/604745.005 | 3.3 - Recreation and Facilities |  |  | 2500000 | MARKET ROOF REPLACEMENT
604745 | Sustainable Development | MUNICIPAL MARKET | I/604745.005 | 3.3 - Recreation and Facilities |  |  | 0
704062 | Electricity | EL_PNL_AND_ASSET_CR | A/704062.1AH.A52 | 7.5 General Manager Electricity | 300000
704062 | Electricity | EL_PNL_AND_ASSET_CR | A/704062.1AH.A53 | 7.5 General Manager Electricity | 450000
704062 | Electricity | EL_PNL_AND_ASSET_CR | A/704062.1AH.A60 | 7.5 General Manager Electricity | 25000000
704062 | Electricity | EL_PNL_AND_ASSET_CR | A/704062.1AH.A61 | 7.5 General Manager Electricity | 2850000 |  | 4000000
704062 | Electricity | EL_PNL_AND_ASSET_CR | A/704062.1ZA.A60 | 7.5 General Manager Electricity | 5900000 |  | 9500000
704062 | Electricity | EL_PNL_AND_ASSET_CR | A/704062.1ZA.A60 | 7.5 General Manager Electricity | 17000000 |  | 27700000
704062 | Electricity | EL_PNL_AND_ASSET_CR | A/704062.1ZA.A60 | 7.5 General Manager Electricity | 2500000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.006 | 7.5 General Manager Electricity | 9000000 | 7088650.8 | 7816695.71
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.007 | 7.5 General Manager Electricity | 18000000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.008 | 7.5 General Manager Electricity | 48000000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.009 | 7.5 General Manager Electricity | 5000000 |  | 34300000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.014 | 7.5 General Manager Electricity | 40500000 |  | 40000000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.019 | 7.5 General Manager Electricity | 34500000 |  | 109915856
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.020 | 7.5 General Manager Electricity | 4200000 | 3050040.21
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.023 | 7.5 General Manager Electricity | 1400000 | 588215.56
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.023 | 7.5 General Manager Electricity
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.024 | 7.5 General Manager Electricity | 1400000 | 502444.39
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.024 | 7.5 General Manager Electricity |  |  | 3271000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.025 | 7.5 General Manager Electricity |  |  | 1700000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.025 | 7.5 General Manager Electricity | 5000000 | 1966178.33 | 4950000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.016 | 7.5 General Manager Electricity |  |  | 2000000
704062 | Electricity | EL_PNL_AND_ASSET_CR | I/704062.017 | 7.5 General Manager Electricity |  |  | 1000000
704062 | Electricity | EL_PNL_AND_ASSET_CR | TO BE CREATED | 7.5 General Manager Electricity |  |  | 5900000
704066 | Electricity | METERING AND TARIFFS | I/704066.001 | 7.4 Revenue Magement | 8000000 | 1880280.63 | 8000000
[5 empty] | 606433740 | 118243110.59 | 824010890.42

## ANNEX A
ANNEXURE A: MONTHLY PROJECTION OF REVENUE BY EACH SOURCE
DESCRIPTION | BUDGET YEAR 2025/2026
R THOUSAND | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | BUDGET YEAR 2025/ 2026 - TOTAL
Service charges - Electricity | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 391879607.7 | 4702555292.4006
Service charges - Water | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 96768674.5221 | 1161224094.2655
Service charges - Waste Water Management | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 20876893.0471 | 250522716.5653
Service charges - Waste Management | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 14644536.835 | 175734442.0196
Sale of Goods and Rendering of Services | [12 empty] | 0
Agency services | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 458965.254 | 5507583.048
Interest earned from Receivables | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 26847578.5257 | 322170942.3087
Interest earned from Current and Non Current Assets | [12 empty] | 0
Rental from Fixed Assets | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 3713844.5751 | 44566134.9012
Licence and permits | [12 empty] | 0
Operational Revenue | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 10739694.6102 | 128876335.3229
Non-Exchange Revenue | [12 empty] | 0
Property rates | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 143472058.9173 | 1721664707.0081
Fines, penalties and forfeits | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 1017761.8016 | 12213141.6187
Licences or permits | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 258054.6573 | 3096655.8876
Transfer and subsidies - Operational | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 82467349.5833 | 989608195
Interest | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 1666352.3672 | 19996228.406
Total Revenue (excluding capital transfers and contributions) | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 794811372.396 | 9537736468.7522

## ANNEX B
ANNEXURE B: MONTHLY PROJECTION OF REVENUE COLLECTED BY EACH VOTE
DESCRIPTION | BUDGET YEAR 2025/2026
R THOUSAND | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | BUDGET YEAR 2025/ 2026 - TOTAL
Revenue by Vote
City Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City Finance | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 232420816.3411 | 2789049796.0932
Corporate Services | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 158852.421 | 1906229.052
Community Services and Social Equity | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 22111962.4078 | 265343548.8936
Infrastructure Services | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 167252934.0725 | 2007035208.8694
Sustainable Development and City Enterprises | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 8101455.511 | 97217466.1318
Electricity | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 396942311.6427 | 4763307739.7122
Total Revenue | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 826988332.396 | 9923859988.7522

## ANNEX D
ANNEXURE D: MONTHLY PROJECTION OF CAPITAL EXPENDITURE BY VOTE
DESCRIPTION | BUDGET YEAR 2024/2025
R THOUSAND | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | BUDGET YEAR 2025/ 2026 - TOTAL
Multi-year expenditure to be appropriated
City Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City Finance | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 45000000
Corporate Services | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 10000000
Community Services and Social Equity | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 3718060 | 44616720
Infrastructure Services | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 28891786.6667 | 346701440
Sustainable Development and City Enterprises | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electricity | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 15111063.4133 | 181332760.96
Total Capital Expenditure | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 52304243.4133 | 627650920.96

## INFRASTRUCTURE SERVICES
CDS REFERENCE | SDBIP REFERENCE | NATIONAL KEY PERFORMANCE AREA | B2B PILLAR | GOAL | STRATEGIC OBJECTIVE | STRATEGY | WARD | INDICATOR | ANNUAL TARGET | UNIT OF MEASURE | ANNUAL BUDGET | FUNDING SOURCE | WBS/GL NUMBER | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | PORTFOLIO OF EVIDENCE | RESPONSIBLE DEPARTMENT
2- BACK TO BASICS | IFS 01 | NKPA 2 - BASIC SERVICE DELIVERY | DELIVERING BASIC SERVICES | Goal 2: Developed and Maintained Infrastructure | 2.2 Ensure availability and sustainable management of water and sanitation for all | 2.2.1 Develop, upgrade and maintain the water and sanitation network | 1 to 41 | Percentage of water meters installed | 90% of water meters installed by the 30th of June 2025 | Percentage | N/A | N/A | N/A | 90% | 90% | 90% | 90% | Monthly water connection spreadsheet, application forms and register | Water & Sanitation
| IFS 02 | [5 empty] | 1 to 41 | Percentage of new sewer connections completed | 100% of new sewer connections completed by the 30th of June 2025 | Percentage | N/A | N/A | N/A | 100% | 100% | 100% | 100% | Monthly sewer connection spreadsheet, application forms register | Water & Sanitation
| IFS 03 | [5 empty] | 1 to 41 | Number of VIP Toilets installed. | 2925 VIP toilets installed by 30th June 2025. | Number | N/A | WSIG | P/504202.007 | N/A | N/A | 2250 | 2925 | Invoices and Happy Letters, register | Water & Sanitation
| IFS 07 | [5 empty] | 4, 5, 28, 30, 39 | Number of km water pipes installed | 16 km of water pipes installed by the 30th of June 2025 | Number | 12250470.89 | MIG/WSIG/CNL | I/504787.026, I/504787.030, I/504787.045, I/504787.036, | N/A | N/A | 14.5 | 16 | Monthly progress reports, register | Water & Sanitation
| IFS 04 | [5 empty] | 30 | Number of Reservoirs Constructed | 1 x 750kl Reservoirs constructed by the 30th of June 2025 | Number | 5000000 | MIG | I/504787.026 | N/A | N/A | N/A | 1 | Monthly progress reports | Water & Sanitation
| IFS 05 | [5 empty] | 21 & 35 | Number km of sewer pipelines installed | 2.33km x of new sewer pipeline installed by the 30th of June 2025 | Number | 9191626.91 | MIG | I/504202.009 | N/A | N/A | 1.99 | 2.33 | Monthly progress reports and register | Water & Sanitation
| IFS 06 | [5 empty] | 29, 39, 4 & 5 | Percentage of mainline bursts repaired | 60% of mainline bursts repaired by the 30th of June 2025. | Percentage | N/A | N/A | N/A | 80% | 80% | 60% | 60% | Heat extract report, job card and register | Water & Sanitation
| IFS 08 |  |  |  | 2.3 Developed and Maintained Municipal road Networks |  | 25 | Percentage of sewer blockages resolved | 60% of sewer blockages resolved by the 30th of June 2025. | Percentage | N/A | N/A | N/A | 60% | 60% | 60% | 60% | Heat report extract, job card and register | Water & Sanitation
| IFS 09 | [5 empty] | N/A | Water Losses reduced to below 30% | Water Losses reduced to below 30% by the 30th of June 2025. | Percentage | N/A | N/A | N/A | below 30% | below 30% | below 30% | below 30% | IWA Water Balance | Water & Sanitation
| IFS 10 |  |  |  |  | 2.3.1 Developed and maintained municipal road networks | 14,13,2,21,33,23,41 &32 | Number of traffic calming measures installed | 16x traffic calming measure installed by the 30th of June 2025 | Number | 238000 | CNL | I/504131.006 | N/A | N/A | N/A | 16 | Completion Certificates and register | Roads & Transportation
| IFS 11 | [5 empty] | 4, 7, 8, 14, 21 | Number of KM of gravel roads upgraded | 3,5km x of gravel roads upgraded by 30th June 2025 (practically completed). | Number | 41278567 | MIG | I/504125.029 I/504125.014 I/504125.043 I/502125.071 I/504125.042 I/504125.055 | N/A | N/A | N/A | 3.5 | Practical Completion Certificates and register | Roads & Transportation
3 - IMPROVING INFRASTRUCTURE EFFICIENCY | IFS 12 | [5 empty] | Various wards | Number of meters of road marking lines completed | 51000x Meters of road marking lines completed by the 30th of June 2025. | Number | N/A | N/A | N/A | N/A | N/A | 45000 | 51000 | Job cards and register | Roads & Transportation
| IFS 13 | [5 empty] | Various wards | Number of stormwater catchpits maintained | 1096 stormwater catchpits maintained by the 30th of June 2025 | Number | N/A | N/A | N/A | N/A | N/A | 796 | 1096 | Job cards and register | Roads & Transportation
| IFS 14 | [5 empty] | 27 | Number of Square meters of pedestrian walkways maintained | 2000 square meters of pedestrian walkways maintained by the 30th of June 2025 | Number | 2000000 | CNL | M/504125. JAH.D33 M/504126.JAH.D34 | N/A | N/A | 1250 | 2000 | Progress Report or Completion Certificates and register | Roads & Transportation
2 - BACK TO BASICS | IFS 16 | [5 empty] | Various wards | Number of km of gravel roads maintained | 30 km of gravel roads maintained by the 30th June 2025 | Number | N/A | N/A | N/A | N/A | N/A | 20 | 30 | Progress Report , job cards and register | Roads & Transportation
| IFS 17 | [5 empty] | 21-28, 30-37 | Number of major traffic signals repaired | 12 major traffic signal repaired by the 30th of June 2025 | Number | 1500000 | CNL | 0/504131.JAH.000 | N/A | N/A | 8 | 12 | Job Cards or Completion Certificates and register
| IFS 18 |  |  |  | 2.4 Social infrastructure | 2.4.3 100% of social infrastructure delivery complies with national standards regarding minimal environmental impact | 8,34,24 | Number of community halls constructed | 3 community halls constructed by the 30th of June 2025 | Number | 13823627.08 | MIG | I/403243.013 I/403243.027 I/403243.010 | N/A | N/A | N/A | 3 | Progress Reports and Practical Completion Certificates | Project Management Office
| IFS 18 | [5 empty] | 2 | Number of sport complexes constructed | 1 sport complex constructed by the 30th of June 2025 | Number | 3133000 | MIG | I/404478.001 | N/A | N/A | N/A | 1 | Progress Reports and Practical Completion Certificates | Project Management Office
4 - BUILDING FINANCIAL SUSTAINABILITY | IFS 19 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | SOUND FINANCIAL MANAGEMENT | Goal 4 - Financial Viability | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Capital Expenditure spent for the Infrastructure Services BU | 100% of Capital Budget spent 30th June 2025 | Percentage | 375326746.94 | N/A | N/A | 100% | 100% | 75% | 100% | Financial Report | IFS - BTO
| IFS 20 | [5 empty] | N/A | Percentage of Operational Budget spent | 100% of Operational Budget spent by the 30th of June 2025 | Percentage | 1730321999.7 | N/A | N/A | 100% | 100% | 75% | 100% | Financial Report | IFS - BTO
14 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | IFS 21 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS | Goal 1: Governance and policy | 1.4 Human Resources Management and Development | 1.4.1 Improve human resource management | N/A | Percentage of Posts Filled | 100% of Posts Filled in Infrastructure Services business unit by the 30th of June 2025 | Percentage | N/A | N/A | N/A | N/A | N/A | N/A | 100% | Staff Vacancy Advice forms (SVA) & Appointment Letters | IFS- Human Resource Support
2 - BACK TO BASICS | IFS 22 | NKPA 2 - BASIC SERVICE DELIVERY | DELIVERING BASIC SERVICES | Goal 2: Developed and Maintained Infrastructure | 2.3 Developed and Maintained Municipal road Networks | 2.3.1 Developed and maintained municipal road networks | Various wards | Number of road symbol markings completed | 5500 of road symbol markings completed by the 30th of June 2025 | Number | N/A | N/A | N/A | N/A | N/A | 3962 | 5500 | Job cards and register | Roads & Transportation
| IFS 23 | [5 empty] | Various wards | Number of square meters of potholes repaired | 35000 square meters of potholes repaired by the 30th of June 2025 | Number | 30500000 | CNL | M/504125. JAH.D33 M/504126.JAH.D34 M/504124/JAH.D33 M/504126.JAH.D33 | N/A | N/A | N/A | 35000 | Job cards and register | Roads & Transportation
| IFS 24 | [5 empty] | 27 | Number of square meters of roads rehabilitated | 48970 square meters of roads rehabilitated by the 30th of June 2025 | Number | 23500000 | CNL | M/504125. JAH.D33 M/504126.JAH.D34 M/504124/JAH.D33 M/504126.JAH.D33 | N/A | N/A | N/A | 48970 | Practical completion certificate and register | Roads & Transportation
Note on J17: Nondumiso B. Buthelezi: (edge lines, centre lines, parking bays)
Note on J24: Nondumiso B. Buthelezi: (Capital Expenditure spent vs original budget)
Note on J25: Nondumiso B. Buthelezi: (Operational Expenditure spent vs Original budget)

## COMMUNITY SERVICES TOP LAYER
CDS REFERENCE | SDBIP REFERENCE | NATIONAL KEY PERFORMANCE AREA | B2B PILLAR | GOAL | STRATEGIC OBJECTIVE | STRATEGY | WARD | INDICATOR | ANNUAL TARGET | UNIT OF MEASURE | ANNUAL BUDGET | FUNDING SOURCE | WBS/GL NUMBER | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | PORTFOLIO OF EVIDENCE | RESPONSIBLE DEPARTMENT
2 - BACK TO BASICS | CSE 01 | NKPA 2-BASIC SERVICE DELIVERY | DELIVERING BASIC SERVICES | Goal 3: Human and Community Development | 3.1 Enhanced waste management capacity | 3.1.1 Improve the basics: cleaning, repairing, enforcing waste management practices | All | Number households receiving refuse removal service | 59182 x households receiving refuse removal service by 30th June 2025 | Number | N/A | N/A | N/A | N/A | N/A | 59182 | 59182 | Customer statements, waste collection schedules and register | Waste Management
| CSE 02 | [5 empty] | 27 | Number of CBD Clean up Campaigns conducted | 12 x CBD Clean up Campaigns conducted by the 30th of June 2025 | Number | N/A | N/A | N/A | 2 | 4 | 8 | 12 | Progress reports and registers | Waste Management
| CSE 03 |  |  |  | 3.3 Enhance the Enforcement of By-laws, Public Safety and Security. | 3.3.1 improve Enforcement of By-laws, Public Safety and Security. | N/A | Number of compliance notices issued | 98 x compliance notices issued by the 30th of June 2025 | Number | N/A | N/A | N/A | N/A | N/A | N/A | 98 | Copies of compliance notice and register | Waste Management
| CSE 04 |  |  |  | 3.2 Enhance public facilities, parks and public spaces within the city | 3.2.1 Improve the basics: cleaning, repairing public spaces | TBC | Number of swimming pools maintenance | 1x swimming pools maintained by the 30th of June 2025 | Number | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Photo's, Completion Certificates & Payment Schedules | Recreation & Facilities
| CSE 05 | [5 empty] | TBC | Number of sports grounds maintained | 6 x community sports grounds maintained by 30th June 2025 | Number | N/A | Council Funding/ External Funding |  | N/A | N/A | N/A | 6 | Photo's, Completion Certificates & Payment Schedules | Recreation & Facilities
8 - SPATIAL EFFECTIVENESS & JUSTICE | CSE 07 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT |  |  |  | 3.3.2 Improve Fire management and mitigation | N/A | Number of Disaster Management Plan Reviewed | 1x Disaster Management Plan Reviewed by the 30th of June 2025 | Number | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Disaster Management Plan, submission, agenda and Council Resolution | Public Safety, Enforcement & Disaster Management
| CSE 09 | NKPA 5 GOOD GOVERNANCE & PUBLIC PARTICIAPATION |  |  |  |  | All | Number of fire & rescue public awareness presentations conducted | 75 x fire & rescue public awareness presentations conducted by the 30th of June 2025 | Number | N/A | N/A | N/A | N/A | N/A | 60 | 75 | Monthly Plan and Attendance register | Public Safety, Enforcement & Disaster Management
1 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | CSE 11 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | SOUND FINANCIAL MANAGEMENT | GOAL 4 - FINANCIAL VIABILITY | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Capital Expenditure spent | 100% of Capital Expenditure spent by the 30th of June 2025 | Percentage | 50900000 | TBC | TBC | 100% | 100% | 75% | 100% | Financial Report | Finance Support - Community Services
| CSE 12 | [5 empty] | N/A | Percentage of Operational Expenditure spent for the Community Services BU | 100% of Operational Expenditure spent by the 30th of June 2025 | Percentage | 859000000 | TBC | TBC | 100% | 100% | 75% | 100% | Financial Report | Finance Support - Community Services
| CSE 13 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS | Goal 1: Governance and policy risk management | 1.4 Human Resources Management and Development | 1.4.1 Improve human resource management | N/A | Percentage of posts filled in the Community Services Unit | 70% of posts filled by the 30th of June 2025 | Percentage | 10000000 | Council funding |  | N/A | N/A | N/A | 100% | HR Matrix, Appointment letters | HR - Community Services
| CSE 14 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | DELIVERING BASIC SERVICES | Goal 3: Human and Community Development | 3.1 Enhanced waste management capacity | 3.1.1 Improve the basics: cleaning, repairing, enforcing waste management practices | N/A | Number of Integrated Waste Management Plan approved | 1 Integrated Waste Management Plan approved by Council by 30th June 2025 | Number | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Disaster Management Plan, submission, agenda and Council Resolution | Disaster Management
| CSE 15 | NKPA 2-BASIC SERVICE DELIVERY |  |  |  | 3.1.2 Improve waste management in economic nodes es | 35 | Percentage of construction of New England Road Landfill Site achieved | 100% of New England Road Landfill Site Construction completed as per Approved Action Plan by the 30th of June 2025 | Percentage | N/A | N/A | N/A | 100% | 100% | 100% | 100% | Progress Report | Waste Management
2 - BACK TO BASICS | CSE 16 | NKPA 2-BASIC SERVICE DELIVERY |  | Goal 3: Human and Community Development | 3.1 Enhanced waste management capacity | 3.1.1 Improve the basics: cleaning, repairing, enforcing waste management practices | 27,28,30 | Number of non-households receiving refuse removal services | 5100 non-households receiving refuse removal service by the 30th of June 2025 | Number | N/A | N/A | N/A |  |  | 5100 | 5100 | Customer statements, waste collection schedules and register | Waste Management
| CSE 17 |  |  | Goal 3: Human and Community Development |  | 3.1 Enhance waste management capacity. | TBC | No. of wards receiving grass cutting services | 30 wards receiving grass cutting services by the 30th of June 2025 | Number | 487765.16 | N/A | N/A |  |  | 30 | 30 | Grass cutting schedule and register | Recreation & Facilities
Note on I7: Nondumiso B. Buthelezi: Sounds operational. How do we calculate, what is the formular?

## ESS TOP LAYER
CDS REFERENCE | SDBIP REFERENCE | NATIONAL KEY PERFORMANCE AREA | B2B PILLAR | GOAL | STRATEGIC OBJECTIVE | STRATEGY | WARD | INDICATOR | ANNUAL TARGET | UNIT OF MEASURE | ANNUAL BUDGET | FUNDING SOURCE | WBS/GL NUMBER | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | PORTFOLIO OF EVIDENCE | RESPONSIBLE DEPARTMENT
2- BACK TO BASICS | ESS 01 | NKPA 2 - BASIC SERVICE DELIVERY | DELIVERING BASIC SERVICES | Goal 2: Developed and Maintained Infrastructure | 2.1 Access to affordable, reliable, sustainable and modern energy for all. | 2.1.1 Develop, upgrade and maintain the electricity network | 1,2,13,19, 33-38 & 40 | Number of Substations Maintained | 30 x Substations Maintained by the 30th of June 2025 | Number | 42740924 | M/704079.JAH.D19, M/704079.JAH.D20, M/704080JAH.D19, M/704080JAH.D20, M/704080.JAH.E28, M/704081.JAH.E27, M/704081.JAH.E28, M/704080.JAH.E28 | 5 | 15 | 20 | 25 | 30 | Inspection sheet, Job cards and Register | Operations and Maintenance & Revenue Management- ESS
| ESS 02 |  |  |  | 2.1 Ensure access to affordable, reliable, sustainable and modern energy for all. | 2.1.1 Develop, upgrade and maintain the electricity network | 29, 30, 38 | Number of new household electricity connections completed | 340 x new household electricity connections completed by the 30th of June 2025 | Number | 4971000 |  |  | N/A | N/A | 200 | 340 | Quarterly progress report, Close-out Report, completion certificate and register | ESS - Planning
| ESS 03 |  |  |  | 2.1 Ensure access to affordable, reliable, sustainable and modern energy for all. | 2.1.1 Develop, upgrade and maintain the electricity network | 1,2,18,19,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,40 | Number of Street lights maintained | 15000 x Street lights maintained by the 30th of June 2025 | Number | 26000000 |  |  | N/A | N/A | 13500 | 15000 | Job cards and register | Operations and Maintenance & Revenue Management- ESS
| ESS 04 |  |  |  | 2.1 Ensure access to affordable, reliable, sustainable and modern energy for all. | 2.1.1 Develop, upgrade and maintain the electricity network | 1,2,18,19,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,40 | Percentage of electricity connections completed | 100% electricity connections completed by the 30th of June 2025 | Percentage | N/A |  |  | 100% | 100% | 100% | 100% | Memos, job card and Register | Revenue Management- ESS
| ESS 05 |  |  |  | 2.1 Access to affordable, reliable, sustainable and modern energy for all. | 2.1.1 Develop, upgrade and maintain the electricity network | 1-24 & 40 | Number of High Mast Lights installed | 15 x High Mast lights erected by the 30th of June 2025 | Number | 7816695.7 |  |  | N/A | N/A | N/A | 15 | Close out report and register | ESS - Planning
| ESS 06 |  |  |  | 2.1 Access to affordable, reliable, sustainable and modern energy for all. | 2.1.1 Develop, upgrade and maintain the electricity network | 1,2,18,19,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,40 | Number of faulty/defective meters Attended/ replaced/ rectified | 1200 of faulty/defective meters Attended/ replaced/ rectified by the 30th of June 2025 | Number | R5 000 000.00 |  |  | N/A | N/A | 974 | 1200 | Memo & Register | Revenue Management- ESS
| ESS 07 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | SOUND FINANCIAL MANAGEMENT | GOAL 4; FINANCIAL VIABILITY | 4.1 Improved Revenue collection | 4.1.1 Implement the revenue policies and enhancement strategy | N/A | Total Percentage of electricity losses reduced | Total Electricity losses reduced to 17% by the 30th of June 2025 | Percentage | N/A |  |  | reduced to 17% | reduced to 17% | reduced to 17% | reduced to 17% | Quarterly losses report | Revenue Management- ESS
| ESS 08 |  | DELIVERING BASIC SERVICES |  |  |  | 1,2,18,19,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,40 | Number of electricity disconnections attended | 39000 of Electricity disconnections attended by the 30th of June 2025 | Number | 8000000 |  |  | N/A | N/A | 31449 | 39000 | Disconnection notice, Disconnection register | Revenue Management- ESS
| ESS 09 | [5 empty] | 1,2,18,19,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,40 | Number of electricity reconnections attended | 4500 Electricity reconnections attended by the 30th of June 2025 | Number | 8000000 |  |  |  |  | 3833 | 4500 | Reconnection fax and register | Revenue Management- ESS
4 - BUILDING FINANCIAL SUSTAINABILITY | ESS 10 |  | SOUND FINANCIAL MANAGEMENT |  | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Capital Expenditure spent | 100% of Capital Expenditure spent by the 30th of June 2025 | Percentage | 279459819.92 |  |  | 100% | 100% | 75% | 100% | SAP expenditure report | ESS- Finance Support
| ESS 11 | [5 empty] | N/A | Percentage of Operational Expenditure spent | 100% of Operational Expenditure spent by the 30th of June 2025 | Percentage | 240552997 |  |  | 100% | 100% | 75% | 100% | SAP expenditure report | ESS- Finance Support
14 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | ESS 12 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS | Goal 1; Governance and policy | 1.4 Human Resources Management and Development | 1.4.1 Improve Human resources management | N/A | Percentage of Posts Filled | 100% of Posts Filled by the 30th of June 2025 | Percentage | 10000000 |  |  | 100% | 100% | N/A | 100% | Internal/external adverts circulated and New appointments circular/memo | ESS Human Resources
2- BACK TO BASICS | ESS 13 | NKPA 2 - BASIC SERVICE DELIVERY | DELIVERING BASIC SERVICES | Goal 2: Developed and Maintained Infrastructure | 2.1 Access to affordable, reliable, sustainable and modern energy for all. | 2.1.1 Develop, upgrade and maintain the electricity network | 1,2,13,19, 33-38 & 40 | Number of Poles Maintained | 400 x Poles Maintained by the 30th of June 2025 | Number | R6 200 000.00 |  |  | N/A | N/A | 280 | 400 | Job Cards and Register | Operations and Maintenance & Revenue Management- ESS
| ESS 14 | [5 empty] | 34 & 38 | Number of meters of MV Al Cable completed | Laying of 8420m x MV Al Cable completed by the 31st of March 2025 | Number | 40000000 |  |  | N/A | N/A | N/A | 8420m | Purchase Order, Invoices, Progress Report, Register and Close-out report | ESS - Planning

## SDCE TOP LAYER
CDS REFERENCE | SDBIP REFERENCE | NATIONAL KEY PERFORMANCE AREA | B2B PILLAR | GOAL | STRATEGIC OBJECTIVE | STRATEGY | WARD | INDICATOR | ANNUAL TARGET | UNIT OF MEASURE | ANNUAL BUDGET | FUNDING SOURCE | WBS/GL NUMBER | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | PORTFOLIO OF EVIDENCE | RESPONSIBLE DEPARTMENT
5 - GROWING THE REGIONAL ECONOMY | SD&CE 01 | NKPA 3 - LOCAL ECONOMIC DEVELOPMENT | LOCAL ECONOMIC DEVELOPMENT | Goal 2: Developed and Maintained Infrastructure | 2.3 Developed and Maintained Municipal road Networks | 2.3.1 Develop and Maintain Municipal road Networks | 22 & 23 | Number of km of Old Edendale Road upgraded | 1,5km of Old Edendale Road upgraded by the 30th of June 2025 | Number | R20,000,000.00 |  |  | N/A | N/A | N/A | 1,5km | Progress Report/ Payment Certificate and register | DEVELOPMENT SERVICES
| SD&CE 02 |  |  | GOAL 5; ECONOMIC GROWTH AND DEVELOPMENT | 5.1 Job Creation | 5.1.1 Facilitate the expansion of Job creation initiatives with Msunduzi | ALL | Number of work opportunities created | 1000 x work opportunities created by the 30th of June 2025 | Number | N/A |  |  | 250 | 500 | 750 | 1000 | CWP Narrative Report and register | DEVELOPMENT SERVICES
| SD&CE 03 |  |  |  | 5.2 Improved Investment Attraction, Retention and expansion | 5.2.1 Improve and streamline the development application processes and business Licencing process | ALL | Number of Businesses registered | 720 x Businesses registered by the 30th of June 2025 | Number | N/A |  |  | 180 | 360 | 540 | 720 | Schedule of business registration & Business registration forms register | DEVELOPMENT SERVICES
| SD&CE 04 | [5 empty] | ALL | Number of Businesses inspected | 900 x Businesses inspected by the 30th of June 2025 | Number | N/A |  |  | 225 | 450 | 675 | 900 | Schedule of Businesses visited and Inspection forms (Compliance notices / Summons), register | DEVELOPMENT SERVICES
1 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | SD&CE 05 |  |  |  |  | 5.2.2 Fast track the Strategic land release programme | 10 to 24 | Number of Hectares of land acquired | 5 x Hectares of land acquired by the 30th of June 2025 | Number | R11 million |  |  | N/A | N/A | N/A | 5 | Final expropriation notice served on land owner and/or advertised in newspaper and government gazette, register | TOWN PLANNING & ENVIRONMENTAL MANAGEMENT
5 - GROWING THE REGIONAL ECONOMY | SD&CE 06 |  |  |  | 5.3 Improved and developed Tourism sector | 5.3.1 Develop and strengthen the Tourism sector | ALL | Number of Msunduzi Tourism events participated in | 7 x Msunduzi Tourism events participated in by the 30th of June 2025 | Number | R 1 Million |  |  | 2 | 4 | 5 | 7 | Pictures, invitations, posters, Post event report and register | CITY ENTITIES
| SD&CE 07 |  |  |  | 5.4 SMME and entrepreneurial development | 5.4.1 Promote SMME and entrepreneurial development | ALL | Number of Quarterly Msunduzi Training Workshops facilitated | 4 x Quarterly Msunduzi Training Workshops facilitated by the 30th of June 2025 | Number | Nil |  |  | 1 | 2 | 3 | 4 | Agenda/Invitations, Attendance register | CITY ENTITIES
| SD&CE 08 | [5 empty] | ALL | Number of Business opportunities created | 20 x Business opportunities created by the 30th of June 2025 | Number | N/A |  |  | 5 | 10 | 15 | 20 | List of registered businesses assisted, signed attendance registers & Business feedback satisfaction forms and register | DEVELOPMENT SERVICES
| SD&CE 09 | [5 empty] | ALL | Number of Cooperatives and SMMEs visited and supported | 60 x Cooperatives and SMMEs visited and supported by the 30th of June 2025 | Number | N/A |  |  | 15 | 30 | 45 | 60 | A signed visitation register and photos of businesses visited and Business feedback satisfaction forms and register and register | DEVELOPMENT SERVICES
8 - SPATIAL EFFECTIVENESS & JUSTICE | SD&CE 10 | NKPA 6 - CROSS CUTTING | PUTTING PEOPLE FIRST | Goal 3; Human and community Development | 3.3 Enhanced Enforcement of By-laws, Public Safety and Security. | 3.3.1 improve Enforcement of By-laws, Public Safety and Security. | N/A | Percentage of Safe City activities completed within Msunduzi Municipality | 100% of Safe City activities completed by the 30th of June 2025 | Percentage | N/A |  |  | 100% | 100% | 100% | 100% | 1. Internal Stakeholders Meeting Minutes & register 2. Safe City Maintenance Schedules 3, Valid Safe City ISO 9001 Accreditation Certificate | CITY ENTITIES
1 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | SD&CE 11 |  |  | 6) SPATIAL EQUITY & HUMAN SETTLEMENTS | 6.2 Improved Environmental Management | 6.2.1 Improve environmental management practices | ALL | Number of sites baited and/or treated | 17 000 sites baited and/or treated by the 30th of June 2025 | Number | R90 000.00 |  |  | 3000 | 6000 | 11500 | 17000 | Vector Control register | TOWN PLANNING & ENVIRONMENTAL MANAGEMENT
| SD&CE 12 | [5 empty] | ALL | Number of water samples taken & analysed | 1 820 water samples taken & analysed by the 31st of June 2025 | Number | R150 000.00 |  |  | 455 | 910 | 1365 | 1820 | Register of Laboratory results/Listing | TOWN PLANNING & ENVIRONMENTAL MANAGEMENT
| SD&CE 13 |  |  |  | 6.3 Integrated human Settlements | 6.3.1 Construction of integrated Human Settlements | ALL | Number of Final Housing Sector Plan submitted to TMC for Council approval | 1 x Final Housing Sector Plan submitted to TMC for Council approval by the 31st of March 2025 | Number | N/A |  |  | N/A | N/A | 1 | N/A | Final housing sector plan, submission, agenda, TMC and full council resolution | HUMAN SETTLEMENTS
| SD&CE 14 | [5 empty] | 11, 13, 14, 16, 17, 18, 29, 32, 35, 38, 41, Imbali phase 3 and 4 | Number of Housing Units constructed | 140 x New Housing Units constructed by the 30th of June 2025 | Number | R 80 000 000.00 |  |  | 70 | 140 | 105 | 140 | D6 and Municipal inspection sheet | HUMAN SETTLEMENTS
4 - BUILDING FINANCIAL SUSTAINABILITY | SD&CE 15 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | SOUND FINANCIAL MANAGEMENT | GOAL 4; FINANCIAL VIABILITY | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Capital Expenditure spent | 100% of Capital Expenditure spent by the 30th of June 2025 | Percentage | TBC |  |  | 5% | 50% | 75% | 100% | Expenditure documents | SUSTAINABLE DEVELOPMENT & CITY ENTERPRISES BUSINESS UNIT
| SD&CE 16 |  |  | GOAL 4; FINANCIAL VIABILITY | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Operational Expenditure spent | 100% of Operational Expenditure spent by the 30th of June 2025 | Percentage | TBC |  |  | 5% | 50% | 75% | 100% | Expenditure documents | SUSTAINABLE DEVELOPMENT & CITY ENTERPRISES BUSINESS UNIT
14 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | SD&CE 17 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS | Goal 1; Governance and policy | 1.4 Human Resources Management and Development | 1.4.1 Improve Human resources management | N/A | Percentage of Posts Filled | 100% of Posts Filled by the 30th June 2025 | Percentage | 5000000 |  |  | N/A | 25% | N/A | 100% | Internal/external adverts circulated and New appointments circular/memo | SUSTAINABLE DEVELOPMENT & CITY ENTERPRISES BUSINESS UNIT
2- BACK TO BASICS | SD&CE 18 | NKPA 2 - BASIC SERVICE DELIVERY | DELIVERING BASIC SERVICES | Goal 2: Developed and Maintained Infrastructure | 2.2 Ensure availability and sustainable management of water and sanitation for all | 2.2.1 Develop, upgrade and maintain the water and sanitation network | 12, 22 and 23 | Number of meters of bulk sewer outfall installed | 2000m bulk sewer outfall installed for Khalanyoni by the 30th of June 2024 | Number | 40000000 |  |  | N/A | N/A | 1700m | 2000m | Progress report signed by the project engineer & meeting minutes | HUMAN SETTLEMENTS
4 - BUILDING FINANCIAL SUSTAINABILITY | SD&CE 19 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | SOUND FINANCIAL MANAGEMENT | GOAL 4; FINANCIAL VIABILITY | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of allocated budget spent | 100% of allocated budget for engineering services spent by the 30th of June 2025 | Percentage | 24000000 |  |  | N/A | N/A | 75% | 100% | INVOICE | HUMAN SETTLEMENTS

## CORPORATE SERVICES TOP LAYER
CDS REFERENCE | SDBIP REFERENCE | NATIONAL KEY PERFORMANCE AREA | B2B PILLAR | GOAL | STRATEGIC OBJECTIVES | STRATEGY | WARD | INDICATOR | ANNUAL TARGET | UNIT OF MEASURE | ANNUAL BUDGET | FUNDING SOURCE | WBS/GL NUMBER | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | PORTFOLIO OF EVIDENCE | RESPONSIBLE DEPARTMENT
14 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | CS 01 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS | Goal 1; Governance and policy | 1.2 Compliance with all legislative provisions | 1.2.1 Improve and strengthen compliance | N/A | Percentage of Legal Services provided within Msunduzi Municipality in line with the SOP | 100% of Legal Services provided by the 30th of June 2025 | Percentage | 10100000 |  |  | 100% | 100% | 100% | 100% | Poe file for Legal Services and SOP | LEGAL SERVICES
| CS 02 |  |  |  | 1.4 Human Resources Management and Development | 1.4.1 Improve Human resources management | N/A | Number of employees trained based on PDPs received from BU's and in accordance to the approved 24/25 Workplace Skills Plan | 510 x employees trained in accordance to the approved 24/25 Workplace Skills Plan facilitated by the 30th of June 2025. | Number | 12493336.98 |  |  | N/A | 20% | 330 | 510 | 1. Dossier of all submitted PDPs and signed reports requesting legal requirement / compliance trainings from Business Units. 2. Approved WSP 3. Bid Adjudication Committee Agendas & Minutes 4. Monthly Minutes/ Resolutions reporting on LGSETA WSP funding expenditure. 5.Monthly Minutes/ Resolutions reporting on the substantive implementation of the approved WSP interventions linked to WSP | HUMAN RESOURCES
| CS 03 | [5 empty] | N/A | Number of Top Management Positions filled | 1 x Top Management Position filled by the 30th of June 2025 | Number | 1778292 |  |  | N/A | N/A | N/A | 1 | 1. Council Report(s) 2. Recruitment Plan 3. Letter of appointment | HUMAN RESOURCES
| CS 04 | [5 empty] | N/A | Percentage Implemetation of Employment Equity Plan | 100% Implementation of the Employment Equity Implementation Plan for the 24/25 FY by the 30th of June 2025 | Percentage | 872304 |  |  | N/A | 1 | 80% | 100% | Employment Equity Implementation Plan Monitoring Reports, TMC Resolution, EE Policy & Council Resolution | HUMAN RESOURCES
| CS 05 | [5 empty] | N/A | Percentage of allocated budget spent | 100% Workplace Skills Plan budget spent by the 30th of June 2025 | Percentage | 17050832,95 |  |  | 3 | 6 | 80% | 100% | WSP Monthly Spend Reports and TMC resolutions | HUMAN RESOURCES
| CS 06 | [5 empty] | N/A | Percentage of Priority Posts | 10% Priority Posts filled within Msunduzi Municipality by the 30th of June 2025 | Percentage | 35000000 |  |  | N/A | N/A | N/A | 10% | 1. List of Priority Posts per BU 2. Post Adverts 3. Recruitment Plans 4. Letters of appointment 5. Final Monitoring Close-out report | HUMAN RESOURCES
| CS 07 | [5 empty] | N/A | Percentage of Posts Filled | 100% of Posts filled by the 30th of June 2025 | Percentage | 2500000 |  |  | N/A | 20% | N/A | 100% | Advert, Final reports | HUMAN RESOURCES
| CS 08 | NKPA 5 - GOOD GOVERNANCE & PUBLIC PARTICIPATION | GOOD GOVERNANCE | Goal 1; Governance and policy | 1.2 Compliance with all legislative provisions | 1.2.1 Improve and strengthen compliance | N/A | Percentage of Secretariat & Auxiliary Services provided within Msunduzi Municipality in line with the SOP | 100% of Secretariat & Auxiliary Services provided by the 30th of June 2025 | Percentage | 21038449 |  |  | 100% | 100% | 100% | 100% | Secretariat & Auxiliary Services POE file and SOP | SECRETARIAT & AUXILLIARY SERVICES
3 - IMPROVING INFRASTRUCTURE EFFICIENCY | CS 09 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT |  | Goal 2: Developed and Maintained Infrastructure | 2.4 Developed ICT infrastructure | 2.4.1 Develop and maintain ICT infrastructure | N/A | Percentage of uptime of all information and communication Technology Solutions | 95% uptime by the 30th of June 2025 | Percentage | 1837367 |  |  | 95% | 95% | 95% | 95% | ICT Server Infrastructure report | ICT
| CS 10 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | SOUND FINANCIAL MANAGEMENT | Goal 2: Developed and Maintained Infrastructure | 2.4 Developed ICT infrastructure | 2.4.1 Develop and maintain ICT infrastructure | N/A | Percentage of allocated budget spent | 100% of ICT allocated budget spent by the 30th of June 2025 | Percentage | 17000000 |  |  | N/A | 30% | 70% | 100% | Project sign-off Payment Invoices and Expenditure report | ICT
4 - BUILDING FINANCIAL SUSTAINABILITY | CS 11 |  |  | GOAL 4; FINANCIAL VIABILITY | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Capital Expenditure spent for the Corporate Services BU | 100% of Capital Expenditure spent by the 30th of June 2025 | Percentage | 18705822 |  |  | N/A | 20% | 80% | 100% | Expenditure documents | CORPORATE SERVICES BU
| CS 12 |  |  |  | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Operational Expenditure spent for the Corporate Services BU | 100% of Operational Expenditure spent by the 30th of June 2025 | Percentage | 190971914 |  |  | N/A | 20% | 80% | 100% | Expenditure documents | CORPORATE SERVICES BU

## BUDGET & TREASURY
CDS REFERENCE | SDBIP REFERENCE | NATIONAL KEY PERFORMANCE AREA | B2B PILLAR | GOAL | STRATEGIC OBJECTIVE | STRATEGY | WARD | INDICATOR | ANNUAL TARGET | UNIT OF MEASURE | ANNUAL BUDGET | FUNDING SOURCE | WBS/GL NUMBER | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | PORTFOLIO OF EVIDENCE | RESPONSIBLE DEPARTMENT
4 - BUILDING FINANCIAL SUSTAINABILITY | BTO 01 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | SOUND FINANCIAL MANAGEMENT | Goal 4: FINANCIAL VIABILITY | 4.1 Improved Revenue collection | 4.1.1 Implement the revenue policies and enhancement strategy | N/A | Percentage of Monthly collection rate of current debt | 90% Monthly collection rate of current debt by the 30th June 2025 | Percentage | N/A | N/A | N/A | 90% | 90% | 90% | 90% | Monthly age analysis report, TMCreport | Revenue Management
| BTO 02 |  |  |  | 4.1 Improved Revenue collection |  | N/A | Percentage of Monthly collection rate of arrear debt | 10% Monthly collection rate of arrear debt achieved for the 24/25 FY by the 30th June 2025 | Percentage | N/A | N/A | N/A | 10% | 10% | 10% | 10% | Monthly age analysis report, TMCreport | Revenue Management
| BTO 03 |  |  |  | 4.1 Improved Revenue collection |  | N/A | Percentage of all electricity and water meters read | 75% of all electricity and water meters read 24/25 FY by the 30th of June 2025 | Percentage | N/A | N/A | N/A | 75% | 75% | 75% | 75% | Meter Reading Stats | Revenue Management
| BTO 06 |  |  | Goal 4: FINANCIAL VIABILITY | 4.4 Improved Budgeting and reporting | 4.4.1Conform to all MFMA and MFMA regulations | N/A | Number of Annual Financial Statements submitted | 1 x Msunduzi Municipality Annual Finanicial Statement to the AG by the 31 August 2024 | Number | N/A | N/A | N/A | 1 | N/A | N/A | N/A | Acknowledgement letter from AG & Annual Financial Statement | Finance Governance
| BTO 07 | [5 empty] | N/A | Number of Msunduzi Municipality Consolidated Annual Finanicial Statement prepared & submitted to the AG | 1 x Msunduzi Municipality Consolidated Annual Finanicial Statement submitted to AG by the 30th September 2024 | Number | N/A | N/A | N/A | 1 | N/A | N/A | N/A | Acknowledgement letter from AG & Annual Financial Statement | Finance Governance
| BTO 08 | [5 empty] | N/A | Number of Procurement Plan for the 2024/2025 financial year prepared | 1 x Procurement Plan for the 2025/2026 financial year prepared and submitted to TMC for approval by Council by the 30th of June 2025 | Number | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Procurement plan, submission to TMC, Agenda, Council resolutions | Supply Chain Management
| BTO 09 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT |  | 4.1 Improved Revenue collection | 4.3 Improved Expenditure Management | 4.3 Improved expenditure management | N/A | Number of Vehicles Purchased and Delivered | 10 x Vehicles Purchased and Delivered for Msunduzi Municipality for the 24/25 FY by the 31st of May 2025 | Number | N/A | N/A | N/A | N/A | 5 | N/A | 10 | Invoices and FAR extract | Assests & Liabilities Management
| BTO 10 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT |  | 4.1 Improved Revenue collection |  |  | N/A | percentage of All creditors be paid within 30 days | 100% of all creditors must be paid within 30 days from date of receipt of invoice by Expenditure Management unit from suppliers by the 30th of June 2025 | Percentage | N/A | N/A | N/A | N/A | 100% | N/A | 100% | Expenditure Report and list of creditors outstanding | Expenditure Management
| BTO11 |  |  | 4.1 Improved Revenue collection | 4.2 Revenue Enhancement | 4.1.1 Implement the revenue policies and enhancement strategy | N/A | Number of indigent customers registered | 6 000 indigent customers registered to receive the free basic services by the 30th June 2025 | Number | N/A | N/A | N/A | 500 | 1500 | 3000 | 6000 | Indigent Registers & Applications | Revenue Management
| BTO12 |  |  | 4.4 Improved Budgeting and reporting | 4.4 Improved Budgeting and reporting | 4.4.1Conform to all MFMA and MFMA regulations | N/A | Number of Draft budget for 2024/25 FY & two outer years prepared & submitted to TMC | 1 x Final Draft & Original budget for 2025/26 FY & two outer years prepared & submitted to TMC by the 15th of May 2025 | Number | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Final Draft & Original budget for 2025/26 FY, Agenda, submission to TMC and TMC Resolution | Budget Planning & Implementation Monitoring
| BTO13 | [5 empty] | N/A | Percentage of Capital Expenditure spent | 100% of Capital Expenditure spent for the Budget & Treasury BU by the 30th of June 2025 | Percentage | N/A | N/A | N/A | 100% | 100% | 75% | 100% | Expenditure report | Budget Planning & Implementation Monitoring
| BTO14 | [5 empty] | N/A | Percentage of Operational Expenditure spent | 100% of Operational Expenditure spent by the 30th of June 2025 | Percentage | 190971914 |  |  | N/A | 20% | 75% | 100% | Expenditure documents | Budget & Treasury Unit
14 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | BTO 15 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS |  | 5.1 Job Creation | Improve Human resources management | N/A | Percentage of Posts Filled | 100% of Posts Filled for Budget & Treasury BU by the 30th of June 2025 | Percentage | N/A | N/A | N/A | 25% | 25% | N/A | 100% | Internal/external adverts circulated and New appointments circular/memo | Budget & Treasury Unit

## OFFICE OF THE MM
CDS REFERENCE | REFERENCE | NATIONAL KEY PERFORMANCE AREA | B2B PILLAR | GOAL | STARTEGIC OBJECTIVE | STRATEGY | WARD | INDICATOR | ANNUAL TARGET / OUTPUT | UNIT OF MEASURE | ANNUAL BUDGET | FUNDING SOURCE | WBS/GL NUMBER | QUARTER 1 | QUARTER 2 | QUARTER 3 | ANNUAL | PORTFOLIO OF EVIDENCE | RESPONSIBLE DEPARTMENT
1 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | MMO 01 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | GOOD GOVERNANCE | Goal 1: Governance and policy | 1.2 Compliance with all legislative provisions | 1.2. 1 Increased institutional capacity and promote transformation | N/A | 100% (5) of IDP Activities completed s per Operational Plan | 100% (5) of IDP Activities by the 30th of June 2025 | Percentage | N/A | N/A | N/A | 100% | 100% | 100% | 100% | Minutes, Presentations, Attendance Register, Reports and resolutions | SP - IDP
| MMO 02 | [5 empty] | N/A | Percentage of PMS Activities Completed | 100% (13) of PMS Activities completed by 30th of June 2025 | Percentage | TBC | COUNCIL | 0/104503/BAH.000 4500460000 | 100% | 100% | 100% | 100% | Minutes, Presentations, Attendance Register, Reports and resolutions | SP - PMS
| MMO 03 | [5 empty] | N/A | 100% (5) of PURP Activities completed as per Operational Plan | 100% (5) of PURP Activities completed by 30th of June 2025 | Percentage | N/A | N/A | N/A | 100% | 100% | 100% | 100% | TMC Agendas, Reports, Resolutions, Policies | SP - PURP
| MMO 04 | [5 empty] | N/A | 100% (6) of CDS Activities completed as per Operational Plan | 100% (6) of CDS Activities completed by 30th of June 2025 | Percentage | N/A | N/A | N/A | 100% | 100% | 100% | 100% | Invite Agenda Register Presentation Minutes Reports E-Mails TMC Resolutions | SP - CD
| MMO 05 | NKPA 5 - GOOD GOVERNANCE & PUBLIC PARTICIPATION |  | Goal 1: Governance and policy | 1.2 Compliance with all legislative provisions | 1.3.2 Strength Public Participation structures | N/A | Number of Oversight Reports tabled | 1 Oversight Report 24/25 FY tabled and adopted by Council by the 31st March 2025 | Number | N/A | N/A | N/A |  |  | N/A | 1 | Oversight report, submission, agenda & Council resolution | Potitical Support
| MMO 06 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT |  | Goal 1: Governance and policy | 1.1 Fight fraud and corruption | 1.1.1 Improve and strengthen Internal Audit and Risk Management | N/A | Number of Risk Managemetn Plans submitted | 1 Annual Risk Management Plan submitted to Risk Management Committee by 30 June 2025 | Number | N/A | N/A | N/A |  |  | N/A | 1 | Annual Risk Plan, submission, agenda and resolution | Risk Management
| MMO 07 | NKPA 5 - GOOD GOVERNANCE & PUBLIC PARTICIPATION |  | Goal 1: Governance and policy | 1.3 Developed and strengthen Communication and Stakeholder Relations | 1.3.1 Develop partnerships in terms of communications | N/A | Number of Media engagements conducted | 4 media engagements conducted by the 30th of June | Number | N/A | N/A | N/A |  |  | 3 | 4 | Agenda, Invites and attendance regisers | Communications & IGR
| MMO 08 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT |  | Goal 1: Governance and policy | 1.1 Fight fraud and corruption | 1.1.1 Improve and strengthen Internal Audit, Risk Management and compliance | N/A | Number of report on the status of selected cases of fraud & corruption which are under Hawks criminal investigation and or prosecution prepared & submitted to the Audit Committee | 4 x reports on the status of selected cases of fraud & corruption which are under Hawks criminal investigation and or prosecution prepared & submitted to the Audit Committee by June 2025 | Number | N/A | N/A | N/A |  |  | 3 Q4 (23/24) REPORT Q1 (24/25) REPORT Q2 (24/25) REPORT | 4 Q4 (23/24) REPORT Q1 (24/25) REPORT Q2 (24/25) REPORT Q3 (24/24) REPORT | Cover report and minutes of Audit Committee, submission, agenda and Meetings/resolutions | Forensic Investigations
| MMO 09 | NKPA 4 - FINANCIAL VIABILITY & MANAGEMENT | [5 empty] | % of Capital Expenditure spent | 100% of Capital Expenditure spent by the 30th of June 2025 | Percentage | 29799499 | N/A | N/A | 100% | 100% | 75% | 100% | Expenditure report | MUNICIPAL MANAGER'S OFFICE
4 - BUILDING FINANCIAL SUSTAINABILITY | MMO 10 |  | SOUND FINANCIAL MANAGEMENT | GOAL 4; FINANCIAL VIABILITY | 4.3 Improved expenditure management | 4.3.1 Apply expenditure controls procedures | N/A | Percentage of Operational Expenditure spent | 100% of Operational Expenditure spent by the 30th of June 2025 | Percentage | 3950000 | TBC | TBC |  |  | 75% | 100% | Expenditure documents | MUNICIPAL MANAGER'S OFFICE
14 - BUILDING A CAPABLE & DEVELOPMENTAL MUNICIPALITY | MMO 11 | NKPA 1 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT | BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS | Goal 1; Governance and policy | 1.4 Human Resources Management and Development | 1.4.1 Improve Human resources management | N/A | Percentage of Posts Filled | 100% of Posts Filled by the 30th June 2025 | Percentage | TBC | TBC | TBC |  |  | N/A | 100% | Internal/external adverts circulated and New appointments circular/memo | MUNICIPAL MANAGER'S OFFICE