THE MSUNDUZI MUNICIPALITY

PUBLIC NOTICE

NOTICE OF AMENDMENT TO CONTRACT

In terms of the Municipal Finance Management Act Section 116(3) (a) and (b) notice is hereby given for the proposed amendment of the contract listed below:

| Contract Number | Project Name | Name of Service Provider | Proposed Amended |
| --- | --- | --- | --- |
| Contract No. SCM 60 OF 20/21 | Provision of Legal Panel to the Msunduzi Municipality | Panel | (a)The extension of time on a month-to-month basis not exceeding a period of 3 months commencing from the 16th of February 2025 to the 17th of May 2025. (b) It noted that there were two other extensions and an extension to the scope of works that was done by the Human Settlements Business Unit and GEDVI on the Conveyancing Panel. (c) It noted that this equivalent to a percentage variation of 13% and when considering the previous extensions on the contract, the variation percentage goes above 15%. (d) This extension is for the finalisation of the existing work/cases or urgent issues and no new work will be issued during this period. (e) This report be noted in terms of Section 116 (3) of the Local Government: Municipal Finance Management Act No.56 of 2003. |

Affected parties must submit representation not later than 13 March 2025 addressed to: Municipal Manager, City Hall, Chief Albert Luthuli Street (Commercial Road), Pietermaritzburg.

For Enquiries: Mrs N. Ngcobo, Telephone 033 392 2002; Email: nelisiwe.ngcobo@msunduzi.gov.za