THE MSUNDUZI MUNICIPALITY

PUBLIC NOTICE

NOTICE OF AMENDMENT TO CONTRACT

In terms of the Municipal Finance Management Act Section 116(3) (a) and (b) notice is hereby given for the proposed amendment of the contract listed below:

| Contract Number | Project Name | Name of Service Provider | Proposed Amended |
| --- | --- | --- | --- |
| Contract No. SCM 66 of 12/13 | CONTRACT NO. SCM 66 OF 12/13: PLANNING, REBUILDING AND REHABILITATION OF 2086 SINGLE AND DOUBLE UNITS IN EDENDALE- WIREWALL RECTIFICATION HOUSING PROJECT | BASFOUR 170 CC | Approval of Extension of Time (a) That a 6-month extension of time for the planning, rebuilding and rehabilitation of 2086 Single and Double units for the vulnerable households under Wire-Wall Rectification Housing Project to be in line with the Provincial Department of Human Settlements programme. (b) That the further extension of contract for a period 6 months’ increments to a total of 24-months. The further extension to be based on the Implementing Agent’s performance as measured against the construction programme in line with the legal advisor’s recommendation, BE NOTED. (c) That it be NOTED that the original scope of work consists of 2086 housing units and to date 1910 units are completed. The requested extension of time is to complete the remaining 176 units thus bringing the scope of works to completion. |

Affected parties must submit representation not later than 23 June 2023 addressed to: Municipal Manager, City Hall, Chief Albert Luthuli Street (Commercial Road), Pietermaritzburg.

For Enquiries: Mr L. H. Mapholoba, Telephone 033 392 2002; Email: Lulamile.mapholoba@msunduzi.gov.za.