THE MSUNDUZI MUNICIPALITY

PUBLIC NOTICE

NOTICE OF AMENDMENT TO CONTRACT

In terms of the Municipal Finance Management Act Section 116(3) (a) and (b) notice is hereby given for the proposed amendment of the contract listed below:

| Contract Number | Project Name | Name of Service Provider | Proposed Amended |
| --- | --- | --- | --- |
| Contract No. SCM 28 of 21/22 | APPOINTMENT OF THREE SKILLS DEVELOPMENT PROVIDERS TO PROVIDE THREE TRAINING PROGRAMMES FOR A PERIOD OF 12 MONTHS | - Qualfurn Training Projects - Meyiswa Training Academy - 3. Velile Supply Chain | (a) Extension of time for a period of 12 months starting from the 26th of August 2025 to the 25th of August 2026 for the Appointment of three skills development providers to provide three LGSETA funded training programmes. (b) This is the first extension for the three LGSETA Funded Training projects and the expenditure for this extension is R 1 205 000 which is 66% of the contract value over 3 years. (c) It noted that the project is fully funded by LGSETA (d) This extension be noted in terms of Section 116 (3) of the Municipal Finance Management Act |

affected parties must submit representation not later than 12 September 2025 addressed to: Municipal Manager, City Hall, Chief Albert Luthuli Street (Commercial Road), Pietermaritzburg.

For Enquiries: Mr S. F. Mndebele, Telephone 033 392 2002; Email: Felani.Mndebele@msunduzi.gov.za