## ANNEX A (hidden)
ANNEXURE A: MONTHLY PROJECTION OF REVENUE BY EACH SOURCE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2011/12
Revenue By Source
Property rates | 28820083.7 | 46112133.92 | 51876150.66 | 57640167.4 | 63404184.14 | 28820083.7 | 46112133.92 | 57640167.4 | 57640167.4 | 80696234.36 | 28820083.7 | 28820083.7 | 576401674
Property rates - penalties & collection charges | 1690613.2058 | 2704981.1293 | 3043103.7704 | 3381226.4116 | 3719349.0527 | 1690613.2058 | 2704981.1293 | 3381226.4116 | 3381226.4116 | 4733716.9762 | 1690613.2058 | 1690613.2058 | 33812264.1157
Service charges - electricity revenue | 70845834.95 | 113353335.92 | 127522502.91 | 141691669.9 | 155860836.89 | 70845834.95 | 113353335.92 | 141691669.9 | 141691669.9 | 198368337.86 | 70845834.95 | 70845834.95 | 1416916699
Service charges - water revenue | 15867682.8 | 25388292.48 | 28561829.04 | 31735365.6 | 34908902.16 | 15867682.8 | 25388292.48 | 31735365.6 | 31735365.6 | 44429511.84 | 15867682.8 | 15867682.8 | 317353656
Service charges - sanitation revenue | 5700000 | 9120000 | 10260000 | 11400000 | 12540000 | 5700000 | 9120000 | 11400000 | 11400000 | 15960000 | 5700000 | 5700000 | 114000000
Service charges - refuse revenue | 3937610.1 | 6300176.16 | 7087698.18 | 7875220.2 | 8662742.22 | 3937610.1 | 6300176.16 | 7875220.2 | 7875220.2 | 11025308.28 | 3937610.1 | 3937610.1 | 78752202
Service charges - other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment | 976688.6 | 1562701.76 | 1758039.48 | 1953377.2 | 2148714.92 | 976688.6 | 1562701.76 | 1953377.2 | 1953377.2 | 2734728.08 | 976688.6 | 976688.6 | 19533772
Interest earned - external investments | 605000 | 968000 | 1089000 | 1210000 | 1331000 | 605000 | 968000 | 1210000 | 1210000 | 1694000 | 605000 | 605000 | 12100000
Interest earned - outstanding debtors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dividends received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines | 173728.55 | 277965.68 | 312711.39 | 347457.1 | 382202.81 | 173728.55 | 277965.68 | 347457.1 | 347457.1 | 486439.94 | 173728.55 | 173728.55 | 3474571
Licences and permits | 3719.35 | 5950.96 | 6694.83 | 7438.7 | 8182.57 | 3719.35 | 5950.96 | 7438.7 | 7438.7 | 10414.18 | 3719.35 | 3719.35 | 74387
Agency services | 19101.27 | 30562.0319 | 34382.2859 | 38202.5399 | 42022.7939 | 19101.27 | 30562.0319 | 38202.5399 | 38202.5399 | 53483.5559 | 19101.27 | 19101.27 | 382025.3992
Transfers recognised - operational | 91301000 |  |  | 91301000 |  |  | 91301000 |  |  | 91301000 |  | 0 | 365204000
Other revenue | 2489241.4356 | 3982786.297 | 4480634.5842 | 4978482.8713 | 5476331.1584 | 2489241.4356 | 3982786.297 | 4978482.8713 | 4978482.8713 | 6969876.0198 | 2489241.4356 | 2489241.4356 | 49784828.7128
Gains on disposal of PPE | [11 empty] | 0 | 0
Total Revenue (excluding capital transfers and contributions) | 222430303.9614 | 209806886.3382 | 236032747.1305 | 353559607.9228 | 288484468.7151 | 131129303.9614 | 301107886.3382 | 262258607.9228 | 262258607.9228 | 458463051.0919 | 131129303.9614 | 131129303.9614 | 2987790079.2277

## ANNEX B (hidden)
ANNEXURE B: MONTHLY PROJECTION OF REVENUE COLLECTED BY EACH VOTE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2011/12
Revenue by Vote
Vote 1 - Corporate Services and Planning | 17300539.9789 | 16318695.6107 | 18358532.562 | 27499724.7355 | 22438206.4647 | 10199184.7567 | 23420050.8329 | 20398369.5133 | 20398369.5133 | 35659072.5409 | 10199184.7567 | -219269705.2654 | 2920226
Vote 2 - Financial Management Area | 18261003.154 | 17224650.3508 | 19377731.6446 | 29026409.6232 | 23683894.2323 | 10765406.4692 | 24720247.0355 | 21530812.9385 | 21530812.9385 | 37638734.7986 | 10765406.4692 | 408517165.2065 | 643042274.8608
Vote 3 - Infrastructure Development, Service Delivery and Maintenance Management | 156367695.5575 | 147493478.8315 | 165930163.6854 | 248551119.8272 | 202803533.3933 | 92183424.2697 | 211677750.1193 | 184366848.5393 | 184366848.5393 | 322297859.2429 | 92183424.2697 | 290768911.7248 | 2298991058
Vote 4 - Sustainable Community Service Delivery Provision Management | 30501065.271 | 28770061.5453 | 32366319.2385 | 48482353.7369 | 39558834.6248 | 17981288.4658 | 41289838.3505 | 35962576.9316 | 35962576.9316 | 62867384.5095 | 17981288.4658 | -348886238.0715 | 42837350
Total Revenue by Vote | 222430303.9614 | 209806886.3382 | 236032747.1305 | 353559607.9228 | 288484468.7151 | 131129303.9614 | 301107886.3382 | 262258607.9228 | 262258607.9228 | 458463051.0919 | 131129303.9614 | 131130133.5945 | 2987790908.8608
0

## ANNEX C (hidden)
ANNEXURE C: MONTHLY PROJECTION OF OPERATIONAL EXPENDITURE BY VOTE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2011/12
Expenditure - Standard
Governance and administration | 27392410.25 | 43827856.4 | 49306338.45 | 54784820.5 | 60263302.55 | 27392410.25 | 43827856.4 | 54784820.5 | 54784820.5 | 76698748.7 | 27392410.25 | 27392410.25 | 547848205
Executive and council | 3554723.25 | 5687557.2 | 6398501.85 | 7109446.5 | 7820391.15 | 3554723.25 | 5687557.2 | 7109446.5 | 7109446.5 | 9953225.1 | 3554723.25 | 3554723.25 | 71094465
Budget and treasury office | 10328299.45 | 16525279.12 | 18590939.01 | 20656598.9 | 22722258.79 | 10328299.45 | 16525279.12 | 20656598.9 | 20656598.9 | 28919238.46 | 10328299.45 | 10328299.45 | 206565989
Corporate services | 13509387.55 | 21615020.08 | 24316897.59 | 27018775.1 | 29720652.61 | 13509387.55 | 21615020.08 | 27018775.1 | 27018775.1 | 37826285.14 | 13509387.55 | 13509387.55 | 270187751
Community and public safety | 18828913.15 | 30126261.04 | 33892043.67 | 37657826.3 | 41423608.93 | 18828913.15 | 30126261.04 | 37657826.3 | 37657826.3 | 52720956.82 | 18828913.15 | 18828913.15 | 376578263
Community and social services | 1935958 | 3097532.8 | 3484724.4 | 3871916 | 4259107.6 | 1935958 | 3097532.8 | 3871916 | 3871916 | 5420682.4 | 1935958 | 1935958 | 38719160
Sport and recreation | 3851892 | 6163027.2 | 6933405.6 | 7703784 | 8474162.4 | 3851892 | 6163027.2 | 7703784 | 7703784 | 10785297.6 | 3851892 | 3851892 | 77037840
Public safety | 8883453.15 | 14213525.04 | 15990215.67 | 17766906.3 | 19543596.93 | 8883453.15 | 14213525.04 | 17766906.3 | 17766906.3 | 24873668.82 | 8883453.15 | 8883453.15 | 177669063
Housing | 1827714 | 2924342.4 | 3289885.2 | 3655428 | 4020970.8 | 1827714 | 2924342.4 | 3655428 | 3655428 | 5117599.2 | 1827714 | 1827714 | 36554280
Health | 2329896 | 3727833.6 | 4193812.8 | 4659792 | 5125771.2 | 2329896 | 3727833.6 | 4659792 | 4659792 | 6523708.8 | 2329896 | 2329896 | 46597920
Economic and environmental services | 8072605.7925 | 12916169.268 | 14530690.4265 | 16145211.585 | 17759732.7435 | 8072605.7925 | 12916169.268 | 16145211.585 | 16145211.585 | 22603296.219 | 8072605.7925 | 8072605.7925 | 161452115.85
Planning and development | 3283402.5 | 5253444 | 5910124.5 | 6566805 | 7223485.5 | 3283402.5 | 5253444 | 6566805 | 6566805 | 9193527 | 3283402.5 | 3283402.5 | 65668050
Road transport | 4789203.2925 | 7662725.268 | 8620565.9265 | 9578406.585 | 10536247.2435 | 4789203.2925 | 7662725.268 | 9578406.585 | 9578406.585 | 13409769.219 | 4789203.2925 | 4789203.2925 | 95784065.85
Environmental protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trading services | 92783261.1 | 148453217.76 | 167009869.98 | 185566522.2 | 204123174.42 | 92783261.1 | 148453217.76 | 185566522.2 | 185566522.2 | 259793131.08 | 92783261.1 | 92783261.1 | 1855665222
Electricity | 60779507.2 | 97247211.52 | 109403112.96 | 121559014.4 | 133714915.84 | 60779507.2 | 97247211.52 | 121559014.4 | 121559014.4 | 170182620.16 | 60779507.2 | 60779507.2 | 1215590144
Water | 23803408.6 | 38085453.76 | 42846135.48 | 47606817.2 | 52367498.92 | 23803408.6 | 38085453.76 | 47606817.2 | 47606817.2 | 66649544.08 | 23803408.6 | 23803408.6 | 476068172
Waste water management | 4750926 | 7601481.6 | 8551666.8 | 9501852 | 10452037.2 | 4750926 | 7601481.6 | 9501852 | 9501852 | 13302592.8 | 4750926 | 4750926 | 95018520
Waste management | 3449419.3 | 5519070.88 | 6208954.74 | 6898838.6 | 7588722.46 | 3449419.3 | 5519070.88 | 6898838.6 | 6898838.6 | 9658374.04 | 3449419.3 | 3449419.3 | 68988386
Other | 2055124 | 3288198.4 | 3699223.2 | 4110248 | 4521272.8 | 2055124 | 3288198.4 | 4110248 | 4110248 | 5754347.2 | 2055124 | 2055124 | 41102480
Total Expenditure - Standard | 149132314.2925 | 238611702.868 | 268438165.7265 | 298264628.585 | 328091091.4435 | 149132314.2925 | 238611702.868 | 298264628.585 | 298264628.585 | 417570480.019 | 149132314.2925 | 149132314.2925 | 2982646285.85

## ANNEX D (hidden)
ANNEXURE D: MONTHLY PROJECTION OF CAPITAL EXPENDITURE BY VOTE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | Nov. | Dec. | January | Feb. | March | April | May | June | Budget Year 2011/12
Multi-year expenditure to be appropriated
Vote 1 - Corporate Services and Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5150000 | 5150000
Vote 2 - Financial Management Area | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
Vote 3 - Infrastructure Development, Service Delivery and Maintenance Management | 0 | 0 | 14300000 | 17876000 | 25025000 | 8938000 | 8938000 | 17876000 | 19663000 | 25025000 | 26813000 | 14299000 | 178753000
Vote 4 - Sustainable Community Service Delivery Provision Management |  |  | 3689000 | 4612000 | 6455000 | 2306000 | 2306000 | 4612000 | 5073000 | 6455000 | 6916000 | 3687000 | 46111000
Capital multi-year expenditure sub-total | 0 | 0 | 17989000 | 22488000 | 31480000 | 11244000 | 11244000 | 22488000 | 24736000 | 31480000 | 33729000 | 23136000 | 230014000

## COMPULSORY INDICATORS (hidden)
MSUNDUZI MUNICIPALITY SDBIP 2012/2013
THE FOLLOWING ARE KEY PERFORMANCE INDICATORS EMANATING FROM SECTION 43 OF THE LOCAL GOVERNMENT MUNICIPAL SYSTEMS ACT AND REGULATIONS 5 (1)
No. | National Key Performance Areas | Strategic Business Unit | Compulsory Key Performance Indicators | Unit of Measure / Calculations | Annual |  |  | Annual |  | Quarterly |  | Blockages | Corrective Measures | Support needed in terms of unblocking | Portfolio of Evidence
[5 empty] | Demand | Baseline | Backlog | Target |  | Target
[8 empty] | Projected | Actual | Projected | Actual
1 | MUNICIPAL TRANSFORMATION AND INSTITUTION/AL DEVELOPMENT | Corporate Services | Budget spent on Work Skills Plan | Budgeted amount
Actual amount spent
Percentage spent
2 |  |  | Number of people from employment equity target groups employed in the three highest levels of management | Number
3 | BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | Infrastrucuture Services | Number (as well as percentage) of households with access to potable (drinkable) water | Number
Percentage
4 |  |  | Number (as well as percentage) of households with access to sanitation | Number
Percentage
5 |  |  | Number of households with access to refuse removal at least once per week | Number
6 |  |  | Number (as well as percentage) of households with access to electricity | Number
Percentage
7 |  | Financial Services | Percentage of households earning less than R1100 per month with access to free basic services | Percentage
8 | LOCAL ECONOMIC DEVELOPMENT | Development Services | Number of work opportunities created through LED development initiatives including Capital Projects | Number
9 | FINANCIAL VIABILITY AND FINANCAIL MANAGEMENT | Financial Services | Percentage of a municipality's capital budget actually spent on capital projects identified in the IDP | Percentage : Total spending on capital projects divided by total capital budget x 100
10 |  |  | Financial viability in terms of debt coverage | Ratio: Total operating revenue received minus operating grants divided by debt service payments (ie. Interests plus redemption)
11 |  |  | Financial viability in terms of cost coverage | Ratio: Available cash plus investments divided by monthly fixed operating expenditure
12 |  |  | Financial viability in terms of outstanding service debtors to revenue | Ratio: Outstanding service debtors divided by annual revenue actually received for services

## CONTENTS PAGE (hidden)
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
CONTENTS PAGE
| NO. | DESCRIPTION | PAGE / S
| 1 | ANNEXURE 1: SDBIP 2012 / 2013 COVER PAGE | Page 1
| 2 | ORGANIZATIONAL OVERVIEW | Page 2
| 3 | ANNEXURE 1 (E) - CBU COVER PAGE | Page 3
| 4 | CORPORATE BUSINESS UNIT OVERVIEW | Page 4
| 5 | INTERNAL AUDIT OVERVIEW | Page 5
| 6 | INTERNAL AUDIT REPORT | Pages 6 - 7
| 7 | OFFICE OF THE MUNICIPAL MANAGER OVERVIEW | Page 8
| 8 | OFFICE OF THE MUNICIPAL MANAGER REPORT | Pages 9 - 16
| 9 | INTERGRATED DEVELOPMENT PLAN OVERVIEW | Page 17
| 10 | INTERGRATED DEVELOPMENT PLAN REPORT | Pages 18 - 19
| 11 | MARKETING OVERVIEW | Page 20
| 12 | MARKETING REPORT | Pages 21 - 22
| 13 | ANNEXURE 1 (F) - FINANCE COVER PAGE | Page 23
| 14 | FINANCE OVERVIEW | Page 24
| 15 | BUDGET & TREASURY OVERVIEW | Page 25
| 16 | BUDGET & TREASURY REPORT | Pages 26 - 27
| 17 | EXPENDITURE MANAGEMENT OVERVIEW | Page 28
| 18 | EXPENDITURE MANAGEMENT REPORT | Pages 29 - 31
| 19 | REVENUE MANAGEMENT OVERVIEW | Page 32
| 20 | REVENUE MANAGEMENT REPORT | Pages 33 - 34
| 21 | SUPPLY CHAIN MANAGEMENT OVERVIEW | Page 35
| 22 | SUPPLY CHAIN MANAGEMENT REPORT | Pages 36 - 38
| 23 | ANNEXURE 1 (G) - COMMUNITY SERVICES COVER PAGE | Page 39
| 24 | COMMUNITY SERVICES OVERVIEW | Page 40
| 25 | AREA BASED MANAGEMENT OVERVIEW | Page 41
| 26 | AREA BASED MANAGEMENT REPORT | Pages 42 - 43
| 27 | HEALTH & SOCIAL SERVICES OVERVIEW | Page 44
| 28 | HEALTH & SOCIAL SERVICES REPORT | Pages 45 - 48
| 29 | COMMUNITY DEVELOPMENT OVERVIEW | Page 49
| 30 | COMMUNITY DEVELOPMENT REPORT | Pages 50 - 54
| 31 | PUBLIC SAFETY ENFORCEMENT & DISASTER MANAGEMENT OVERVIEW | Page 55
| 32 | PUBLIC SAFETY ENFORCEMENT & DISASTER MANAGEMENT REPORT | Pages 56 - 58
| 33 | ANNEXURE 1 (H) - INFRASTRUCTURE SERVICES COVER PAGE | Page 59
| 34 | INFRASTRUCUTURE SERVICES OVERVIEW | Page 60
| 35 | WATER & SANITATION OVERVIEW | Page 61
| 36 | WATER & SANITATION REPORT | Pages 62 - 64
| 37 | ELECTRICITY OVERVIEW | Page 65
| 38 | ELECTRICITY REPORT | Page 66 - 68
| 39 | PROJECT MANAGEMENT UNIT OVERVIEW | Page 69
| 40 | PROJECT MANAGEMENT UNIT REPORT | Pages 70 - 71
| 41 | FLEET MANAGEMENT OVERVIEW | Page 72
| 42 | FLEET MANAGEMENT REPORT | Page 73
| 43 | ROADS, TRANSPORTATION & PUBLIC WORKS OVERVIEW | Page 74
| 44 | ROADS, TRANSPORTATION & PUBLIC WORKS REPORT | Page 75 - 79
| 45 | LANDFILL SITE OVERVIEW | Page 80
| 46 | LANDFILL SITE REPORT | Pages 81 - 83
| 47 | ANNEXURE 1 (I) - CORPORATE SERVICES COVER PAGE | Page 84
| 48 | CORPORATE SERVICES OVERVIEW | Page 85
| 49 | SOUND GOVERNANCE OVERVIEW | Page 86
| 50 | SOUND GOVERNANCE REPORT | Pages 87 - 89
| 51 | LEGAL SERVICES OVERVIEW | Page 90
| 52 | LEGAL SERVICES REPORT | Page 91
| 53 | INFORMATION COMMUNICATION TECHNOLOGY OVERVIEW | Page 92
| 54 | INFORMATION COMMUNICATION TECHNOLOGY REPORT | Pages 93 - 94
| 55 | HUMAN RESOURCE MANAGEMENT, OCCUPATIONAL HEALTH, ORGANIZATIONAL DEVELOPMENT & SKILLS DEVELOPMENT UNIT OVERVIEW | Page 95
| 56 | HUMAN RESOURCE MANAGEMENT, OCCUPATIONAL HEALTH, ORGANIZATIONAL DEVELOPMENT & SKILLS DEVELOPMENT UNIT REPORT | Pages 96 - 101
| 57 | ANNEXURE 1 (J) - ECONOMIC DEVELOPMENT COVER PAGE | Page 102
| 58 | ECONOMIC DEVELOPMENT OVERVIEW | Page 103
| 59 | LOCAL ECONOMIC DEVELOPMENT OVERVIEW | Page 104
| 60 | LOCAL ECONOMIC DEVELOPMENT REPORT | Pages 105 - 107
| 61 | HOUSING OVERVIEW | Page 108
| 62 | HOUSING REPORT | Pages 109 - 111
| 63 | GEDI, PLANNING, ENVIRONMENTAL & LICENSING OVERVIEW | Page 112
| 64 | GEDI, PLANNING, ENVIRONMENTAL & LICENSING REPORT | Pages 113 - 114

## ANNEXURE 1
ANNEXURE 1: SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
SDBIP 2012/2013

## Organizational overview
ORGANISATIONAL OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | ORGANISATIONAL OVERVIEW
| 1.1 | TOTAL PROJECTS: | 366
| 1.1.1 | OPERATING PROJECTS | 299
| 1.1.2 | CAPITAL PROJECTS | 67
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 1.1.1 | A total of 299 Operating Projects were reported on the SDBIP for the Quarter ending Dember 2012 - 2012/2013 financial year
| 1.1.2 | 8.36% of the projects were reported as having Nil Achievements for the Quarter ending December 2012 - 2012/2013 financial year
| 1.1.3 | 21.73% of the projects were reported as having been partially met for for the Quarter ending December 2012 - 2012/2013 financial year
| 1.1.4 | 42.80% of the projects were reported as having been met for the Quarter ending December 2012 - 2012/2013 financial year
| 1.1.5 | 9.36% of the projects were reported as having exceeded the target for the Quarter ending December 2012 - 2012/2013 financial year
| 1.1.6 | 17.72% of the projects were reported as not applicable due to not having any targets set for the Quarter ending December 2012
| 1.1.7 | 0% of the projects were not reported on by Business Units for the 3rd Quarter.
- 2012/2013 financial year.
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS
| 2.1.1 | A total of 67 Capital Projects were reported on the SDBIP for the Quarter ending Dember 2012 - 2012/2013 financial year
| 2.1.2 | 11.94% of the projects were reported as having Nil Achievements for the Quarter ending December 2012 - 2012/2013 financial year
| 2.1.3 | 32.83% of the projects were reported as having been partially met for for the Quarter ending December 2012 - 2012/2013 financial year
| 2.1.4 | 34.22% of the projects were reported as having been met for the Quarter ending December 2012 - 2012/2013 financial year
| 2.1.5 | 19.40% of the projects were reported as having exceeded the target for the Quarter ending December 2012 - 2012/2013 financial year
| 2.1.6 | 1.49% of the projects were reported as not applicable due to not having any targets set for the Quarter ending December 2012
- 2012/2013 financial year.
2.1.7

## CBU COVER
ANNEXURE 1(E): CORPORATE BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
SDBIP 2012/2013

## CBU overview
CORPORATE BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
1 | CORPORATE BUSINESS UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 69
1.1.1 | OPERATING PROJECTS | 69
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## IA overview
INTERNAL AUDIT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | INTERNAL AUDIT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 15
| 1.1.1 | OPERATING PROJECTS | 15
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Internal Audit
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.1 INTERNAL AUDIT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
IA 01 | Institutional Development and Transformation/Governance | Annual Audit Plan | Development of the Annual Audit Plan | N/A | Annual Plan for 2011/12 was approved on 25 February 2012 | Annual plan for 2012/13 approved by Audit Committee by 31 August 2012 | Date of approval of the Annual Audit Plan | N/A | N/A | N/A | Nil Required | Approved Annual plan by 31 August 2012 | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IA02 | Institutional Development and Transformation/Governance | Risk Management Function | Risk Management Policy | N/A | Current Risk Management Policy adopted by Council on 12 February 2009 | Revised Risk Management Policy adopted by Council by 30 September 2012 | Date of adoption of the Risk Management Policy | N/A | N/A | N/A | Nil Required | Adopted Risk Management Policy by 30 September 2012 | N/A | N/A | Not Applicable | N/A | N/A | N/A
IA03 | Institutional Development and Transformation/Governance | Risk Management Function | Risk Assessment | N/A | Risk Assessment finalised 25/02/12 | Risk Profile/Register of the Municipality adopted by Council by 30 September 2012 | Date of adoption of the Risk Profile/Register | N/A | N/A | N/A | Nil Required | Adopted Risk Profile/Register | N/A | N/A | Not Applicable | N/A | N/A | N/A
IA04 | Institutional Development and Transformation/Governance | Risk Management Function |  | N/A | Risk Management Strategy not in place | Risk Management Strategy adopted by Council 30 September 2012 | Date of adoption of Risk Management Strategy | N/A | N/A | N/A | Nil Required | Adopted Risk Management Strategy by 30 September 2012 | Review & reporting | Finalised for SMC deliberations | Target met | Lack capacity as a result EM:IAU is stretched to the limit | Worked overtime through the festive season to catch up | Risk Management Strategy & SMC minnutes
IA05 | Institutional Development and Transformation | Anti-Fraud & Corruption | Anti-Fraud & Corruption Policy | N/A | Anti-Fraud & Corruption Policy developed in 2009 | Revised Anti-Fraud & Corruption Policy adopted by Council by 31 October 2012 | Date of adoption of Anti-Fraud & Corruption Policy | N/A | N/A | N/A | N/A | N/A | Adopted revised Anti-Fraud & Corruption Policy by 31 October 2012 | Finalised for SMC deliberations | Target met | Lack capacity as a result EM:IAU is stretched to the limit | Worked overtime through the festive season to catch up | Rant-fraud & Corruption Policy & SMC minnutes
IA06 | Institutional Development and Transformation | Anti-Fraud & Corruption | Anti-Fraud & Corruption Strategy | N/A | Anti-Fraud & Corruption Strategy developed in 2009 | Revised Anti-Fraud & Corruption Strategy adopted by Council by 31 October 2012 | Date of adoption of the Anti-Fraud & Corruption Strategy | N/A | N/A | N/A | N/A | N/A | Adopted revised Anti-Fraud & Corruption Strategy by 31 October 2012 | Finalised for SMC deliberations | Target met | Lack capacity as a result EM:IAU is stretched to the limit | Worked overtime through the festive season to catch up | Anti-fraud and corruption Strategy & SMC minnutes
IA07 | Institutional Development and Transformation/Governance | Anti-Fraud & Corruption | Anti-Fraud/Ethics Awareness Campaign | N/A | Never done | Anti-Fraud & Corruption/Ethics workshops Rollout Plan submitted to MANCO by 31 October 2012 | Date of Anti-Fraud & Corruption / Ethics workshops Rollout Plan | N/A | N/A | N/A | N/A | N/A | Anti-Fraud & Corruption / Ethics Workshop Rollout Plan | Anti-fraud & Corruption framework finalised for SMC & workshops to be done once adoption by Council has been obtained | Target met | Lack capacity as a result EM:IAU is stretched to the limit | Worked overtime through the festive season to catch up | Plan
IA08 | Institutional Development and Transformation/Governance | Anti-Fraud & Corruption |  | N/A | Never done | Anti-Fraud & Corruption/Ethics workshops done as per the Rollout Plan | Number of Workshops done vs planned | 280000 | N/A | N/A | Council | N/A | Anti-Fraud & Corruption/Ethics workshops done as per the Rollout Plan | Anti-fraud & Corruption framework finalised for SMC & workshops to be done once adoption by Council has been obtained | Nil achieved | Lack capacity as a result EM:IAU is stretched to the limit and lack of budget | Submitted request for additional budget during mid-term review | Attendance registers
[8 empty] | 0361001100 | N/A | N/A |  | N/A | 60000 | N/A | N/A | N/A | N/A | N/A
IA09 | Governance | Anti-Fraud & Corruption | Adhoc Forensic Investigations | N/A | No record | Forensic Investigations done as per request/need | Forensic investigations done within the timeframe prescribed in the project plan | N/A | N/A | N/A | Nil Required | Forensic investigations done within the timeframe prescribed in the project plan | Forensic investigations done within the timeframe prescribed in the project plan | Forensic investigations done within the timeframe prescribed in the project plan | Target met | N/A | N/A | Reports
[8 empty] | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IA10 | Institutional Development and Transformation/Governance | Annual Audit Plan 2012/13 | Internal Audit Assignments | N/A | 11 projects completed 2011/12 | Internal Audit assignments done as per Annual Audit Plan per annum | Number of projects completed | 1120000 | N/A | N/A | Council | Internal Audit Assignments Completed as per the annual plan | Internal Audit Assignments Completed as per the annual plan | Assignements being done in terms of the annual plan. | Target Partially Met | Delays in submitting information on time and challenges experience one of the partners | Educating Managers in the delays with the submission. Appoint a bigger pool of service providers in the new contract. | Internal Aduti Reports and updated plan
[8 empty] | 0361001100 | N/A | N/A |  | 340000 | 210000 | N/A | N/A | N/A | N/A | N/A
IA11 | Institutional Development and Transformation/Governance | Internal Audit Methodology | Internal Audit Methodology | N/A | Not in place | Internal Audit Methodology developed and implemented by 31 December 2012 | Date by which the methodology is completed | N/A | N/A | N/A | Nil Required | N/A | Internal Audit Methodology completed | Completed | Target Exceeded | N/A | N/A | Methodology
[8 empty] | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
IA12 | Institutional Development and Transformation | Training & Development | Training Auditors | N/A | Nil | Training attended as per the training plan | Number of training courses attended | N/A | N/A | N/A | Nil Required | Training attended as per the training plan | Training attended as per the training plan | Waiting for budget approval during mid-term review | Nil Achieved | Lack of budget | Waiting for budget approval during mid-term review | Documents for attandence of training
[8 empty] | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
IA13 | Institutional Development and Transformation/Governance | Annual Audit Plan | Development of the Annual Audit Plan | N/A | Annual Plan for 2011/12 was approved on 25 February 2012 | Annual plan for 2013/14 approved by Audit Committee by 30 June 2013 | Date of approval of the Annual Audit Plan | N/A | N/A | N/A | Nil Required | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IA14 | Institutional Development and Transformation/Governance | Risk Management Function | Risk Assessment 2013/14 | N/A | Risk Assessment for 2011/12 finalised 25/02/12 | Updated Risk Profile/Register of the Municipality adopted by Council by 30 June 2013 | Date of adoption of the Updated Risk Profile/Register | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
IA15 | Institutional Development and Transformation/Governance | Risk Management Function |  | N/A | Risk Management Strategy not in place | Risk Management Strategy for 2013/14 done & submitted to the Audit Committee 30 June 2013 | Date of submission to the Audit Committee of Risk Management Strategy | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A

## MMs OFFICE overview
OFFICE OF THE MUNICIPAL MANAGER OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | OFFICE OF THE MUNICIPAL MANAGER OVERVIEW
| 1.1 | TOTAL PROJECTS: | 37
| 1.1.1 | OPERATING PROJECTS | 37
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## OFFICE OF THE MM
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.2 OFFICE OF THE MUNICIPAL MANAGER
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
MSP 01 | Good Governance and Public Participation | Sports Programme | Salga Games | All | Annual Games | Participated in SALGA Games with 15 codes by December 2012. | Date and number of sports codes | 300 000 | N/A | N/A | Council | District games in July 2012 / 15 codes | Participated in SALGA Games in December 2012 with 15 codes | Participated in SALGA Games in December 2012 with 15 codes |  | Target Met | N/A | N/A | teamlists
[8 empty] | 0131151015 | N/A | N/A |  | 300 000 | District Funding | N/A |  | N/A | N/A | N/A | N/A
MSP 02 | Good Governance and Public Participation |  | Golden Games | All | Annual Games | Participated in Games with 120 participants by August 2012 | Date and number of participants | 286 808 | N/A | N/A | Council | Participated in Golden Games 27 -29 August 2012 with 120 participants | Purchase of sports equipment for the elderly | equipment delivered |  | Target Met | N/A | N/A | delivery note
[8 empty] | 0131151015 | N/A | N/A |  | 120 000 | 166 808 | N/A |  | N/A | N/A | N/A | N/A
MSP 03 | Good Governance and Public Participation | Junior Council Outreach Programme | Back to School | All | N/A | Visit 5 schools | Number of schools visited | 10 000 | N/A | N/A | Council | Select schools to be visited | Draft letters to the schools | letters delivered to the schools |  | Target Met | N/A | N/A | draft letters
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 04 | Good Governance and Public Participation |  | Child Protection Campaign | All | N/A | 2 child protection campaigns in July 2012 and May 2013 | Number of campaigns | 20 000 | N/A | N/A | Council | 1 Campaign during Imbizo yamadoda | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | 10 000 | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 05 | Good Governance and Public Participation |  | School Exchange | All | N/A | 4 rural and 4 urban schools | Number of schools | 7 000 | N/A | N/A | Council | Identification of rural and urban schools | 2 Meetings with the schools | Meetings with the schools |  | Target Met | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 06 | Good Governance and Public Participation |  | Child to Work | All | N/A | 2 children (1 boy and 1 girl) per zone | Number of children placed | 10 000 | N/A | N/A | Council | 2 Meetings with the Department of Education | Identification of schools and selection of learners | schools & learners identified |  | Target Met | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | 8 000 | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 07 | Good Governance and Public Participation |  | JCC Festival | All | N/A | Participation by 14 schools | Number of schools participated | 35 000 | N/A | N/A | Council | Weekly Meeting with JCC and Marketing and Comunication unit for publicity; invitations, advertisement | JCC Festival for 14 schools forming JCC | N/A |  | Target Partially Met | festival postponed due to school exams | new date to be proposed by JCC | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | 35 000 | N/A |  | N/A | N/A | N/A | N/A
MSP 08 | Good Governance and Public Participation |  | Leadership Training | All | N/A | 30 JCC members trained on leadership | Number of members trained | 30 000 | N/A | N/A | Council | N/A | N/A |  |  | Not Applicable | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 09 | Good Governance and Public Participation | Annual Events/Campaigns Programme | Annual Reed dance | All | Annual Event | Annual Reed dance held on 14-16 September 2012 with 440 participants | Date of event and number of participants | 90 000 | N/A | N/A | Council | Reed dance | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | 90 000 | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 10 | Good Governance and Public Participation | Annual Events/Campaigns Programme | 16 Days Activism | All | Annual Awareness Programme | Annual Awareness Programme held on 25 November – 10 December 2012 with 500 participants | Date of event and number of participants | 227 000 | N/A | N/A | Council | N/A | 16 Days of Activism campaign | 16 Days of Activism campaign |  | Target Met | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | 227 000 | N/A |  | N/A | N/A | N/A | N/A
MSP 11 | Good Governance and Public Participation |  | Annual Information Week | All | Annual Event | Participation of 60 high schools in the Annual Information Week to be held from 20 -24 February 2013 | Number of schools participating | 350 000 | N/A | N/A | Council | Meeting with National Departments | Meetings with schools | Meetings with stakeholders |  | Target Partially Met | schools closed in December | further meetings early in 2013 | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 12 | Good Governance and Public Participation | Educational Programmes | Blindness Education/ Awareness | All | N/A | 20 participants per zone educated on common causes of blindness | Number of participants | 140 000 | N/A | N/A | Council | Blindness education in Zone 1 | Blindness education in Zone 2 | rtps & expenditure schedule signed |  | Target Partially Met | rtps & expenditure schedules signed, funds not available | funds to be made available during midterm budget review | rtps & expenditure schedules
[8 empty] | 0131151015 | N/A | N/A |  | 35 000 | 35 000 | N/A |  | N/A | N/A | N/A | N/A
MSP 13 | Good Governance and Public Participation |  | Human Trafficking Education/ Awareness | All | N/A | Participation of 5 primary schools in educating them on Human Trafficking | Number of participants |  | N/A | N/A | Council | Zone 1 | Zone 2&3 | N/A |  | Target Met | N/A | N/A | N/A
[9 empty] | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 14 | Good Governance and Public Participation |  | Human Rights Education | All | N/A | 100 persons with disabilities educated on Human Rights in March 2013 | Number of participants | 90 000 | N/A | N/A | Council | Meetings with Ward Councillors and war rooms members | Meetings with Provincial Departments | Meetings with Provincial Departments |  | Target Met | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 15 | Good Governance and Public Participation |  | Blind & Deaf Literacy Programme | All | N/A | 60 participants for Braille literacy and 80 for sign language. | Number of participants | 320 000 | N/A | N/A | Council | 15 for Braille and 20 for sign language | 15 for Braille and 20 for sign language | rtps & expenditure schedules |  | Target Partially Met | rtps & expenditure schedules signed, funds not available | funds to be made available during midterm budget review | rtps & expenditure schedules
[8 empty] | 0131151015 | N/A | N/A |  | 80 000 | 80 000 | N/A |  | N/A | N/A | N/A | N/A
MSP 16 | Good Governance and Public Participation | Orphans & Vulnerable Children | Drivers Licences | All | N/A | Provision of driver’s licences to 78 orphans and vulnerablechildren. | Number of orphans/ vulnerable children getting drivers licences | 195 000 | N/A | N/A | Council | 20 | 20 | rtps & expenditure schedules |  | Target Partially Met | rtps & expenditure schedules signed, funds not available | funds to be made available during midterm budget review | rtps & expenditure schedules
[8 empty] | 0131151015 | N/A | N/A |  | 50 000 | 50 000 | N/A |  | N/A | N/A | N/A | N/A
MSP 17 | Good Governance and Public Participation |  | 2) School Uniforms | All | N/A | Provision of school uniforms to 10 schools | Number of orphans/ vulnerable children getting school uniforms | 300 000 | N/A | N/A | Council | Purchase of school uniforms for 10 schools | N/A | MM to approve bid specification report |  | Target Partially Met | report to be signed by MM | to advertise once report is signed | bid specification report
[8 empty] | 0131151015 | N/A | N/A |  | 300 000 | N/A | N/A |  | N/A | N/A | N/A | N/A
MSP 18 | Good Governance and Public Participation | Public Participation | Izimbizo | All | 2011/12 Izimbizo | Conduct imbizo in November 2012 & April 2013 | Number and date of imbizo | 250 000 | N/A | N/A | Council | N/A | Izimbizo | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | 0131151013 | N/A | N/A |  | N/A | 125 000 | N/A | N/A | N/A | N/A | N/A | N/A
OTS 02 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act | Ward Committee Support | Computers | All | N/A | Acquire 37 computers for 37 ward offices | date | N/A | 245 000 | N/A | MSIG | Specifications and award of tender | Delivery of 37 computers and install in 37 ward offices | Went on tender notice on the 21 December 2012 | Still on tender notice | Target Partially Met | Delays in tender advertisement | Appoint service provider within the received quotation | Speaker's Office/SCM
[8 empty] | N/A |  | N/A |  |  | 245 000 | N/A | N/A | N/A | N/A | N/A | N/A
OTS 03 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act | Functioning of Ward Committees | Annual schedule of meetings | All | 1 | Completed schedule of ward committee meetings submitted to Cogta by 30/6/13 | completed schedule and date | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTS 04 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act |  | Monthly Ward Reports | All | N/A | 1) Submission of monthly reports from each of the 37 ward committees by the 5th monthly to the Speaker’s Office | Monthly report from each ward by the 5th monthly | N/A | N/A | N/A | N/A | 111 | 111 | nil |  | Nil Achieved | Cllr's on reses will be submitting on the 05th Feb 2013 | N/A | Speaker's Office
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTS 05 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act |  |  |  |  | 2) Forward report to relevant business unit/ Customer Care Centre for actioning | Register of forwarded items | N/A | N/A | N/A | N/A | Updated and maintained register | Updated and maintained register | as per queries that would be received. | All queries received was forwarded to CCC within 5 days of receiving them | Target Met | N/A | N/A | Office of the Speaker files
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTS 06 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act |  | Submission of minutes by Ward Assistants | All | N/A | Submission of Ward Committee minutes and Community meetings by Ward Assistants 5 days after each meeting | Minutes from each ward within 5 days of each meeting | N/A | N/A | N/A | N/A | Minutes from each ward within 5 days of each meeting | Minutes from each ward within 5 days of each meeting | 7 community meetings expected to be held and 27 ward committee meetings as per annual schedule of meetings | 04 community meetings held and 10 ward committee meetings helda | Target Met | N/A | N/A | Office of the Speaker files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 01 | Municipal Transformation & Institutional Development | Organizational Performance Management | SDBIP | All | SDBIP 2012/2013 was approved within 28 days after the approval of the budget & IDP | Approved SDBIP 2013 / 2014 - 28 days after the approval of the budget (before 30 June 2013) | Date of approval | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 02 | Municipal Transformation & Institutional Development |  |  | All | SDBIP 2011/2012 was not made public within 14 days after the approval by the Mayor | Approved SDBIP 2012 / 2013 made public within 14 days after the approval of the Mayor - Placed on Muncipal Website | Date of publishing | N/A | N/A | N/A | Nil Required | Approved SDBIP 2012/ 2013 published on website by 12/7/2012 | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 03 | Municipal Transformation & Institutional Development |  |  | All | Nil monthly reports on the SDBIP produced in 2011/2012. | 12 Monthly reports on the SDBIP submitted to PF’s, MPAC, EXCO & Full Council | Number of monthly reports | N/A | N/A | N/A | Nil Required | 3 | 3 | 3 |  | Target Met | N/A | N/A | Reports / Council Resolutions
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 04 | Municipal Transformation & Institutional Development | Performance Management Reporting | SDBIP Quarterly Reports | All | 4 | 4 Quarterly reports on the SDBIP submitted to PF’s, MPAC, EXCO & Full Council | Number of quarterly reports | N/A | N/A | N/A | Nil Required | 1 | 1 | 1 |  | Target Met | N/A | N/A | Reports / Council Resolutions
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 05 | Municipal Transformation & Institutional Development |  | Annual performance report | All | 1 | Completed Annual Performance Report submitted to the Auditor General by 31st August 2012 | Date of submission | N/A | N/A | N/A | Nil Required | Completed Annual Performance Report submitted to the Auditor General by 31st August 2012 | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 06 | Municipal Transformation & Institutional Development |  | Mid-year performance review | All | 1 | Mid-Year Performance Review submitted and approved by Council by the end of January 2013 | Date of approval | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 07 | Municipal Transformation & Institutional Development |  | Annual report | All | 1 | Annual Report tabled in Council by the 31st January 2013 | Date Annual Report tabled in Council | 250 000 | N/A | N/A | Council | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | 011 100 1031 | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 08 | Municipal Transformation & Institutional Development |  | Oversight Report | All | 1 | Oversight Report tabled and adopted by Council by the 31st March 2013 | Date Oversight report tabled in Council | 50 000 | N/A | N/A | N/A | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | To identify savings at mid-year review | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 09 | Municipal Transformation & Institutional Development | Performance Management System | PMS Policy | All | 0 | Annual Performance Management Policy Framework adopted by 31 July 2012 | Date of adoption | N/A | N/A | N/A | Nil Required | Annual Performance Management Policy Framework adopted by 31/7/2012 | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 10 | Municipal Transformation & Institutional Development |  |  |  | N/A | 100 % implementation of approved Annual Performance Management Policy Framework | 100% implementation | N/A | N/A | N/A | Nil Required | 100% implementation | 100% implementation | 100% implementation |  | Target Met | N/A | N/A | SDBIP Monthly Reports, Quarterly Reports, Annual Report, 1st Qtr Performance assessments of s57 & 58 managers. Council Resolutions
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 11 | Municipal Transformation & Institutional Development | Performance Management System | Performance Agreements | All | 2 | 30 x signed performance agreement for Managers up to level 3 within 1 month of the beginning of the financial year | Date of signed performance agreements | 410 400 | N/A | N/A | Council | 28 x signed performance agreements by 31/07/2012 | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | savings in 2011/ 2012 year to be identified | N/A | N/A |  | 410 400 | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 12 | Municipal Transformation & Institutional Development |  |  | All | 0 | S57 Managers Annual Performance agreements made public within 14 days after the approval of the SDBIP | Date of published performance agreements | N/A | N/A | N/A | N/A | Performance agreements published on website by 11/7/2012 | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 13 | Municipal Transformation & Institutional Development |  |  | All | 0 | 30 Quarterly Assessments of all Managers up to level 3 | Number of quarterly assessments | N/A | N/A | N/A | N/A | 22 Quarterly Assessments of all Managers up to level 3 | 30 Quarterly Assessments of all Managers up to level 3 | 27 |  | Target Partially Met | DMM - ED not available at time of assessments as well as PM - LED & PM-ICT. | Assessments to be conducted before 2nd qtr assessments | Performance assessment schedule of meetings and assessments.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
OPMS 14 | Municipal Transformation & Institutional Development |  | Automation of Performance Management System | All | 0 | Reporting template (SDBIP) Automated & available online via Council’s Intranet | Date of Automation (live system) | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A

## IDP overview
INTERGRATED DEVELOPMENT PLAN UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | INTERGRATED DEVELOPMENT PLAN UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 11
| 1.1.1 | OPERATING PROJECTS | 11
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## IDP
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.3 INTERGRATED DEVELOPMENT PLAN
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
IDP 01 | Good Governance & Public Pariticpation | IDP Review | IDP Process Plan 2013/14 | N/A | Approved IDP Process Plan 2012/13 | IDP Process Plan 2013/14 approved and adopted by 30 August 2012 | Date of adopted IDP Process Plan | N/A | N/A | N/A | Nil Required | IDP Process Plan 2013/14 approved and adopted by 30 August 2012 | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | n/a | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 02 | Good Governance & Public Pariticpation |  | Situational Analysis Presentation (Backlogs, baseline data | All Wards | Stats SA Community Survey | Finalized baseline data and backlogs by 15 October 2012 | Finalized baseline data and backlogs | N/A | N/A | N/A | Nil Required | N/A | Finalized baseline data and backlogs by 15 October 2012 | Finalized baseline data and backlogs by 15 October 2012 |  | Target partially met | Provisional report presented based only on available statistics of the Stats SA phased reports | A fully comprehensive report would be made available | Provisional Situational Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 03 | Good Governance & Public Pariticpation |  | Corporate Reviews for Corporate Strategies and Sector plans | All Wards | Five Year Sector Plans in the 2012/13-2016/17 IDP | Approved, Agreed and Revised Strategies completed by 30 November 2012 | Date of approved strategies | 90 000 | N/A | N/A | COGTA | Data collection & collation | Approved, Agreed and Revised Strategies completed by 30 November 2012 | Approved, Agreed and Revised Strategies completed by 30 November 2012 |  | Nil achieved | Delayed decisions caused by postment of SMC meeting between end of October 2012 and November 2012 | Finalization of the review of existing sector plans and departmental new submissions prioritization process will be finalised on 16-18 Jan 2013 at the OMC workshop | October 2012 Monthly Report
[8 empty] | 141001643 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 04 | Good Governance & Public Pariticpation |  | Conduct Projects Prioritization Process | All Wards | Prioritized projects in the IDP 2012/13-2016/17 | Approved Priority Projects by 30 Novmber 2012 | Date of approved priority projects | N/A | N/A | N/A | N/A | Data collection & collation | Approved Priority Projects by 30 Novmber 2012 | Approved Priority Projects by 30 Novmber 2012 |  | Nil achieved | Similar to as above point 3 | Similar to as above point 3 | Similar to as above point 3
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 05 | Good Governance and Public Participation | Public Participation | Stakeholders and Ward Committees Consultations | All Wards | Stakeholders Forum and izimbizo | Conduct stakeholders and community needs engagements by 15 November 2012 & 15 April 2013 | Dates of community needs engagements | 15 000 | N/A | N/A | Council | N/A | End of October and mid November 2012 | End of October and mid November 2012 |  | Target Partially met | Delayed decisions on submitted reports to the SMC | Due to delayed decisions on report submitted, public paerticipation dates were rescheduled for 09 December 2012 | October 2012 Monthly Report
[8 empty] | 141001643 | N/A | N/A |  | N/A | 7 500 | N/A | N/A | N/A | N/A | N/A | N/A
IDP 06 | Good Governance and Public Participation |  | Sector Departments (IGR engagements) |  | Quarterly engagements on agreed priorities for Local Municipality and District | Quarterly IGR Engagements between the Msunduzi Municipality and District Municipality; and Sector departments. | Quarterly meetings | N/A | N/A | N/A | Nil Required | End of Septmber 2012 | Mid December 2012 | Mid December 2012 |  | Target met | N/A | N/A | IDP Forum minutes and SMC minutes for late November 2012
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 07 | Good Governance and Public Participation |  | IDP Representative Foum | All Wards | Previous Prioritised needs | Quarterly meetings of the IDP Representative Forum | Quarterly meetings | N/A | N/A | N/A | Nil Required | Quarterly meetings of the IDP Representative Forum-End of Septmber 2012 | Quarterly meetings of the IDP Representative Forum-Mid December 2012 | Quarterly meetings of the IDP Representative Forum-Mid December 2012 |  | Target met | N/A | N/A | IDP Forum minutes and SMC minutes for late November 2012
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 08 | Good Governance and Public Participation | IDP Review | Publication and Printing | N/A | Public Notices and adverts published | 5 x Public notices and Adverts | Number of public notices and adverts | 24 000 | N/A | N/A | Council | 1 x public notice | 2 x public notice | 2 x public notice |  | Target met | N/A | N/A | Advert for imbizo/engagement of various stakeholders on 09 December 2012
[8 empty] | 141001643 | N/A | N/A |  | 6 000 | 12 000 | N/A | N/A | N/A | N/A | N/A | N/A
IDP 09 | Good Governance and Public Participation | IDP Review | Publication and Printing | N/A | IDP Document printed and approved | IDP Document designed, printed and approved by 30 April 2012 | Published IDP Book | 170 000 | N/A | N/A | Council & COGTA | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | 141001643 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 10 | Good Governance and Public Participation | MDB Plan | Facilitation the MDB Process | 7, 26, 37 AND DEM 4155 | MDB Action Plan Guideline towards 2016 LG Elections | Finalized re-determination of municipal boundaries through public participation and stakeholders involvement | Finalized re-determination of municipal boundaries | N/A | N/A | N/A | N/A | As per the MDB Action Plan | As per the MDB Action Plan | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDP 11 | Good Governance and Public Participation | IDP Review | Facilitate and co-ordinate development and revision of various sector plans | N/A | Completed Sector Plans | Finalized revised/ new sector plans by 31 October 2012 | Completed sector plans | N/A | N/A | N/A | N/A | Data collection & collation | Finalized revised/ new sector plans by 31 October 2012 | Already covered by points IDP 03 and 04 above |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## MARKETING overview
MARKETING UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | MARKETING UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 6
| 1.1.1 | OPERATING PROJECTS | 6
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## MARKETING
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.4 MARKETING
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
M&C 01 | Municipal Transformation and Institutional Development | Corporate Image | Corporate Identity | N/A | No Corporate identity. | Approved Corporate Identity policy and implementation plan by 31/12/12: 100% Implementation of the implementation plan | Adoption Date | N/A | N/A | N/A | Nil Required | First Draft of policy and implementation plan completed | Adopted policy & implementation plan: 31/12/12 | Corporate Identity submitted and approved by SMC, Portfolio Committee and EXCO | Target Partially Met | Dependent on processes of approval by committees. | Follow up on processes. | Corpotae Identity Manual.
[7 empty] | % Implementation | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
M&C 02 | Social and Economic Development. | Marketing | City Marketing Strategy | N/A | No Marketing Strategy. | Approved Marketing Strategy by 31/12/12: 100% Implemented | Adoption Date | N/A | N/A | N/A | Nil Required | First Draft Completed | Marketing strategy Adopted: 31/12/12 | Draft Marketing Strategy submitted and approved by SMC. Going through other committees. | Target Partially Met | Delayed submission of inputs by stakeholders. | Follow up on approval processes. | Draft Marketing Strategy document.
[7 empty] | % Implemented | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
M&C 03 | Good Governance | Communication | Municipal Newspaper | N/A | No existing Municipal Newspaper. | Monthly copies of newspaper published & distributed. | Number of newspapers published and distributed monthly | 1 200 000 | N/A | N/A | Council | Monthly copies of newspaper published & distributed. | Monthly copies of newspaper published & distributed. | Municipal Newspaper produced and distributed Monthly. | Target Met | N/A | N/A | Monthly Copies.
[8 empty] | 0111001330 | N/A | N/A |  | 300 000 | 300 000 | N/A | N/A | N/A | N/A | N/A
M&C 04 | Good Governance |  | Communication Strategy | N/A | Approved Communication Strategy needing review. | Reviewed Communication Strategy adopted by 30/9/12 & 100% Implemetned. | Date and % implementation | N/A | N/A | N/A | Nil Required | Communication strategy adopted by 30/9/12 | 100% implementation | Reviewd Communication Strategy approved by Full Council. | Target Met | N/A | N/A | Reviewed Communication Strategy.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
M&C 05 | Good Governance |  | Communications Forum. | N/A | No Forum. | Communications Forum established by 30/9/12, and monthly meetings held. | Established forum & monthly meetings | N/A | N/A | N/A | Nil Required | Forum established by 30/9/12 | Established Communicator's Forum. | Terms of Reference for Communicator's Forum approved. | Target Partially Met | Delayed Provincial Communicator's Forum sitting. | Meeting with relevant stakeholders | Terms of Reference.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
M&C 06 | Good Governance |  | Municipal Website | N/A | Operational but not compliant nor effective. | 100% compliant website | % compliance | N/A | N/A | N/A | Nil Required | 100% | Upload all approved documents. | All approved documents uploaded. | Target Met | N/A | N/A | Uploaded documents on website.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## FINANCE COVER
ANNEXURE 1(F): FINANCE BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## FINANCE overview
FINANCE BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | FINANCE BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 48
| 1.1.1 | OPERATING PROJECTS | 48
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## BUDGET overview
BUDGET & TREASURY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | BUDGET & TREASURY UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 11
| 1.1.1 | OPERATING PROJECTS | 11
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Budget & Treasury
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.1 BUDGET & TREASURY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
B&T 01 | Financial Viability and Management | Compliance | IDP/BUDGET Process Plan | N/A | 2011/2012 process plan approved on the 31 August 2011 | Approved legislative process plan by 31 August 2012 | Date of approved process paln | N/A | N/A | N/A | Nil Required | Approved legislative process plan by 31 August 2012 | N/A | not yet applicable | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 02 | Financial Viability and Management |  | Reporting | N/A | N/A | 12 Section 71 monthly reports produced within 10 days after the month ends | Number | N/A | N/A | N/A | Nil Required | 3 x monthly reports produced within 10 days after the month ends | 3 x monthly reports produced within 10 days after the month ends | 3 x monthly reports produced within 10 days after the month ends | Target Partially Met | December is not yet over, but last quarter reports is done | we have to wait until month to prepare the report | Mothly Reports
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 03 | Financial Viability and Management |  |  | N/A | N/A | 4 quarterly reports produced within 10 days after the quarter ends | Number | N/A | N/A | N/A | Nil Required | 1 x quarterly report produced within 10 days after the month ends | 1 x quarterly report produced within 10 days after the month ends | 1 x quarterly report produced within 10 days after the month ends | Target Partially Met | Quarter is not yet over however Sept & Oct reports are ready | Waiting for month end so we can prepare relevant reports | Mothly Reports
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 04 | Financial Viability and Management |  |  | N/A | N/A | 1 mid year / adjustment budget review S72 report produced by 25 January 2013 | Date | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 05 | Financial Viability and Management |  | Budget Policy | N/A | 2011/2012 Budget policy approved on the 2012/05/28 | Reviewed Budget Policy by 31 May 2013 | Date | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 06 | Financial Viability and Management |  | Virement Policy | N/A | 2011/2012 Virement policy approved on the 2012/05/28 | Reviewed Virement Policy by 31 May 2013 | Date | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 07 | Financial Viability and Management | Annual Financial Statements | Cash flow | N/A | Daily, weekly, monthly and quarterly monitoring and reporting | Healthy cash & cash equivalents | Daily, weekly, montly & quarterly monitoring and reporting. | N/A | N/A | N/A | Nil Required | 66 daily, 12 weekly, 3 monthly & 1 quarterly reports produced | 66 daily, 12 weekly, 3 monthly & 1 quarterly reports produced | the cashflow is tabled on a weekly and monthly basis to SMC, Finance Portfolio,EXCO | Target Met | N/A | N/A | Cashflow
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 08 | Financial Viability and Management |  | Financial Control | N/A | NIL | Adopted policy/ procedure manual by 30/09/12 | Date of adopted policy/ procedure manual | N/A | N/A | N/A | Nil Required | Adopted policy/ procedure manual by 30/09/12 | N/A | Procedure manual already approved by SMC | Target Met | N/A | N/A | Minutes of SMC reports
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 09 | Financial Viability and Management |  |  |  | NIL | 100% Implementation of policy/ procedural manual | % | N/A | N/A | N/A | Nil Required | 100% Implementation of policy/ procedural manual | 100% Implementation of policy/ procedural manual | Since approval we are ensuring compliance with the manual | Target Met | N/A | N/A | Minutes of SMC reports
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&T 10 | Financial Viability and Management |  | Annual Financial Statements | N/A | 2010/2011 Audited Annual financial statements tabled on the 25th of January 2012. | Annual Financial Statements adopted by 31/01/13 | 1. Date of adoption of Annual Financial Statements | N/A | N/A | N/A | Nil Required | Annual Financial Statements submitted to the AG by 31 August 2012 | N/A | N/A | Not Applicable | N/A | N/A | N/A
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | 2. Submit Annual Financial Statements to the Auditor General by 31 August 2011 | 2. Date of adoption of Annual Financial Statements | N/A | N/A | N/A |  | N/A | N/A | N/A | Not Applicable | N/A | N/A | N/A
B&T 11 | Financial Viability and Management |  | Audit Compliance | N/A | Unqualified audit report | Clean audit report | Unqualified audit opinion | N/A | N/A | N/A | Nil Required | N/A | Unqualified audit report | Unqualified audit opinion received | Target Met | N/A | N/A | AG's Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## EXP MGT overview
EXPENDITURE MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | EXPENDITURE MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 13
| 1.1.1 | OPERATING PROJECTS | 13
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Expenditure
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.2 EXPENDITURE MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
EXM 01 | Financial viability and Management | Trade and Sundry Paments | Cost containment strategy | N/A | Nil | 1.Approved strategy by the 31st of August 2012 | 100 % implementation of the plan. | N/A | N/A | N/A | N/A | Approved cost containment strategy by 31 Aug 2012 | Full implementation of the cost containment strategy | Draft strategy to SMC. | Target Partially Met | Delays in collecting informatiom | Report to SMC has been prepared. | Draft strategy and Report.
[6 empty] | 2. Implementation by 1 September 2012 |  | N/A | N/A | N/A |  | Implementation | Implementation | N/A | N/A | N/A | N/A | N/A
EXM 02 | Financial viability and Management | Payment of all invoices within 30 days | N/A | N/A | About 10 % of supplier paid long after 30 days. | All invoices paid within 30 days | All invoices paid within 30 days | N/A | N/A | N/A | N/A | Payment within 30 days of invoice | Payment within 30 days of invoice | Not all payments are made within 30 Days of Invoice. | Target Partially Met | Internal delays. | Draft payment procedure manual has been developed. | List of payments made.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 03 | Financial viability and Management | Payment of all invoices within 30 days | Management of expenditure | N/A | 100 % of payments to have EC approval | 100 % of payments to have EC approval | 100 % of payments to have EC approval | N/A | N/A | N/A | N/A | 100% of payments made to have EC approval | 100% of payments made to have EC approval | 100% of payments made have EC approval. | Target Met | N/A | N/A | Payment files.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 04 | Financial viability and Management | Management of General insurance fund | Management of claims by ensuring that all claims honoured are valid | N/A | 100 % of claims are properly assessed | 100 % of claims are properly assessed | 100 % of claims to have legal approval and assessor approval | N/A | N/A | R17m | N/A | 100% of claims are properly assessed prior to payment | 100% of claims are properly assessed prior to payment | 100% of claims are assessed prior to payment. | Target Met | N/A | N/A | Insurance claims.
[5 empty] | All claims to have legal opinion and assessor report | All claims to have legal opinion and assessor report |  | N/A | Various | N/A |  | All claims to have legal opinion and assessor report | All claims to have legal opinion and assessor report | All claims have legal opinion and assessor report. | Target Met | N/A | N/A | Insurance claims.
EXM 05 | Financial viability and Management | Management of General insurance fund | Prepare monthly reports on insurance claims to Council | N/A | Monthly reports are prepared and presented | Monthly reports | 12 Reports per annum | N/A | N/A | N/A | N/A | 3 | 3 | 3 | Target Met | N/A | N/A | Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 06 | Financial viability and Management | Management of General insurance fund | Operationalisation of the insurance bank account | N/A | Bank account not utilised | All receipts of insurance and payments go through the insurance bank account | 100 % of insurance transactions go through this account | N/A | N/A | N/A | N/A | Transfer sufficient funds monthly | Transfer sufficient funds monthly | Funds are transferred per cash flow requirement. | Target Met | N/A | N/A | Insurance report.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 07 | Financial viability and Management | Remuneration Management | All salaries are paid on due date. There are sufficient funds to pay salaries on a monthly basis. | N/A | Salaries are paid on the 24th each month | Salaries to be paid by 24th each month. Other statutory payments by the 7th of the following month. | 100 % compliance | N/A | N/A | N/A | N/A | 3 payments per month | 3 payments per quarter | 3 payments | Target Met | N/A | N/A | Payroll
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 08 | Financial viability and Management | Remuneration Management | Random Audit of staff | N/A | No Audits | Signed registers | All staff on our payroll sign register of verification once a year | N/A | N/A | N/A | N/A | 25% of staff verified | Next 25% of staff verified | 25% | Target Met | N/A | N/A | Register.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 09 | Financial viability and Management | MFMA compliance | Ensure compliance with all MFMA requirements | N/A | Audit report for 2010-2011 with irregular expenditure, fruitless expenditure and wasteful expenditure | Reduction in fruitless and wasteful expenditure by recovering 100 % of fruitless expenditure from responsible parties | 0 qualifications due to expenditure section | N/A | N/A | N/A | N/A | 100 % compliance | 100 % compliance | 100% Compliance | Target Met | N/A | N/A | Report on Fruitless and Wastefull Expenditure.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 10 | Financial viability and Management | MFMA compliance | Budget planning in terms of MFMA | N/A | Section budget not completed and submitted timeously | Credible sectional budget prepared and sent on time | Budget input submitted to budget office by November each year | N/A | N/A | N/A | N/A | N/A | 100% budget input | 100% budget input. | Target Met | N/A | N/A | Draft budget submission.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 11 | Financial viability and Management | Development of Financial Policy | Develop a new financial regulations in line with treasury regulations, MFMA, council resolutions etc | N/A | Outdated financial regualations issued in 2005 | New regulations approved by council resolution | Council resolution on new policies adopted by 30 September 2012 | N/A | N/A | N/A | N/A | 100% Review of Financial Regulations | N/A | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXM 12 | Financial viability and Management | Financial Management Systems | Sourcing of the new FMS to deal with the legacy | N/A | 41 Different systems | 1 System | 1 System | 11 000 000 | N/A | N/A | Council | 20% | 50% | 25% | Target Partially Met | NT Circular 57 requirements. | Follow up with NT. | Bid Spec Report.
[8 empty] | N/A | N/A | N/A |  | R3m | R4m | N/A | N/A | N/A | N/A | N/A
EXM 13 | Financial viability and Management | Leave Management | Automation of employee records | N/A | Leave managed manually leading to inefficiencies | Payday fully utilised to manage leave | Payday fully utilised to manage leave | N/A | N/A | N/A | N/A | Monthly reports on leave liability | Monthly reports on leave liability | Report being circulated. | Target Met | N/A | N/A | Leave Liability Report.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## REV MGT overview
REVENUE MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | REVENUE MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 13
| 1.1.1 | OPERATING PROJECTS | 13
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Revenue
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.3 REVENUE MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
RVM 01 | Financial Viability and Management | Credit Control and billing | Reduction in estimates | All | 71% of meters read | 90% of meters read | % of meters read | N/A | N/A | N/A | Nil Required | 75% of meters read | 80% of meters read | 52% meters read |  | Target Partially Met | Not all meter readers according to the plan were employed and 4 have left | Introducing the parallelsystem | meteer reading report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RVM 02 | Financial Viability and Management | Credit Control and billing | Accurate billing of rates | All | 85% accuracy of billing iro rates | 100% accurate billing iro rates | % of accurate billing iro rates | N/A | N/A | N/A | Nil Required | 90% accurate billings ito names | 93% accurate billings ito names | 93% correct bills are being sent |  | Target Met | N/A | N/A | Monthly billing returns register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RVM 03 | Financial Viability and Management | Credit Control and billing | Debtors | All | 80% debt collection | 100% debt collection | % of Debt collection | N/A | N/A | N/A | Nil Required | 85% debt collection | 90% debt collection | The debt has not changed and improverment is expected as the year commences , We have secured significant PTP from DPW for outstanding debtors |  | Target Partially Met | Unclean debtors book | Debtor book cleansing plann and the most part of it is inflated. | debtors age analysis report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RVM 04 | Financial Viability and Management | Credit Control and billing | Database clean-up | All | 14 000 accounts | 14 000 returned mail accounts delivered to consumer | Number of accounts cleaned | N/A | N/A | N/A | Nil Required | 4000 consumers reached | 4000 consumers reached | 4000 target reached |  | Target Met | N/A | N/A | Mothly bills teutrns register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RVM 05 | Financial Viability and Management | Policies | Credit Control & Debt Collection Policy | All | 2013-05-31 | Review Credit Control & Debt Collection policy by 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Required | N/A | Draft Completed | Reviwed Draft completed |  | Target Met | N/A | N/A | draft report and Minutes
[13 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RVM 06 | Financial Viability and Management | Policies |  | All | 2012-05-31 | 100% Implementation and monitoring of the Credit Control & Debt Collection policy | 100% Implementation and monitoring of the Credit Control & Debt Collection policy | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of the Credit Control & Debt Collection policy | Disconnection of overdue accounts | Most of overdue accounts were disconnected |  | Target Partially Met | Most contractors were on holiday | Update the disconnection accounts and hand over for disconnection. | Disconnections register
RVM 07 | Financial Viability and Management | Policies | Tariff Policy | All | 41425 | Review Tariff Policy by 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Required | N/A | Review plan is underway | Draft complete |  | Target Met | N/A | N/A | draft tariff policy
[8 empty] | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RVM 08 |  |  |  | All | 2012-05-31 | 100% Implementation and monitoring of Tariff Policy | % implementation and monitoring of Tariff Policy | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Tariff Policy | 100% Implementation and monitoring of Tariff Policy | Draft Procedure manual complete |  | Target Met | N/A | N/A | procedure manual
RVM 09 | Financial Viability and Management | Policies | Rates Policy | All | 2013-05-31 | Review Rates policy by the 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Required | N/A | Draft Completed | Draft policy complete |  | Target Met | N/A | N/A | draft Review Rates policy
RVM 10 | Financial Viability and Management | Policies |  | All | 2012-05-31 | 100% Implementation and monitoring of Rates policy | % Implementation and monitoring of Rates Policy | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Rates policy | 100% Implementation and monitoring of Rates policy | Reviewed Draft Policy Manual |  | Target Partially Met | it will be implemented after Mid year budget review | adoption of Rates policy | draft Review Rates policy
RVM 11 | Financial Viability and Management | Policies | Indigent Policy | All | 2013-05-31 | Review Indigent policy by 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Required | N/A | N/A | Dratft complete for council adoption |  | Target Met | N/A | N/A | reviewed draft indigent policy
RVM 12 |  |  |  | All | 2012-05-31 | 100% Implementation and monitoring of Indigent policy | % Implementation and monitoring of Indigent policy | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Indigent policy | 100% Implementation and monitoring of Indigent policy | Indigent register is currently being updated |  | Target Partially Met | Had to be preceded by changes in the policy | In progress | updated indigent policy
RVM 13 | Financial Viability and Management | Policies | Indigent Register | All | 2012-07-01 | 100% Implementation and monitoring of Indigent register | % Implementation and monitoring of Indigent register | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Indigent register | 100% Implementation and monitoring of Indigent register | Draft policy complete |  | Target Partially Met | Awaiting for final adoption in mid year budget review | In progress | indigent register

## SCM overview
SUPPLY CHAIN MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | SUPPLY CHAIN MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 11
| 1.1.1 | OPERATING PROJECTS | 11
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## SCM
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.4 SUPPLY CHAIN MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
SCM 01 | To promote sound financial management and reporting, effective budgeting & revenue enhancement | Supply Chain Management | Annual Procurement Plan | N/A | 30/09/2011 | Approved Procurement Plan by 30 June 2013 | Date of approval of procurement plan | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 02 | To promote sound financial management and reporting, effective budgeting & revenue enhancement | Supply Chain Management | Annual Procurement Plan | N/A | Nil | Implementation and monitoring of the Annual Procurement Plan | Implementation and monitoring of the Annual Procurement Plan | N/A | N/A | N/A | Nil Required | Implementation of the Annual Procurement Plan | Implementation of the Annual Procurement Plan | Implementation of the Annual Procurement Plan |  | Target Partially Met | shut down period in december affected the awarding process as contracts could not furnish the insurance documents to finalise the awarding process | letters sent to contractors to fast track the insurances. | contract register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 03 | To promote sound financial management and reporting, effective budgeting & revenue enhancement | Supply Chain Management (SCM) | SCM Policy Review | N/A | 30/05/2012 | Adopted reviewed SCM Policy by 30/09/2012 | Date of approved reviewed SCM Policy | N/A | N/A | N/A | Nil Required | Adopted reviewed SCM Policy by 30/09/2012 | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 04 | To promote sound financial management and reporting, effective budgeting & revenue enhancement |  | SCM Policy Implementation | N/A | 30/07/2012 | (1) 100% Implementation and monitoring of SCM Policy | % Implementation of SCM Policy | N/A | N/A | N/A | Nil Required | Implementation and monitoring of SCM Policy | Implementation and monitoring of SCM Policy | Implementation and monitoring of SCM Policy |  | target met | N/A | N/A | SCM Policy
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 05 | To promote sound financial management and reporting, effective budgeting & revenue enhancement |  |  | N/A | N/A | (2) favourable audit report | Auditor General favourable audit report | N/A | N/A | N/A | Nil Required | compliance with SCM Policy | compliance with SCM Policy | compliance with SCM Policy |  | target partially met | contract management the process of contract monitoring was initiated late in April 2012 however this will not affect the 12/13 audit report and irregular expenditure | contract management the process of contract monitoring was initiated late in April 2012 however this will not affect the 12/13 audit report and irregular expenditure | audit report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 06 | To promote sound financial management, effective budgeting & revenue enhancement | Supply Chain Management | Inventory management | N/A | 1/07/2011 | All purchases to comply with SCM policy according to the value for money principle. | All purchases to comply with SCM policy according to the value for money principle. | N/A | N/A | N/A | Nil Required | All purchases to comply with SCM policy according to the value for money principle. | All purchases to comply with SCM policy according to the value for money principle. | All purchases to comply with SCM policy according to the value for money principle. |  | target met | N/A | N/A | inventory management
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 07 | To promote sound financial management, effective budgeting & revenue enhancement |  | Just in Time Purchasing | N/A | 2011-07-01 | 100% curb Fruitless & wasteful expenditure | 100% curb Fruitless & wasteful expenditure | N/A | N/A | N/A | Nil Required | curb Fruitless & wasteful expenditure | curb Fruitless & wasteful expenditure | curb Fruitless & wasteful expenditure |  | target met | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 08 | To promote sound financial management, effective budgeting & revenue enhancement |  | Inventory management | N/A | 2011-07-01 | Efficient, Effective & cost contained service delivery to communities | 5 day customer turn-around time | N/A | N/A | N/A | Nil Required | 5 day customer turn-around time | 5 day customer turn-around time | 5 day customer turn-around time |  | target met | N/A | N/A | inventory management
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM 09 | To promote sound financial management, effective budgeting & revenue enhancement | Supply Chain Management | Bid Processing | N/A | 120 days | Bid time processing not to exceed the stipulated time, 7 day quatation 21 days turnaround time, competitive bidding 75 days turnaround time | Bid time processing not to exceed the stipulated time, 7 day quatation 21 days turnaround time, competitive bidding 75 days turnaround time | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM10 | To promote sound financial management, effective budgeting & revenue enhancement | Supply Chain Management | Reporting | N/A | N/A | 4 Quaterly report on tenders awarded submitted to Council within 10 days after the monthends | 4 Quaterly report on tenders awarded submitted to Council within 10 days after the monthends | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM11 | To promote sound financial management, effective budgeting & revenue enhancement | Supply Chain Management | Reporting | N/A | 2011-06-30 | 1 X Implementation and monitoring of SCM policy report submitted to FPC,EXCO and Full Council annually | 1 X Implementation and monitoring of SCM policy report submitted to FPC,EXCO and Full Council annually | N/A | N/A | N/A | Nil Required | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[6 empty] | SCM Reg 6 (2) (a) (i) | SCM Reg 6 (2) (a) (i) | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## COMM SERV COVER
ANNEXURE 1 (G): COMMUNITY SERVICES BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
SDBIP 2012/2013

## COMM SERV overview
COMMUNITY SERVICES BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | COMMUNITY SERVICES BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 76
| 1.1.1 | OPERATING PROJECTS | 74
| 1.1.2 | CAPITAL PROJECTS | 2
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## ABM overview
AREA BASED MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (MONTH 5 - NOVEMBER 2012) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
1 | AREA BASED MANAGEMENT UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 12
1.1.1 | OPERATING PROJECTS | 12
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## ABM
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.1 AREA BASED MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012 | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012 | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
ABM 01 | Good Governance Public Participation | Community Participation | Public Participation Policy | All | N/A | PP Policy adopted by 30/9/12 | Date of approval | N/A | N/A | N/A | Nil Required | 30/09/2012 | N/A | N/A | Not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABM 02 | Good Governance Public Participation | Community Participation |  |  | N/A | 100% Implementation of Public Participation & monitoring Policy | % Implementation | N/A | N/A | N/A | Nil Required | N/A | 100% Implementation of Public Participation & monitoring Policy | 100% Implementation of Public Participation & monitoring Policy | Target Partially met | Only institutionalisation projects have been collected. Workshoping of ward committees will happen on the in february, march & appril. | ongoing | Institutionalisation of paerticipation projects file
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABM 03 | Good Governance Public Participation | Community Participation | Complaints Reporting referral & community feedback | All | It takes 2 months for complaints by depts to address. | 100% Complaints referred to relevant dept for actioning within 5 days | % of complaints referred | N/A | N/A | N/A | Nil Required | 100% complaints addressed within 20 days | 100% complaints addressed within 15 days | 75% complaints addressed within 15 days. (30 addressed within 15 days from 40 queries received) | Target Partially met | Departments don’t have capacity to attend to some queries. | To encourage departments to attend to queries | Spreedsheet file
[7 empty] | Turn around time of complaints addressed by departments | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABM 04 | Good Governance Public Participation | Community Participation | Community based planning | 10,11,12,20,22. | 28 wards have no plans. | Completed 28 ward plans by 30/06/2013 | 9 plans completed by date. | N/A | N/A | N/A | Nil Required | Strategy development & administration by 30/09/12 | Research Surveys completed by 31/12/2012 | N/A | Not Applicable | Cogta training of ABM managers will take place on the 14 to 19 of January 2013 | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABM 05 | Good Governance Public Participation | Community Participation | Institutionalization of Particpation | All | N/A | Community Participation Programme Adopted by 30/12/2012 | Programme implemented by 31/03/2013 | N/A | N/A | N/A | N/A | Develop programme | Adoption of programme by SMC | Programme was developed & send to SMC which requested a detailed programme. | Nil Achieved | A detailed programme was demanded by SMC. | Detailed Programme to be sent to SMC but avoid clash with CBP implementation plan in Jan 2013. | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABM 06 | Basic Service Delivery | Community Participation | Conduct Ward audits | All | No ward audits | 37 ward audits completed by 30/09/2012 | 37 ward audits completed by 30/09/2012, reviewed& updated quartely | N/A | N/A | N/A | Nil Required | 37 ward audits completed by 30/09/2012 | Ward audits reviewed & updated quarterly | Ward audits reviewed & updated quarterly | Target met | N/A | N/A | Ward Audits file
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABM 07 | Good Governance Public Participation | Community Participation | Monitor functioning of war rooms | All | No tool to monitor functioning of War Rooms | Develop tool to monitor functioning of war rooms by 30/09/2012 | Developed tool to monitor functioning of war rooms | N/A | N/A | N/A | Nil Required | Develop tool to monitor functioning of war room by 30/09/2012 | Implement tool to monitor functioning of war rooms | Implement tool to monitor functioning of war rooms | Target met | N/A | N/A | Tool for war room functionality. War Room reports file
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABM 08 | Good Governance Public Participation | Community Mobilisation | Loudhailing | All | Councillor's scheduled meeting | 111 of loud hailing done | 444 loud hailings done | N/A | N/A | N/A | Nil Required | 111 loud hailing scheduled community meetings done | Do scheduled community meetings loudhailing as requested by ward councillrs | 5 requests received and 5 completed. | Target met | N/A | N/A | Loudhailing requests file
ABM 09 | Good Governance Public Participation | Community Participation | Vulindlela Rural Development Strategy | 1 to 9 | No Rural Strategy | Rural Development Strategy for Vulindlela | Developed Rural Strategy by 31/06/13 | N/A | N/A | N/A | Nil Required | Research done | Compile information into document | Strategy approved by SMC | Target exceeded | N/A | N/A | Draft Trural Strat File
ABM 10 | Good Governance Public Participation | Community Participation | Review ABM management boundaries | All | 5 Outdated ABM management boundaries | Consistant adopted ABM boundaries by 30/06/13 for 5 Areas | All 5 areas having developed boundaries | N/A | N/A | N/A | Nil Required | Review ABM boundaries | Submit report to MANCO for approval | Reviewal of ABM boundaries was approved by full council | Target met | N/A | N/A | ABM Boundaries file
ABM 11 | Good Governance Public Participation | Community Participation | Conduct IDP Budget need survey | All Council Izimbizos | Outdated completed Izimbizo Budget/IDP survey | Completed IDP/Budget needs survey completed | IDP/Budget needs survey completed | N/A | N/A | N/A | Nil Required | N/A | Conduct Budget/IDP izimbizo survey | Budget/IDP izimbizo survey conducted | Target met | N/A | N/A | Budget/IDP Izimbizo survey file
ABM 12 | Good Governance Public Participation | Community Participation | War room monthly reports | All | Inconsistant reports | Submission of monthly reports from each war rooms | Monthly report for each war room submitted | N/A | N/A | N/A | Nil Required | 111 Reports produced | 37 war room Reports produced | 15 war room reports produced | Nil achieved | War rooms stakeholders mostly were on holiday ( on leave) | ABM to Rearrange meetings for quarter 3 | War Room reports file

## HS SS overview
HEALTH & SOCIAL SERVICES UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
1 | HEALTH & SOCIAL SERVICES UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 24
1.1.1 | OPERATING PROJECTS | 24
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Health & Social Serv
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.2 HEALTH & SOCIAL SERVICES
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
HIV 01 | Social and Economic Development | HIV&AIDS | Community Counselling Course | All wards | 9 | 12 Counselling Course sessions Conducted | Number of counseling Course conducted | N/A | N/A | N/A | N/A | 3 Counselling Course sessions Conducted | 3 Counselling Course sessions Conducted | 3 Counselling Course sessions Conducted |  | Target Met | N/A | N/A | Counselling Course Registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 02 | Social and Economic Development |  | Community Peer Education Training | Not available, dependent on requests | 4 | 6 Peer Education training Conducted | Number of Peer Education Training conducted | N/A | N/A | N/A | N/A | 1 Peer Education training Conducted | 2 Peer Education training Conducted | 2 Peer Education training Conducted |  | Target Met | N/A | N/A | Peer education training registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 03 | Social and Economic Development |  | Community Awareness campaigns | Not available, dependent on finalized year plan. | 3 | 5 Community Awareness campaigns conducted | Number of campaigns conducted | N/A | N/A | N/A | N/A | 1 Community Awareness campaign conducted | 1 Community Awareness campaign conducted | 4 Community Awareness campaign conducted |  | Target Exceeded | N/A | N/A | Attendance Registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 04 | Social and Economic Development |  | Condom Distribution Outlets | 1;3;4;6;7;8;9;14;16;17;19;21;26;29;31;32;33;36 & 37 | 18 | Additional 19 wards with condom distribution outlets | number of Wards with Condom Distribution outlets | N/A | N/A | N/A | N/A | Additional 4 wards with condom distribution outlets | Additional 5 wards with condom distribution outlets | Additional 7 wards with condom distribution outlets (Wards 2, 10, 13,15, 18, 22, 30) |  | Target Exceeded | N/A | N/A | HIV/AIDS register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 05 | Social and Economic Development |  | Home Based Care Groups | All wards | 33 | Additional 4 wards with fully functioning Home Based care groups | Number of wards with fully functioning Home Based care groups | N/A | N/A | N/A | N/A | NA | Additional 2 wards with fully functioning Home Based care groups | Additional 3 wards (27, 28, 30) with fully functioning Home Based care groups |  | Target Exceeded | N/A | N/A | Attendance Registers
[8 empty] | N/A | N/A | N/A |  | NA | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 06 | Social and Economic Development |  | Local AIDS Council meetings | N/A | 4 LAC meetings held | 4 LAC meetings Held in the year. | Number of LAC meetings conducted | N/A | N/A | N/A | N/A | 1 LAC meeting Held | 1 LAC meeting Held | 2 LAC meeting Held |  | Target Exceeded | N/A | N/A | LAC meeting minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 07 | Social and Economic Development |  | Training of Councillors Ward and PR Amakhosi and Izinduna | All wards | Nil | 89 Ward and PR Councillors, Amakhosi and Izinduna trained | Number of Ward and PR Councillors, Amakhosi and Izinduna trained | N/A | N/A | N/A | N/A | 22 Ward and PR Councillors, Amakhosi and Izinduna trained | 23 Ward and PR Councillors, Amakhosi and Izinduna trained | 16 Ward & PR councillors trained |  | Target Partially Met | Poor Attendance from Councillors | Work with Speaker's office to ensure Councillors attend training courses | Attendance Registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 08 | Social and Economic Development |  | Ward AIDS Committees | All wards | 25 | 16 additional Ward AIDS Committees fully functional | Number of new Ward AIDS Committees in place | N/A | N/A | N/A | N/A | 4 additional Ward AIDS Committees fully functional | 4 additional Ward AIDS Committees fully functional | 04 additional Ward AIDS Committees (1, 2, 7, 13,) fully functional |  | Target met | N/A | N/A | Attendance Registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 09 | Social and Economic Development |  | Ward AIDS Strategy | All | Nil | Adopted Ward AIDS Strategy by the 31 July 2012 | Date of adoption of Ward AIDS Strategy | N/A | N/A | N/A | N/A | Adopted Ward AIDS Strategy by the 31 July 2012 | N/A | N/A |  | Not Applicable | Strategy was adopted at Full Council on the 31/10/2012 | N/A | Full Council Resolution 31/ 10 / 2012
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIV 10 | [5 empty] | 100% Implementation of Ward AIDS Strategy by the 30 September 2012 | % Implementation of Ward AIDS Strategy | N/A | N/A | N/A | N/A | NA | 100% Implementation of Ward AIDS Strategy | The Five Task Teams: (I). Awareness and Prevention: Carried out in Wards by members of HIV & AIDS Unit and other NGOs e.g. Lifeline, Child line and Hospice. (II) Sustaining Health and Wellness: Data base has been started. (III) Protection of Human Rights database almost completed : (IV)Reducing structural vulnerability : Nil done. (V) Monitoring and Evaluation: Started collecting the tools that various stakeholders use to enable a friendly data collection tool to be formulated. | Initial Implementation Meeting held on the 14/11/2012 | Target Partially Met | Task Team IV: Unable to coordinate a meeting with stakeholeders due to them being busy with preparations for World AIDS DAY and going on vacation. | To schedule a meeting when all stakeholder are available. | Attendance registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 03 | Social and Economic Development |  | Air Pollution Control | 12; 22; 23; 24; 26; 29; 33; 35 ; 36 | 120 premises inspected annually | 120 premises to be inspected annually | Number of premises inspected annually | N/A | N/A | N/A | Nil Required | 30 premises to be inspected | 30 premises to be inspected | 33 premises inspected |  | target exceeded | N/A | N/A | Property Files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 04 | Social and Economic Development |  | Water Quality Control | All wards | 900 samples taken/ analyzed annually | 19, 25,28 samples taken weekly on a rotation | Number of samples taken weekly from reservoirs/ consumer points | 40 000 | n/a | nil | Council | 225 samples taken weekly on a rotation | 225 samples taken weekly on a rotation | 324 samples taken |  | target exceeded | N/A | N/A | Water sampling Files
[8 empty] | 3471001030 |  |  |  | 10 000 | 10 000 | N/A | N/A | N/A | N/A | N/A | N/A
EHS 05 | Social and Economic Development |  | Food Quality Control | All wards | 1600 premises inspected annually | 1600 premises inspected annually | Number of premises inspected annually | N/A | N/A | N/A | Nil Required | 400 premises inspected | 400 premises inspected | 366 premises inspected |  | target partially met | staff on leave during November and December (compulsory) | inspections of food premises to be prioritized in 3rd quarter to make up deficit | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 06 | Social and Economic Development |  | Food Sampling | All wards | 360 food samples and 120 swabs taken/ analyzed annually | 90 food samples and 30 swabs to be taken/ analyzed quarterly | Number of Samples taken quarterly | 40 000 | n/a | nil | CNL | 90 food & 30 swabs to be taken/ analyzed quarterly | 90 food & 30 swabs to be taken/ analyzed quarterly | 70 food samples and 70 swabs taken |  | target partially met | staff on leave during November and December (compulsory) | additional food samples to be taken in 3rd quarter to make up deficit | Property files
[8 empty] | 3471001030 | N/A | N/A |  | 10 000 | 10 000 | N/A | N/A | N/A | N/A | N/A | N/A
EHS 07 | Social and Economic Development |  | Vector Control | All wards | 1200 sites Baited/ Treated annually | 1200 sites annually: 100 sites baited, treated monthly | Number of sites treated annually | 70 000 | N/A | N/A | Council | 300 (100 sites baited, treated monthly) | 300 (100 sites baited, treated monthly) | 254 sites baited |  | target partially met | staff on leave during November and December (compulsory) | additional sites to be baited/treated in 3rd quarter to make up deficit | Vector control files
[8 empty] | 3471001560 | N/A | N/A |  | 17 500 | 17 500 | 24 407.50 |  | N/A | N/A | N/A | N/A
EHS 08 | Social and Economic Development |  | Public Complaint investigations | All wards | Investigate and finalize complaints | 100% Investigations within turnaround time of 1 to 5 days | % investigated within 1 to 5 days | N/A | N/A | N/A | Nil Required | 100% Investigations within turnaround time of 1 to 5 days | 100% Investigations within turnaround time of 1 to 5 days | 89 % of 215 complaints received were investigated within turnaround time |  | target partially met | staff on leave during November and December (compulsory) | stricter controls to ensure turn around time is met | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 09 | Social and Economic Development |  | Health Care Risk Waste Control | All wards | 480 premises inspected annually | 480 premises inspected annually | Number of Inspections/ Registrations annually | N/A | N/A | N/A | Nil Required | 120 (40 Inspections/ Registrations monthly) | 120 (40 Inspections/ Registrations monthly) | 83 inspections |  | target partially met | staff on leave during November and December (compulsory) | stricter controls to ensure target is met | Health care risk waste files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 10 | Social and Economic Development |  | Tobacco Control | All wards | 1680 premises inspected annually | 1680 premises inspected annually | Number of Inspections annually | N/A | N/A | N/A | Nil Required | 420 (140 Inspections monthly) | 420 (140 Inspections monthly) | 434 premises inspected |  | target met | N/A | N/A | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 11 | Social and Economic Development |  | Places of Care | All wards | 240 premises inspected annually | 240 premises to be inspected | Number of Inspections/ Registrations annually | N/A | N/A | N/A | Nil Required | 60 (20 Inspections/ Registrations monthly) | 60 (20 Inspections/ Registrations monthly) | 110 premises inspected |  | target exceeded | N/A | N/A | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 12 | Social and Economic Development |  | Funeral Undertakers; cemeteries and crematoria Control | All wards | 30 premises inspected annually | 30 premises inspected annually | Number of Inspections/ Registrations annually | N/A | N/A | N/A | Nil Required | 8 Inspections/ Registrations quarterly | 8 Inspections/ Registrations quarterly | 9 premises inspected |  | target met | N/A | N/A | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 13 | Social and Economic Development |  | Health Surveillance of commercial, industrial and residential premises | All wards | 800 premises inspected annually | 800 premises inspected annually | Number of premises inspected annually | N/A | N/A | N/A | Nil Required | 200 premises inspected | 200 premises inspected | 568 premises exceeded |  | target exceeded | N/A | N/A | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 14 | Social and Economic Development |  | Communicable Disease Control | All wards | Investigate and finalise disease notifications | 100% investigations within a turnaround time of 1 to 5 days | % investigated within 1 to 5days | N/A | N/A | N/A |  | 100% investigations within a turnaround time of 1 to 5 days | 100% investigations within a turnaround time of 1 to 5 days | 81 % of 138 notifications investigated |  | target partially met | vehicles not available, during November and December (at workshop) | workload to be shared amongst practitioners and assistants in 3rd quarter | CDC files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 15 | Social and Economic Development |  | Health Education/ Promotion | All wards | 60 programs annually | Conduct 60 health education/ promotion programs annually | Number of programmes annually | N/A | N/A | N/A | Nil Required | Conduct 15 health education/ promotion programs | Conduct 15 health education/ promotion programs | 87 health education programs/promotions conducted |  | target exceeded | N/A | N/A | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EHS 16 | Social and Economic Development |  | Compliance and Enforcement Measures | All wards | Follow up and finalize all notices and prosecutions | 100% Notices/ summonses issued when contraventions occur | % summonses issued when contraventions occur | N/A | N/A | N/A | Nil Required | 100% Notices/ summonses issued when contraventions occur | 100% Notices/ summonses issued when contraventions occur | 147 notices and 7 summons issued - 100 % in terms of compliance and enforcement measures |  | target met | N/A | N/A | Property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Comm DEv overview
COMMUNITY DEVELOPMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT | SDBIP 2012/2013 QUARTER 2 (MONTH 5 - NOVEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | AIRPORT, CREMATORIA, ART GALLERY, CEMETERIES UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 27
| 1.1.1 | OPERATING PROJECTS | 25
| 1.1.2 | CAPITAL PROJECTS | 2
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Community Development
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.3 COMMUNITY DEVELOPMENT (LIBRARIES, ART GALLERIES, CREMATORIA & CEMETERIES, PARKS, COMMUNITY FACILITIES, WASTE MANAGEMENT, LANDFILL SITE)
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LBS 01 | Basic Service Delivery | Library Services | To assess and develop a maintainance plan for libraries | 12,35,28,32,34,37,27,36 | 9 Libraries | 9 Libraries maintained | Number of Libraries maintained | 3 000 000 | N/A | N/A | Council/ Arts & Culture | Assessment Completed. Maintance plan developed. | 3 Libraries maintained as per assessment | Costing for 9 libraries has been done (2 out of the 9 libraries were partially maintained) | Nil Achieved | Budget reallocation | Budget reallocation approval | Maintainance Plan
[8 empty] | 513 100 | N/A | N/A |  | N/A | 1 000 000 | N/A | N/A | N/A | N/A | N/A
LBS 02 | Basic Service Delivery | Library Services | Purchasing of books & processing material | 12,35,28,32,34,37,27,36 | 15000 -2011/2012 6Rolls of material | Processing material and books purchased | number of books purchased per acquisition dept. | 1 700 000 | N/A | N/A | Council/ Arts & Culture | book selection process | Purchase of books and internet connectivity | Preparing specs for tender process | Target Partially Met | Change of purchasing books as per directive from treasurer | New system to purchase books | Bid specification doc.
[8 empty] | 5131001643 | N/A | N/A |  | N/A | 1 700 000 | N/A | N/A | N/A | N/A | N/A
TAG 01 | Art & Culture Community out Reach Programme | Art & Culture Community out Reach Programme | Arts Exhibitions | N/A | 12 | Conducted 8 exhibitions per annum | Number of Exhibitions | 693 000 | N/A | N/A | Council & Prov Arts & Culture Department | 2 x Art Exhibitions Conducted | 2 x Art Exhibitions Conducted | 2 Art Exhibitions conducted | Target Met | N/A | N/A | Art Exhibitions programme
[8 empty] | 4804668337 | N/A | N/A |  | 173 250 | 173 250 | N/A | N/A | N/A | N/A | N/A
PKS 01 | Basic Service Delivery | Grass Cutting | City Grass Cutting | All | Once every four months | Cut grass four times a year as per annual schedule per surburb | Number of Cuts per surburb |  | N/A | N/A | Council & Cogta | One cut per surburb per quarter | One cut per surburb per quarter | One cut per surburb per quarter | Target Met | N/A | N/A | Daily stats Monitoring performance template
[8 empty] | 402404412 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 02 | Basic Service Delivery | Development of new parks. | Two Parks in Greater Edendale | Greater Edendale | 16 community parks zero parks in edendale and vulindlela | Develop Busines plan for the establishment of two parks in Greater Edendale | Completed Business Plan for the establishment of two parks in graeter edendale | N/A | N/A | N/A | Nil Required | Consultation with stakeholders | Draft Business plan and submit to MANCO | Approved by SMC. Awaiting decision from portfolio committee,exco | Target Met | N/A | N/A | Business Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKS 03 | Basic Service Delivery | Parks | maintainance and rehabilitation of the regional park. | 27 | 1 regional park delapidated alexandra regional park. | Revitalization business plan completed by December 2012 | Completed business plan by December 2012 | N/A | N/A | N/A | Nil Required | First draft completed and submitted to MANCO | Final draft completed and submitted to premiers office for funding application | Business Plan submitted to SMC | Target Met | N/A | N/A | Business Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKS 04 | Basic Service Delivery | Parks | Traffic islands and city entrances beautified | All | 10 traffic islands and main entrances into the city require landscaping and Maintenance | Landscape and maintenance of 10 traffic islands and main entrances as per annual schedule (seasonal) | Number of traffic islands and main entrances maintained |  | N/A | N/A | Council | 10 traffic islands and main entrances landscaped and maintained | 10 traffic islands and main entrances landscaped and maintained | 10 Traffic islands maint ained only not landscaped | Target Partially Met | Delay in acquisition of seedlings | Procurement must fast track the process | RTP for seedlings
[8 empty] | 402404412 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 05 | Basic Service Delivery | Community facilities | Halls | All | Sixty halls requiring Maintenance | Develop Maintenance plan for sixty halls | Completed maintenance plan for sixty halls | N/A | N/A | N/A | Nil Required | Completed maintenance plan for 60 halls | identify savings during mid year review and implement plan. | Master plan for maintenanco e sumitted to SMC | Target Met | N/A | N/A | Master Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKS 06 | Basic Service Delivery | Community facilities | Sport facilities | All | Sixty five sports facilities requiring Maintenance | Develop Maintenance plan for sixty five Sports facilities. | Completed maintenance plan for sixty five Sports facilities. | N/A | N/A | N/A | Nil Required | Completed maintenance plan for sixty five Sports facilities. | Identify savings during mid year review and implement plan. | Master plan for maintenanco e sumitted to SMC | Target Met | N/A | N/A | Master Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKS 07 |  | Sport Development | Msunduzi Sport and Recretion Plan | All | 20 Satellites | Develop Msunduzi Sport & Recreation Plan | Completed Msunduzi sport & Recreation Plan | N/A | N/A | N/A | Nil Required | Analysis of National Sport & Recreation | Draft Msunduzi Sport and Recreation | To be submitted to SMC | Target Met | N/A | N/A | Sports PlanDevelopment
PKS 08 | Basic Service Delivery | Community facilities | Athletics track | All | No athletic track in Msunduzi | Completed constuction of Athletics track for Msunduzi (phase 1) | Completed athletics track 30 June 2013 | N/A |  | N/A | Dept. sports and Recreation -MIG Funding | Eartworks completed | Fencing and drainage completed | Concept design and specification still in progress. Second Phase | Target Met | N/A | N/A | Appointment letter to Consultant
[8 empty] | N/A | 4316411201 | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 09 | Basic Service Delivery | Community facilities | Winston Churchill theatre | All | Currently under construction | Develop and Implement annual operational Plan for Winston Churchill theatre | Completed operational Plan | N/A | N/A | N/A | Nil Required | Research and Collation of data from other Municipalities | Identify savings during mid year review and implement Operational plan. | Draft agrreement proposed by Dept of Arts and Culture aproved by Exco | Target met | N/A | N/A | Exco resolution dated 19 Nov 2012
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKS 10 | Basic Service Delivery | Cemetries and Crematoria | Cremators | All | Three cremators (1 functional and 2 non-functional) | Purchase of two new cremators | Purchase of two new cremators by 30/12/2012 | N/A | 2 800 000 | N/A | Council | Completed Tender rocess and place order | Two new Cremators purchased and installed | N/A RSW21 | Target Partially Met | N/A RSW21 | N/A RSW21
[8 empty] | N/A |  | N/A |  | N/A | 2 800 000 | N/A | N/A | N/A | N/A | N/A
PKS 11 | Basic Service Delivery | Cemetries and Crematoria | Fencing of Cemeteries Plan | All | Mountain Rise, Azalea, Snathing and Community Cemeteries not fenced. | Develop business plan for the fencing of Cemeteries (as per the requirements of the Act) | Completed business Plan | N/A | N/A | N/A | Nil Required | Assesment of fencing at all cemeteries completed | Business plan developed and submitted to MANCO | Draft Business Plan to be submitted to SMC | Target Met | N/A | N/A | Business Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKS 12 | Basic Service Delivery | Cemetries and Crematoria | Cemeteries & Crematoria Sector Plan | All | Nil | Development of Crematoria | Completed business Plan | N/A | N/A | N/A | Nil Required | Bench Mark with Germiston and KwaDukuza fact Finding Mission | Draft of Cemeteries and Crematoria | Draft Business Plan to be submitted to SMC | Target Met | N/A | N/A | Business Plan
PKS 13 | Basic Service Delivery | Community facilities | Grading and Categorisation of venues(Sports facilities and halls) | All | 125 sport facilities and halls requires grading and Categorisation | Develop business plan to grade and Categorise 125 venues. | Completed Business Plan | N/A | N/A | N/A | Nil Required | Completed business plan for grading and catergorisation of 125 venues. | Identify savings during mid year review and implement plan. | To be submitted to Portfolio and Exco for resolution. | Target Met | N/A | N/A | Business Plan. Resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKS 14 | Basic Service Delivery | Community facilities | Harry Gwala sustainability Plan | All | Harry Gwala is not self sustainable | A sound sustainable Business plan for Harry Gwala developed. | Developed sustainable business Plan | N/A | N/A | N/A | Nil Required | Consultation with stakeholders by 30/9/2012 completed | Draft business plan completed |  | nil achieved | scope of work changed | Alexendra precint masterplan | report on HG sustainability plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMS 01 | Infrastructure & Basic Service Delivery | Cleansing | Domestic refuse collection | 10-37 | 83 994 houses weekly refuse collection | 94 073 houses collection 1x week | Number of households with weekly refuse collection | 230004 | N/A | 43 268 858 | Council | 93 994 households with weekly refuse collection | 94 073 households with weekly refuse collection | 83944 households with refuse collection | Target Met | N/A | N/A
[8 empty] | 182… | N/A | 1824698439 |  | 50571 | 50571 | N/A | N/A | N/A | N/A | N/A
WMS 02 | Infrastructure & Basic Service Delivery |  | Business refuse collection | 10-37 | 5 757 busineses weekly refuse collection | 5 757 businesses weekly refuse collection | Number of business with weekly refuse collection | 30000 | N/A | 20 778 254 | Council | 5 757 of business with weekly refuse collection | 5 757 of business with weekly refuse collection | 5757 of business with weekly refuse collection | Target Met | N/A | N/A | Consolidated billing
[8 empty] | 183… | N/A | 1834698046 |  | 7500 | 7500 | N/A | N/A | N/A | N/A | N/A
WMS 03 | Infrastructure & Basic Service Delivery |  | Street sweeping | 10-37 | 300 kms swept per quarter | 300 kms of street swept per quarter | kms of street swept per quarter | 178952 | N/A | N/A | Council | 300 kms of street swept per quarter | 300 kms of street swept per quarter | 100 km done | Target Met | N/A | N/A | Foremans stats
[8 empty] | 181.... | N/A | N/A |  | 44738 | 44738 | N/A | N/A | N/A | N/A | N/A
WMS 04 | Infrastructure & Basic Service Delivery | Integrated Waste Management | Garden refuse | 10-37 | 8 garden sites serviced daily | 8 garden sites serviced daily | Number | 30000 | N/A | N/A | Council | 8 garden sites serviced daily | 8 garden sites serviced daily | 4 garden sites serviced daily | Target Partially met | roll on roll off breakdown | workshop intervention | WMD records.
[8 empty] | 184... | N/A | N/A |  | 7500 | 7500 | N/A | N/A | N/A | N/A | N/A
WMS 05 | Infrastructure & Basic Service Delivery |  | Plan for Garden refuse sites income | All | Nil income | Revenue Plan for garden refuse sites adopted by December 2012. | Date of adoption of business plan | N/A | N/A | N/A | Nil | Draft report submitted to MANCO | Draft report submitted to Community Services Portfolio Committee & EXCO for adoption. | Draft report submitted to Community Services Portfolio Committee & EXCO for adoption. | nil achieved | targrt changed | to implement the SMC resolution as per report dated 03 Sept. 2012 | Report recommending closure of garden refuse sites.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMS 06 | Infrastructure & Basic Service Delivery |  | Illegal dumping | All | Unknown | Illegal dumping measured and reduced by 10% | * extent of illegal dumping; * reduced % in illegal dumping | 12496 | N/A | N/A | Council | Illegal dumping quantified and report submitted to MANCO | 3% reduction in illegal dumping | 3% reduction in illegal dumping | Target Met | N/A | N/A | WMD records..
[8 empty] | 187 | N/A | N/A |  | 3124 | 3124 | N/A | N/A | N/A | N/A | N/A
WMS 07 | Infrastructure & Basic Service Delivery |  | Education and awareness | All | Unknown | 104 education and awareness initiatives conducted (2 per week) | Number of initiatives conducted | 208 000 | N/A | N/A | Keep Pietermaritzburg Clean Association | 25 education and awareness initiatives conducted (2 per week) | 25 education and awareness initiatives conducted (2 per week) | 25 education and awareness initiatives conducted (2 per week) | Target Met | N/A | N/A | KPCA monthly report file
[9 empty] | N/A | N/A |  | 52 000 | 52 000 | N/A | N/A | N/A | N/A | N/A
WMS 08 | Infrastructure & Basic Service Delivery |  | Waste minimisation: Orange Bag Recycling Project | 25-37 | Currently operational in 5 wards | Increase the Orange Bag Recycling Project to 13 wards | Number of wards in which the recycling project is extended | N/A | N/A | N/A | Council/DAEA/private | Orange Bag Recycling Project increased by 1 ward | Orange Bag Recycling Project increased by 2 wards | Orange Bag Recycling Project increased by 2 wards | Nil Achieved | report not sent to SMC/OMC and stood down for the next SMC | Report to be sent in January for consideration | Report on orange bag recycling
[8 empty] | N/A | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
WMS 09 | Infrastructure & Basic Service Delivery |  | Integrated Waste Management Plan (IWMP) | All | District IWMP | IWMP Adopted by 30/3/13 | Date of adopted IWMP | N/A | N/A | N/A | Nil | Draft IWMP submitted to MANCO | Consultation on IWMP with relevant stakeholders | refuse collection and illegal dumping completed. | Target Partially Met | draftt being done as per MPAC instructions and following SMART principles. | to complete the draft by end of 31/01/2013 | UMDM IWMP - DRAFTand draft on refuse collection and street sweeping
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMS 10 | Infrastructure & Basic Service Delivery | Cleansing | Public Conveniences/Toilets | 27,32,33 | 29 conveniences | 29 conveniences operated daily | number of conveniences | 50004 | N/A | N/A |  | 29 conveniences operated daily | 29 conveniences operated daily | 29 convenience services daily | Target Met | N/A | N/A | Supervisors stats
[8 empty] | 181.... | N/A | N/A |  | 12501 | 12501 | N/A | N/A | N/A | N/A | N/A

## PS DM overview
PUBLIC SAFETY & DISASTER MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | PUBLIC SAFETY & DISASTER MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 13
| 1.1.1 | OPERATING PROJECTS | 13
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Public Safety Enf & Dis Mng
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.4 PUBLIC SAFETY ENFORCEMENT & DISASTER MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - OCTOBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
FDMS 01 | Basic Service Delivery | Fire Services | Business plan developed for Northdale Fire Station | 28,29,30,31,32,34,35 | No Fire Station in Northdale. | Business Plan submitted to Manco by 30/10/12 | Date of completed Business Plan | N/A | N/A | N/A | Nil Required | First draft compiled by 31/08/12 | Final Business Plan submitted to Manco by 31/10/12 | Final Business Plan submitted to Manco by 31/10/12 |  | Target Met | N/A | N/A | MANCO resolution on fire station
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 02 | Basic Service Delivery |  | Business plan developed for Fire Training facility. | Nil | Current training facility not to the Nat. Standard | Business Plan submitted to Manco by 30/11/12 | Date of completed Business Plan | N/A | N/A | N/A | Nil Required | First draft compiled by 30/09/12 | Final Business Plan submitted to Manco by 30/11/12 | Final Business Plan submitted to Manco by 30/11/12 |  | Target Met | N/A | N/A | Business plan
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 03 | Basic Service Delivery |  | Business Premises inspected as per Fire Bylaws and regulations. | All | 800 Businesses Premises inspected as per Fire Bylaws and regulations. | 800 Businesses Premises inspected as Fire Bylaws and regulations by 30/ 04/13 | Number of inspected Premises as per Fire Bylaws and Regulations | N/A | N/A | N/A | Nil Required | 200 Businesses Premises inspected as per Fire Bylaws and regulations. | 200 Businesses Premises inspected as per Fire Bylaws and regulations. | 218 |  | target exceeded | N/A | N/A | daily stats spreadsheet
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 04 | Basic Service Delivery | Fire Services | Major hazardous installation meetings | All | 36 Major hazardous installation meetings per annum | 36 Major hazardous installation meetings by 30/06/13 | Major hazardous installation meetings | N/A | N/A | N/A | Nil Required | 12 Major hazardous installation meetings per quarter | 6 Major hazardous installation meetings per quarter | 14 |  | Target Exceeded | N/A | N/A | nil
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 05 | Basic Service Delivery |  | Fire awareness sessions conducted to schools | All | 80 Fire awareness sessions conducted per annum | 80 schools fire awareness sessions conducted by 03/06/13 | Number of schools fire awareness sessions conducted. | N/A | N/A | N/A | Nil Required | 20 schools fire awareness sessions conducted | 20 schools fire awareness sessions conducted | 14 |  | target partially met | school exams/holidays, year end shutdown etc | nil, previous quarter target exceeded and covers this quarter | daily stats spreadsheet
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 06 | Basic Service Delivery | Disaster Management | Reviewed Disaster Risk Management Plan | All | non- compliance with Disaster Management Act | Disaster Risk Management Plan reviewed by 30/04/13 | Date of approved Disaster Risk Management Plan | N/A | N/A | N/A | Nil Required | Wards Consultations completed by 31/09/12 | submitted to Disaster Management Advisory Plan Committee 31/12/12 | conducted workshop in ward 2 |  | Target Met | N/A | N/A | Disaster Management Act
[8 empty] | N/A | N/A | N/A |  | N/A | N/A |  |  | N/A | N/A | N/A | N/A
FDMS 07 | Basic Service Delivery |  | Workshops of Disaster Risk Management Plan | All | Nil | 100% workshops conducted in all wards by 30/06/13 | Number of wards workshops conducted | N/A | N/A | N/A | Nil Required | 25% of Wards | 25% of Wards | 81% completed |  | target exceeded | N/A | N/A | Disaster risk analyis attendance register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 08 | Basic Service Delivery |  | Disaster Management Advisory Planning Committee | All | Nil | Disaster Management Advisory Planning Committee established by 30/09/12 | Date Disaster Management Advisory Planning Committee established | N/A | N/A | N/A | Nil Required | Disaster Management Advisory Planning Committee established by 30/09/12 | Implimentation of Committee meetings | Letters to nominated DMAC members drafted |  | target partially met | Committee not yet appointed | Appoint committee | EXCO Resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMS 01 | Basic Service Delivery |  | Traffic Sector Policing Business Plan developed | All | no Traffic Sector Policing Business Plan. | Traffic Sector Policing Business Plan submitted to Manco by 28/02/13 | Date of completed Traffic Sector Policing Business Plan. | N/A | N/A | N/A | Nil Required | N/A | Compiled First Draft Business Plan 31/10/12 | traffic strategic plan approval by SMC ? | Target Partially Met | Target Met | N/A | N/A | approval by SMC
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMS 02 | Basic Service Delivery |  | Business Plan developed for Vulindlela Traffic Station. | All | 1 Traffic Station Central | Completed Business Plan submitted to MANCO BY 30/10/12 | Date of completed Business Plan | N/A | N/A | N/A | Nil Required | Compiled First draft Business Plan 31/09/12 | Final Business Plan submitted to Manco by 30/10/12 | Final Business Plan submitted to Manco 20 November 2012 | Target Met | Target Met | N/A | N/A | Manco resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMS 03 | Basic Service Delivery |  | Compliance Fire Arms Controls Act | N/A | 50% Compliance | Fire Arm Training (shoot) undertaken by 60 officers by 31/12/12 | Date of Fire arm training completed; number of traffic officers trained. | N/A | N/A | N/A | Council | Fire arm Training funds identified. | 60 officers undertaken fire arm Training | Training schedule for Traffic Officers complited December 2012, 15 Security Officers trained | Target Exceeded | Target Exceeded | N/A | N/A | Minutes of pre assessment meeting
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMS 04 | Basic Service Delivery |  | Compliance Fire Arms Controls Act | n/a | non compliance with Fire Arm Control Act | Fire Arm Audit Conduted by 31/10/12 | date fire arm audit completed | N/A | N/A | N/A | N/A | fire arm audit in progress | fire arm audit completed by 31/10/12 | internal fire arm audit completed by 30 November 2012 | Target Met | Target Met | N/A | N/A | Fire arm Audit documents
TMS 05 | Basic Service Delivery |  | Road Safety awareness conducted at schools | all | 80 schools sessions conducted per annum | 120 school sessions per annum | number of school sessions conducted. | N/A | N/A | N/A | N/A | 30 school safety awreness sessions conducted. | 30 school safety awreness sessions conducted. | 8 school safety Awareness sessions conducted due to school closure | Target Met | Target Met | N/A | N/A | confirmation letters from schools

## INFRA COVER
ANNEXURE 1(H): INFRASTRUCTURE SERVICES BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## INFRA overview
INFRASTRUCTURE SERVICES BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | INFRASTRUCTURE SERVICES BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 77
| 1.1.1 | OPERATING PROJECTS | 12
| 1.1.2 | CAPITAL PROJECTS | 65
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## WATER overview
WATER & SANITATION UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | WATER & SANITATION UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 14
| 1.1.1 | OPERATING PROJECTS | 0
| 1.1.2 | CAPITAL PROJECTS | 14
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Water & Sanitation
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.1 WATER & SANITATION
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
W&S 01 | Basic Service Delivery and Infrastructure Development | Sanitation | Rehabilitation :Sanitation Infrastructure | 15, 19, 16, 30, 35, 32, 33, 26, 25, 29, 31 | 50 km of sewer pipe to be upgraded and 6 Pump Stations upgraded | Replace 3 km of Sewer pipe and upgrade 1 Pump Station | km of sewer pipe replaced, no of pump stations upgraded | N/A | 10 000 000 | N/A | MIG | Consultant Appointed | Design Completed | 3 Designs completed |  |  | Target Met | N/A | N/A | Designs
[18 empty] | N/A | N/A
[18 empty] | N/A | N/A
[8 empty] | N/A | 2026051303 | N/A |  | 1 200 000 | 2 000 000 | 127004 |  |  | N/A | N/A | N/A | N/A
W&S 02 | Basic Service Delivery and Infrastructure Development |  | Shenstone Ambleton Sanitation System | 18 | 0 | 3.8km of pipe installed | Km of pipe installed | N/A | 13 500 000 | N/A | MIG | Await Record Of Decision, Bid Spec Approved (Once ROD in received) | Contract Awarded, 0.8km of pipe installed | Provisional letter of award sent |  |  | Target Partially Met | Delay in EIA in 1st Quarter | Implement Program with Contractor to fastrack in 3rd and 4th quarters | Award Letters
[8 empty] | N/A | 2026051302 | N/A |  | 250 000 | 2 000 000 | 42065 |  |  | N/A | N/A | N/A | N/A
W&S 03 | Basic Service Delivery and Infrastructure Development |  | Sewer Pipes unit H-Ward 16 | 16 | N/A | Completed Design and Tender Document by 30 June 2013 | Date | N/A | 600 000 | N/A | MIG | Contract Advertised Tender | Consultant Appointed - Planning Phase commenced | Consultant Appointed - Planning Phase commenced |  |  | Target Met | N/A | N/A | Award Letter and Consultants correspondence, Minutes of meeting
[8 empty] | N/A | 2026051304 | N/A |  | 30 000 | 100 000 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 04 | Basic Service Delivery and Infrastructure Development |  | Sewer Pipes Azalea - Phase 2 | 10 | N/A | Completed Draft Design and Tender Document by 30 June 2013 | Date | N/A | 600 000 | N/A |  | Contract Advertised | Consultant Appointed - Planning Phase commenced | Consultant Appointed - Planning Phase commenced |  |  | Target Met | N/A | N/A | Award Letter and Consultants correspondence. Minutes of meeting
[8 empty] | N/A | 2026051305 | N/A |  | 30 000 | 100 000 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 05 | Basic Service Delivery and Infrastructure Development |  | Infrastructure Feasibility | 15, 19, 16, 30, 35, 32, 33, 26, 25, 29, 31 | High levels of Storm Water Infiltration | Completed Infiltration assessment report by 30 June 2013 | Date of completion | N/A | 500 000 | N/A | MIG | Contract Advertised | Preliminary Investigation Report completed | Preliminary Report |  |  | Target Met | N/A | N/A | Draft Investigation Report (received 4 January 2013)
[8 empty] | N/A | 2026051301 | N/A |  | 30 000 | 150 000 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 06 | Basic Service Delivery and Infrastructure Development |  | Elimination of Conservancy Tanks-Sewer | 20.21 | N/A | 2.5km of sewer installed | km of sewer installed | N/A | 5 000 000 | N/A | MIG | Contract Advertised | Contractor Appointed | Provisional Letter of acceptance sent. Awaiting Surety. |  |  | Target Partially Met | 14 Days for contractor to submit surety fell in the"shutdown period" | Revise program once contractor appointed to ensure targets are met in the 3rd and 4th Quarters. | Provisonal Award letter (SCM).
[8 empty] | N/A | 2026081301 | N/A |  | 80 000 | 720 000 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 07 | Basic Service Delivery and Infrastructure Development |  | Service Midblock Eradication | 23 | N/A | 5km of sewer pipe constructed | km of Sewer Pipe constructed | N/A | 10 000 000 | N/A | MIG | Contract Advertised | Contractor appointed, 0.3km of Sewer Pipe constructed | Provisional Letter of acceptance sent. Awaiting Surety. |  |  | Target Partially Met | Contractor wanted to negotiate surety policy | Implement Program with Contractor to fastrack in 3rd and 4th quarter | Provisonal Award letter (SCM) and E-mails
[8 empty] | N/A | 2026081302 | N/A |  | 150 000 | 2 000 000 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 08 | Basic Service Delivery and Infrastructure Development | Water | Basic Water Supply | 1 to 11, 14 | 0.5km | Install 0.5km of water pipe | km of Water Pipe installed | N/A | 2 000 000 | N/A | MIG | SAC Approved | MIG Approved, 0.2km of Water Pipe installed | Implemeneted in Ward 2, 0.1 km of basic water pipe |  |  | Target Partially Met | Ward 7 had to stop because on DOT servitude. | Implement in 3rd quarter. | MIG Progress Spreadsheet. Email from Umgeni Water.
[8 empty] | N/A | 7876051304 | N/A |  | 50 000 | 650 000 | 302328 |  |  | N/A | N/A | N/A | N/A
W&S 09 | Basic Service Delivery and Infrastructure Development |  | Masons Reservoir & Pipeline | 26 | N/A | Completed Final Design and Tender Documentation by 30 June 2013 | Date | N/A | 500 000 | N/A | MIG | Submit for MIG approval for Pipelines, Appoint EIA Consultant | Completed Planning phase | Planning phase complete with the Goetech and Survey outstanding |  |  | Target Partially Met | No Tenders received for Geotech and Survey. | Arrange Documentation for VO to imlement wioth consultant in 3rd Quarter | Planning and Design of Reservoir
[8 empty] | N/A | 7876061301 | N/A |  | 120 000 | 80 000 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 10 | Basic Service Delivery and Infrastructure Development |  | Copesville Reservoir | 29 | 0 | Cast 100% Floor, Cast 50% Reservoir Walls | % Complete | N/A | 21 219 450 | N/A | MIG | Completed Site preparation, demolition of old reservoir | Casted Floor Slab (50%) | Blinding of floor completed and Steel work commenced on the Colms |  |  | Target Met | N/A | N/A | Minutes of Techncial Meeting.
[8 empty] | N/A | 7876061205 | N/A |  | 4 500 000 | 5 300 000 | 2869833 |  |  | N/A | N/A | N/A | N/A
W&S 11 | Basic Service Delivery and Infrastructure Development |  | Reduction - Non Revenue Water | ALL | Non -Revenue Water for the 2010/11 financial year is 46.7% | Non-Revenue Water to be 50.5% | % of Non-Revenue Water | N/A | 15 000 000 | N/A | MIG | 54.1% | 52.1% | 43.04% |  |  | Target Exceeded | N/A | N/A | IWA Balance for November 2012.
[8 empty] | N/A | 7876051301 | N/A |  | 2 500 000 | 3 250 000 | 3732795 |  |  | N/A | N/A | N/A | N/A
W&S 12 | Basic Service Delivery and Infrastructure Development |  | Elimination of Conservancy Tanks-Water | 20,21 | N/A | Install 0.3km of water pipe. | km of Water Pipe installed | N/A | 250 000 | N/A | MIG | Contract Advertised | Contractor appointed, | Provisional Letter of acceptance sent. Awaiting Surety. |  |  | Target Partially Met | 14 Days for contractor to submit surety fell in the"shutdown period" | Revise program once contractor appointed to ensure targets are met in the 3rd and 4th Quarters. | Provisonal Award letter (SCM).
[8 empty] | N/A | 7876051302 | N/A |  | 0 | 0 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 13 | Basic Service Delivery and Infrastructure Development |  | Service Midblock Eradication | 23 | N/A | 0.4 km of water pipe constructed | km of water Pipe constructed | N/A | 500 000 | N/A | MIG | Contract Advertised | Contractor appointed | Provisional Letter of acceptance sent. Awaiting Surety. |  |  | Target Partially Met | Contractor wanted to negotiate surety policy | Implement Program with Contractor to fastrack in 3rd and 4th quarter | Provisonal Award letter (SCM) and E-mails
[8 empty] | N/A | 7876051303 | N/A |  | 0 | 120 000 | 0 |  |  | N/A | N/A | N/A | N/A
W&S 14 | Basic Service Delivery and Infrastructure Development |  | Edendale Proper | 20 | 3.9km | Appoint Contractor, complete 3.6km of Water Pipe. | km of water Pipe | N/A | 1 200 000 | N/A | MIG | Contract Advertised | Contractor Appointed, Completed 1.2km Water Piping | Contractor Appointed |  |  | Target Partially Met | Delay in advertisement in 1st Quarter | Implement Program with Contractor to fastrack in 3rd quarter | Award letter.
[8 empty] | N/A | 7876051202 | N/A |  | 30 000 | 350 000 | 52642 |  |  | N/A | N/A | N/A | N/A

## ELEC overview
ELECTRICITY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | ELECTRICITY UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 13
| 1.1.1 | OPERATING PROJECTS | 1
| 1.1.2 | CAPITAL PROJECTS | 12
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Electricty
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.2 ELECTRICITY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
EL 01 | Basic service delivery | Electricity provision | Service connections (credit meters) | All | install 600 connections | install 600 connections | number od connections installed | N/A | N/A | N/A | Customer pays for service connection | 150 connections installed | 150 connections installed | 37 connections installed |  | Target Partially Met | customer driven | proposing to change Quartely target as it is customer driven | Job cards
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 02 | Basic service delivery |  | Service connections (pre-paid) | All | 1000 prepaid connections installed | 1000 prepaid meter connections installed | Number of connections installed | N/A | N/A | N/A | Customer pays for service connection | 250 connections installed | 250 connections installed | 96 connections installed |  | Target Partially Met | customer driven | proposing to change Quartely target as it is customer driven | Job cards
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 03 | Basic service delivery |  | Electrification | 30 | istalled 500 connections | Ezinketheni (Copesville)-500 connections installed | Number of connections installed | N/A | 5 million | N/A | DOE | Design Completed | Construction | Material purchased by the Consultant |  | Nil Achieved | delays on data collection and design by the Consultant | Regular meetings with Consulatnt | Copies of the invoices
[8 empty] | N/A | 7136091301 | N/A |  | N/A | 3 000 000 | N/A | N/A | N/A | N/A | N/A | N/A
EL 04 | Basic service delivery |  | High mast lights | 1-18; 20 & 23 | N/A | 20 high mast lights installed | Number of high mast lights installed | N/A | 4 082 960 | N/A | Capex MIG. Opex Council | Bid advertised | Tender awarded | Tender awarded and purchase of material |  | Target Exceeded | Material purchased by the Consultant | Regular meetings with Consulatnt | Copies of the invoices
[8 empty] | N/A | 7136181301 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 05 | Basic service delivery | Electricity Maintenance | Mini sub-stations | All | Replacement of 10 Mini substations | Replacement of 10 mini substations | Number of mini substations replaced | N/A | 4 000 000 | N/A |  | Order placed & 2 replaced | Delivery & 2 mini substations replaced | 4 mini substation installed and replaced |  | Target Exceeded | N/A | N/A | Stock Document
[8 empty] | N/A | 7136541302 | N/A |  | N/A | 2 000 000 | N/A | N/A | N/A | N/A | N/A | N/A
EL 06 | Basic service delivery |  | Pole mounted transformers | 1 & 2 | Replacement of 12 pole mounted transformers | Replacement of 12 pole mounted transformers | Number of pole mounted transformers replaced | N/A | 2 000 000 | N/A |  | Order placed & 3 installed | delivery and 3 installed | 4 delivered and installed |  | Target Exceeded | N/A | N/A | Stock Document
[8 empty] | N/A | 7136541302 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 07 | Basic service delivery |  | Switchgear | All | Replacement of 40 switch gear & accessorie | Replacement of 40 switch gear & accessories | Number of switch gear replaced | N/A | 12 500 000 | N/A |  | Order placed | delivery | 11 swith gear relaced |  | Target Exceeded | N/A | N/A | Stock Document
[8 empty] | N/A | 7136541302 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 08 | Basic service delivery |  | Ground Mounted Transformers & ring main units | All | Replacement of 6 transformers & 10 ring main units | Replacement of 6 transformers & 10 ring main units | Number of transformers & ring main units replaced | N/A | 2 000 000 | N/A | Council | Order placed | delivery | 4 transformers and 5 ring main units replaced |  | Target Exceeded | N/A | N/A | Stock Document
[8 empty] | N/A | 7136541302 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 09 | Basic service delivery |  | Streetlights | All | Obsolete | Replacement of 900 streetlights | Number of street lights replaced | N/A | N/A | N/A | DoE | 200 street lights replaced | 250 street lights replaced | 896 street lights replaced |  | Target Exceeded | N/A | N/A | joc cards and stock documents
[8 empty] | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 10 | Basic service delivery | Electricity Upgrade | Hilton Overhead Line | 1 & 2; Hilton | Design completed | Construct 33kV overhead line to Hilton | Completed construction of line | N/A | 13 500 00 | N/A | Council | Commence Construction of 33kV overhead line to Hilton | Complete Construction of 33kV overhead line to Hilton | Construction on progress |  | Target Partially Met | Delays due to unpredictable weather condition and terrain | Consultant is on site | Monthly reports
[8 empty] | N/A | 7135211301 | N/A |  | 6 000 000 | 7 500 000 | N/A | N/A | N/A | N/A | N/A | N/A
EL 11 | Basic service delivery | Protection Rectification | Protection testing & Maintenance | All | Assessment of sub-stations complete | Protection study, testing, maintenance and updating- 132/11kV | Completion of protection setting and grading | N/A | 2 500 000 | N/A | Council | Commence Protection study, testing, maintenance and updating- 132/11kV | Complete Protection study, testing, maintenance and updating- 132/11kV | On progress |  | Target Partially Met | delays on collection of data and redesign of electricity network | Consultant is on site | Monthly reports
[8 empty] | N/A | 7136541303 | N/A |  | 1 000 000 | 1 500 000 | N/A | N/A | N/A | N/A | N/A | N/A
EL 12 | Basic service delivery |  | Electricity Maintenance Plan | All | N/A | Adopt maintenance plan by 30/06/2013 | Date of adopted maintenance plan | N/A | N/A | N/A | Nil | Information Collected (data collection) | Data collation | Data collation |  | Target Met | N/A | N/A | maintanance plan document
[7 empty] | Date | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EL 13 | Basic service delivery | Electricity Maintenance | Electricity upgrade & protection | All | obsolete equipment | replacement of obselete equipment | number of equipment replaced | N/A | 34 492 442 | N/A | Council | order placed | delivery of equipment | equipment purchased and delivery |  | Target Met | N/A | N/A | Stock Document
[8 empty] | N/A | 7136541301 | N/A |  | N/A | 10 000 000 | N/A | N/A | N/A | N/A | N/A | N/A

## PMU overview
PROJECT MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | PROJECT MANAGEMENT & FLEET UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 6
| 1.1.1 | OPERATING PROJECTS | 6
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## PMU
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.3 PROJECT MANAGEMENT UNIT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
PMU 01 | Basic Service Delivery | Project Management support | Monthly programme/ project monitoring reports for MIG/OGF/CNL Budget | All | Reports compiled & submitted by 5th of every month. Ensure 100% of budget is spent. | Reports compiled & submitted by 5th of every month. Ensure 100% of budget is spent. | Date of report compiled monthly | N/A | N/A | N/A | Nil Required | 3 X monthly reports submitted by the 5th of every month to project managers | 3 X monthly reports submitted by the 5th of every month to project managers | 3x monthly reports submitted |  | target met | N/A | N/A | Report,IDP Documnt, Mig Budget
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PMU 02 | Basic Service Delivery | Project Management support | Weekly programme/project monitoring reports for MIG/OGF/CNL Budget | All | Minutes/ reports compiled every second Wednesday. Ensure 100% of budget is spent. | Minutes/ reports compiled every second Wednesday. Ensure 100% of budget is spent. | Weekly reports compiled | N/A | N/A | N/A | Nil Required | 6 X weekly reports sent out every second Wednesday to PM's | 6 X weekly reports sent out every second Wednesday to PM's | 2xreports for Oct,2xreports forNov,1x report for Dec submitted |  | Target partially met | 1xmeeting held in DEC | N/A | reports/IDP/MIG Budget
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PMU 03 | Basic Service Delivery | Project Management Support | Monitoring, Co-ordination, assistance facilitation and implementation to all BU | All | Minimised Risks to projects not meeting targets and develop action plans | Meet project service delivery objectives | No | N/A | N/A | N/A | N/A | Daily action plans and implementation monitoring | Daily action plans and implementation monitoring | daily action plans implemented and monitored |  | Target Met | N/A | N/A | MIG Budget /IDP Document
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PMU 04 | Basic Service Delivery | Project Management Support | Administration of payment process and ongoing monitoring | All | All invoices packaged and submitted to client departments within 48 hours | All invoices packaged and submitted to client departments within 48 hours | Turn-around time for submission of invoices | N/A | N/A | N/A | Nil Required | All invoices packaged and submitted to client departments within 48 hours | All invoices packaged and submitted to client departments within 48 hours | All financial issues attended within 48 hours |  | Target Met | N/A | N/A | MIG Budget /IDP Document
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PMU 05 | Basic Service Delivery | Project Management Support | Financial support budget and reporting to MIG (Provincial/National Treasury) | All | Maintaining and implementing of all financial issues daily | Maintaining and implementing of all financial issues daily | Time | N/A | N/A | N/A | N/A | Attending to financial issues Within 48 hours | Attending to financial issues Within 48 hours | All financial issues attended within 48 hours |  | Target Met | N/A | N/A | MIG Budget /IDP Document
[8 empty] | N/A | N/A | N/A |  | Daily monitoring | Daily monitoring | N/A | N/A | N/A | N/A | N/A | N/A
PMU 06 | Basic Service Delivery | Project Management Support | Administration Support and reporting to MIG (Provincial) and reporting to OGF/CNL/EPWP | All | Ensure project documentation completion to report expenditure to MIG/Funding Source by the 15th of every Month | Ensure project documentation completion to report expenditure to MIG/ Funding Source by the 15th of every Month | Date of submission of monthly reports | N/A | N/A | N/A | Nil Required | 3 X monthly reports by the 15th of every month | 3 X monthly reports by the 15th of every month | 3x monthly Reports submitted to MIG Office |  | Target Met | N/A | N/A | Reports/MIG budget/IDP document
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Fleet Overview
FLEET MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | PROJECT MANAGEMENT & FLEET UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 5
| 1.1.1 | OPERATING PROJECTS | 5
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Fleet
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.4 FLEET MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
FLT 01 | Basis Service Delivery | FLEET | Vehicle monitoring system | NA | Service provider contract | Fitment of vehicle monitoring system to 789 vehicles by 30/12/12 | Date of fitment to vehicles |  | N/A | N/A | Council | Vehicle monitoring system fitted to 429 vehicles | Vehicle monitoring system fitted to all 789 vehicles | Vehicle monitoring system fitted to 611 vehicles |  | Target Partially Met | Vehicles not being made available for fitment | Vehicles to be made available for fitment | Vehicle monitoring system fitment register
[7 empty] | Number | 160 | N/A | N/A |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A
FLT 02 | Basis Service Delivery |  | Vehicle and Plant service plan | NA | Inadequate service plan | 100% of vehicle and plant serviced | % of vehicles and plant serviced | 13 000 000 | N/A | N/A | internal | 100% of vehicle and plant serviced | 100% of vehicle and plant serviced (216 vehicles) | 9.25% of vehicles and plant serviced (20 vehicles) |  | Target Partially Met | Delays in obtaining order numbers | Develop procedure to obtain order numbers quicker | job cards
[8 empty] | 215 3200 | N/A | N/A |  | 107 000 | 107 000 | 107 000 |  | N/A | N/A | N/A | N/A
FLT 03 | Basis Service Delivery |  | Fleet Policy | NA | Draft fleet policy in place | Adopt fleet policy by the 30/12/2012 | date of adopted fleet policy | N/A | N/A | N/A | Nil Required | Final Draft Considered | Fleet policy adopted by 30/12/2012 | Fleet policy adopted |  | Target Met | N/A | N/A | Council resolution 26 September 2012 Approved Fleet policy
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
FLT 04 |  |  |  |  | Nil | 100% Implementation of fleet Policy | % implementation of fleet policy | N/A | N/A | N/A | Nil Required | NA | NA | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | NA | NA | NA |  | NA | NA | NA | NA
FLT 05 | Basic Service delivery |  | Accident Review Committee | all | No committee | Committee operational by 30/12/12 with monthly meetings. | Date of established accident review committee and monthly meetings | N/A | N/A | N/A | Nil Required | Report to Manco | Accident Review Committee established by 30/12/2012 | Members appointed |  | Target Partially Met | Chair person to be appointed among the members | Appointment letter to chair person and first meeting to be convened | Minutes of the meeting
[7 empty] | Number of monthly meetings | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A

## ROADS overview
ROADS & STORMWATER UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | ROADS & STORMWATER UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 30
| 1.1.1 | OPERATING PROJECTS | 0
| 1.1.2 | CAPITAL PROJECTS | 30
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Roads & Stormwater
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.5 ROADS & STORMWATER
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
RSW 01 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Horse Shoe Access Road | 15 & 19 | Gravel horse shoe and passages in need of upgrade to all weather surface access. | Upgrading of 1.2 km Horse Shoe Access Rd | km of road upgraded | N/A | 1 700 000 | N/A | MIG | Commencement of sub-base layers by internal staff. Developed programme and acquired quotations from suppliers | Prepared sub-base layers using internal staff. | Sub-base prepared. Surfacing of passages commenced. |  | Target Exceeded | N/A | N/A | Pictures
[8 empty] | N/A | 125 625 1305 | N/A |  | 375 000 | 475 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 02 | Basic Service Delivery and Infrastructure Development |  | Moscow Roads | 12 | Grav-seal and gravel roads with limited access levels in need of upgrade to all weather access | Upgrading of 1.3 km to Moscow Roads | km of road upgraded | N/A | 4 000 000 | N/A | MIG | Design Report and Specifications completed. Bid specification approval. | Tender advertised and awarded. | Tender advertised and awarded by BAC. |  | Target Met | N/A | N/A | Minutes of BAC / Resolution
[8 empty] | N/A | 125 625 1307 | N/A |  | Nil | 50 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 03 | Basic Service Delivery and Infrastructure Development |  | Ashdown Roads | 23 | Grav-seal and gravel roads with limited access levels in need of upgrade to all weather access | Rehabilitation of 2.0 km Ashdown Roads | km of road rehabilitated | N/A | 2 500 000 | N/A | MIG | Work programme developed Acquiring quotations from suitable contractor | Sub-base layers prepared | Commenced with the preparation. The contract for surfacing and stormwater awarded. |  | Target Partially Met | The Department could get the hired plant from the Suppliers due to high demand. | The Department is rotating the existing three sets of plant between maintenance and Capital project as best as possible. | Minutes of BAC / A copy of appointment letter
[8 empty] | N/A | 125 625 1315 | N/A |  | Nil | 450 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 04 | Basic Service Delivery and Infrastructure Development |  | Machibisa/Dambuza Roads | 21 | Grav-seal and gravel roads with limited access levels in need of upgrade to all weather access | Upgrading of 0.8 km Machibisa / Dambuza Roads | km of road upgraded | N/A | 2 000 000 | N/A | MIG | Advertised for a contractor | Appointed contractor | Contractor appointed to commence construction in January 2013 |  | Target Met | N/A | N/A | Minutes of BAC / A copy of appointment letter
[8 empty] | N/A | 125 625 1316 | N/A |  | Nil | 50 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 05 | Basic Service Delivery and Infrastructure Development |  | D1128 Road | 5 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgrade of 3.25 km gravel road into all weather access by 30 September 2012. | km of road upgraded | N/A | 3 000 000 | N/A | MIG | Upgrade of 3.25 km gravel road into all weather access by 30 September 2012. | N/A | N/A |  | Not Applicable | N/A | N/A
[8 empty] | N/A | 125 625 1301 | N/A |  | 3 000 000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RSW 06 | Basic Service Delivery and Infrastructure Development |  | Station Road Bridge | 11 | 0 | Design Report and Approved EIA (RoD from DAEARD) by 30 June 2013 | Date of approved EIA | Nil | 100 000 | N/A | MIG | Design Report to be completed by 30 Sep 2012 | Draft EIA Basic Assessment Report to be completed by 31 Dec 2012 | Draft EIA complete |  | Target Met | N/A | N/A | Draft EIA doucment.
[8 empty] | Nil | 125 625 1313 | N/A |  | 45 000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RSW 07 | Basic Service Delivery and Infrastructure Development |  | Haniville Internal Roads | 29 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.2km internal gravel roads in Haniville Township | km of road upgraded | N/A | 1 500 000 | N/A | MIG | Developed Work Programme Acquiring quotations from suitable contractors | Preparation/ construction of base layers | 100% Base layer prepared but in some areas it was damaged by storms. Surfacing commenced - 40% complete. |  | Target Exceeded | N/A | N/A | Pictures
[8 empty] | N/A | 1256251311 | N/A |  | Nil | 375 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 08 | Basic Service Delivery and Infrastructure Development |  | Mbucwana Road | 1 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.3km by 30 June 2013 | km of road upgraded | N/A | 1 800 000 | N/A | MIG | Quotations for storm-water and black base Commenced with storm-water | Completion of storm-water Preparation of sub-base layer - G5 - internally | SWD Quotation awarded. The contractor to attend to sub-base and surfacing under adjudication. |  | Nil Achieved | Delays in compiling the database of contractors from the advert. | Expedite adjudication process. | Close tender register of bidders.
[8 empty] | N/A | 125 625 1309 | N/A |  | Nil | 500 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 09 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Ward 22 Roads | 22 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.3km of Gravel Roads in Ward 22 by 30 June 2013 | km of road upgraded | N/A | 2 300 000 | N/A | MIG | Developed programme and quotations from suppliers | Completed sub-base layers | Completed sub-base layers and 70% of surfacing completed. |  | Target Exceeded | N/A | N/A | Progress payment invoices.
[8 empty] | N/A | 125 625 1306 | N/A |  | Nil | 300 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 10 | Basic Service Delivery and Infrastructure Development |  | Esigodini Roads. Upgrading of gavel road to all weather surface | 12 | 0 | Design Report and Approved 31 December 2012. | Completed design report | N/A | 400 000 | N/A | MIG | Advertised and appointed a consultant by 30 Sep 2012 | Completed Draft Design Report by 31 Dec 2012 | The Design completed for the intended roads. A saving was realised due to prices lower than estimates. Spec drafted to design additional roads with the saving. |  | Target Exceeded | A saving has been realised due to prices coming in less than estimated. Funds to be used to design more roads. Design complete. | N/A | Design drawings.
[8 empty] | N/A | 125 625 1312 | N/A |  | Nil | 175 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 11 | Basic Service Delivery and Infrastructure Development |  | Ward 16 Roads | 16 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 0.87km of gravel roads in Ward 16 by December 2012 | km of road upgraded | N/A | 1 200 000 | N/A | MIG | Preparation of sub-base layer - G5 0 internally Engage Annual Supply Contract - obtain quotation and a programme | Completed upgraded 0.87km of gravel roads in Ward 16 by December 2012 | Upgrade of 3 roads - 0.86 km complete. 1 road to be completed in March. |  | Target Partially Met | Shortage of funds caused the delay. | Funds to be reallocated in the Mid-Year Review. | Pictures of 3 completed roads.
[8 empty] | N/A | 125 625 1310 | N/A |  | 300 000 | 900 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 12 | Basic Service Delivery and Infrastructure Development |  | KwaNyamazane Roads | 13 | Damaged roads by uncontrolled water in need of investigation and rehabilitation | Completed Investigated stormwater and design by 30 June 2013 | Completed investigation and design report | N/A | 500 000 | N/A | MIG | Approved spec by BSC Advertised tender | Appointed Consultant. Commenced with stormwater investigation and design | Tender advertised, closed and is under technical adjudication. |  | Nil Achieved | A panel of consultants was not appointed by BAC. The Department had to revert to the normal SCM process after the above delayed. | To expedite adjudication process. | Tender advert and Register of Received Tenders
[8 empty] | N/A | 125 625 1308 | N/A |  | Nil | 250 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 13 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Tafuleni Road | 11 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 2.4km of Tafuleni gravel road by 30 June 2013. | km of road upgraded | N/A | 3 500 000 | N/A | MIG | Stormwater & quotation | Completed s/w implementation | Suitable bidders were invited by SCM from the database for a briefing. Tenders closed in December 2012. |  | Nil Achieved | Delays in compiling the database of contractors from the advert. | Expedite adjudication process. | Close tender register of bidders.
[8 empty] | N/A | 125 625 1304 | N/A |  | N/A | 500 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 14 | Basic Service Delivery and Infrastructure Development |  | Willowfountain (Main, Khuzwayo and Kwa-Phupha Roads) | 14 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 3.0km of gravel roads in Willowfountain Roads by 30 June 2013 | km of road upgraded | N/A | 6 500 000 | N/A | MIG | Completed Design of the Main Road. Appointment of the contractors to undertake 1.2 km road. Quotation for Khuzwayo & Kwa-Phupha Rds Preparation for Khuzwayo & Phupha Rds | Completed construction of 1.0 km of gravel roads. | Design completed. Tenderers were invited. Briefing was on 7/12/12. Closure on 18/12/2012. Upgrade of KwaPhupha and Khuzwayo Road compelted. |  | Target Exceeded | N/A | N/A | Close tender register of bidders. Completion Certifications for KwaPhupha and Khuzwayo Roads.
[8 empty] | N/A | 125 625 1302 | N/A |  | 1 200 000 | 1 600 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 15 | Basic Service Delivery and Infrastructure Development |  | Roads in Ward 17 | 17 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.2 km by 31 December 2012 | km of road upgraded | N/A | 1 500 000 | N/A | MIG | Obtained quotes from Annual Suppliers Commenced with placing of the base layer - G5 | Completed upgraded 1.2 km by 31 December 2012 | Completed 0,8 km. |  | Target Partially Met | The other road was affected by encroachment. | The Cllr is attending to the matter or a different road will be chosen by Cllr. | Pictures
[8 empty] | N/A | 1256251317 | N/A |  | 300 000 | 1 200 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 16 | Basic Service Delivery and Infrastructure Development |  | Mbanjwa Road | 20 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.9km of Mbanjwa Rd in Siyamu by 30 June 2013 | km of road upgraded | N/A | 3 500 000 | Nil | MIG | Finalize appointment of service provider | Prepared sub-base layer & stormwater quotations to be acquired. | Tenders closed. |  | Nil Achieved | The intention was to construct road internally but workload forced this to be outsourced. | Fast-track the adjudication. | Close tender register of bidders.
[8 empty] | N/A | 125 625 1303 | Nil |  | Nil | 500 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 17 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Footpaths in Sobantu by 31 March 2013 | 35 | Unsafe and gravel footpaths in need of upgrade. | Constructed 0.2km footpaths in Sobantu by 30 March 2013 | km of footpath constructed | N/A | 200 000 | Nil | MIG | Develop programme and call for quotations | Preparation of sub-layer | 0.2 km completed. |  | Target Exceeded | N/A | N/A | Completion Certificates
[8 empty] | N/A | 125 625 1314 | Nil |  | nil | 50 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 18 | Basic Service Delivery and Infrastructure Development |  | Upgrading Shembe, Joe Ngidi, Ndwendwe, Mavimbela, Stebhisi Link, Shandu & Ntombela Roads | 12 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 0.5km of gravel roads in Edendale | km of road upgraded | N/A | 664 590 | N/A | MIG | Develop programme and acquire quotations from suppliers and preparation of sub-base layers. | Completed upgraded 0.5km of gravel roads in Edendale. | Completed 0.5km SWD for the upgraded gravel roads. |  | Target Met | N/A | N/A | Completion Certificates
[8 empty] | N/A | 125 625 1318 | N/A |  | 100 000 | 564 590 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 19 | Basic Service Delivery and Infrastructure Development |  | N3/Chota Motala Interchange | 32, 33, 35 | Main Road operating at low Level Of Service (LOS) in need of upgrade | Completion of Municipal additional 1.5 km road lanes in Chota Motala Road by September 2012 | Completion date of Chota Motala Rd | N/A | 16 790 000 | Nil | Council | Completion of Municipal additional 1.5 km road lanes in Chota Motala Road by September 2012 | N/A | Completed 1.5 km of road works, except the bridge. |  | Target Partially Met | The delay was experienced on the Dorpspruit bridge due to storms in the Nov/Dec'12. | Revised schedule to complete the project in mid-Feb'13. | Site minutes
[8 empty] | N/A |  | Nil |  | 16 790 000 | Nil | N/A | N/A | N/A | N/A | N/A | N/A
RSW 20 | Community and Social Services | Cemeteries | Hollingwood Cemetery (Multi-year project) | 35 | Open land for development into a new cemetery | - Building works completed - Road works completed up to sub-base level - Rehabilitation of waste site commenced | milestone by date | N/A | 13 500 000 | N/A | MIG | Completed design and specifications Advertised for contractor | Appointed contractor and commenced with works | Contractor appointed to commence construction in January 2013 |  | Target Partially Met | Advert period was extended. This left no time for the contractor to take occupation of site. | To commence in January 2013 after the contractor shut-down period. | Minutes of BAC
[8 empty] | N/A | 392 642 1301 | N/A |  | 500000 | 1 500 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 21 | Community and Social Services | Cemeteries | Cremators | 35 | Old and dysfunctional cremators in need of replacement | Installation of 2 new cremators by 30 March 2013 | Project milestone completion date | Nil | 2 800 000 | Nil | MIG | Approved spec by BSC Advertised tender | Appointed Service Provider for Cremators | The BAC report referred to MM for appointment |  | Target Partially Met | The report was referred back by BEC for written references and similarly by BAC to for unknown reasons and referred to MM. | Awaits BAC and MM outcome. | BAC minutes
[8 empty] | Nil | 392 630 1302 | Nil |  | Nil | Nil | N/A | N/A | N/A | N/A | N/A | N/A
RSW 22 | Community and Social Services | Public ablutions | Public Ablution Facilities | 27, 32, 23, 35 | Endless problems with existing ablutions in need of upgrading | 8 rehabilitated public ablution facilities by June 2013 | Number of ablutions rehabilitated | N/A | 1 500 000 | Nil | MIG | Approved specs for quotations by 30 Sept 2012 | Quotations adjudicated and awarded by 30 Oct 2012 | 5 Quotation were awarded |  | Target Partially Met | Companies awarded quotation are being investigated by Internal Audit. Therefore not willing to commence with work. | Trying to cancel orders and re-advertise quotations subject to them signing forms to force-closed the orders. | Orders
[8 empty] | N/A | 141 360 1301 | Nil |  | Nil | Nil | N/A | N/A | N/A | N/A | N/A | N/A
RSW 23 | Community and Social Services | Community Hall | Unit 18 Community Hall - Phase 1 | 15 | Non-existence of hall in Ward 15. New Hall needed. | Completed Phase 1 of Unit 18 Community Hall | Date of completion of phase 1 of community hall | N/A | 2 500 000 | N/A | MIG | Approved specification Advertised tender by 30 Sep 2012 | Tender awarded Service Provider appointed by 31 Dec 2012 | service Provider appointed. |  | Target Met | N/A | N/A | BAC minutes/Letter of Appointment.
[8 empty] | N/A | 243 630 1304 | N/A |  | Nil | 800 000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 24 | Community and Social Services | Sports facility | Caluza Sports facility - Phase 1 | 20 | Non-existence of the sport facility. New facility needed. Construction of portal frames structure and installation of concrete palisade fencing. | Completed Phase 1 - Caluza sport facilities | Date of completion of phase 1 of Caluza sport facilities | N/A | 5 500 000 | N/A | MIG | Approved spec by BSC Advertised tender by 30 Sep 2012 | Tender awarded Service Provider appointed by 31 Dec 2012 | service Provider appointed. |  | Target Met | N/A | N/A | BAC minutes
[8 empty] | N/A | 431 360 1301 | N/A |  | Nil | 1500000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 25 | Local Economic Development | Economic Developments Facilities | Informal Trade Structures | 32 | 18 structures needed to boost the second economy | 18 Installed informal trade structures in CBD by June 2013. | No. of installed informal trade structures by Date | N/A | 500 000 | N/A | MIG | Approved spec by BSC Advertised tender by 30 Sep 2012 | Tender awarded Service Provider appointed by 30 Nov 2012 | This has been declared part of PURP by MM office |  | Nil Achieved | Awaited the MM's decision | Still not clear if project must be cancelled and funds be reallocated in the MID-YEAR Review.
[8 empty] | N/A | 241 630 1301 | N/A |  | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 26 | Basic Service Delivery and Infrastructure Development | Public Transport Network System - Multi Year Project | IRPTN - DoT (Multi-year project) | 12,21,22,23,27,32, etc. | Uncoordinated public transport in need of upgrade to safe, cost-effective and efficiency | Completed planning and preliminary design report by 30/6/13 | Date of completed design report | N/A | 111 576 000 | N/A | DOT | Base Data to be completed by 30 Sep 2012 | Model developed by 31 Dec 2012 | Base Data collection and analysis complete |  | Target Partially Met | Because of the delays in the base data collection, according to the revised programme, this milestone will be achieved in April 2013. | Outstanding data has since been received and work is in progress. | December monthly report.
[8 empty] | N/A | 131 601 1301 | N/A |  | 10 577 175 | 14 994 650 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 27 | Local Economic Development | Economic Developments Facilities | Widening of Thwala Rd to incorporate parking & mini taxi rank and trading facilities. (Multi-year project) | 22 | Congested Road with limited parking for business, no trading facilities for second economy businesses and no facilities for passengers. | Completed design report, specs and services plan by 15 Dec'12. 40% construction works completed by June'13 | % of construction works completed | N/A | 6600000 | N/A | DOT | Appointed a consultant. Commenced with the design and investigation of affected services. | Completed design, specification and affected services plan. Commenced with the negotiation with Services Owners in term of reallocation and cost. | TIA/ GEO Survey partially complete |  | Target Partially Met | Ward Councillor delay/objection | Report to be completed end January 2013. | Report.
[8 empty] | N/A | To be advised by Finance | N/A |  | 100000 | 200000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 28 | Local Economic Development | Economic Developments Facilities | Widening of New England Road by adding 1.3km of roadway / lanes. (Multi-year project) | 33 | Congested Road during traffic peak-hour period, limiting ease of access into the CBD | Completed widening of 2.1km of additional roadway. | km of completed roadway. | N/A | 8000000 | N/A | COGTA and CNL | Completed reallocation of services and 65% of roadworks | Completed 2.1km of road widening by 30 November 2012 | Original appointed contractor liquidated. New contractor appointed through a signed cession |  | Nil Achieved | The original appointed contractor was liquidated. This delay construction by more than 4 months. | New contractor appointed and has taken occupation of site. Revised schedule to complete in April'13. | Signed Cession Agreement
[8 empty] | N/A | 131 601 1303 | N/A |  | 4000000 | 4000000 | N/A | N/A | N/A | N/A | N/A | N/A
RSW 29 | Community and Social Services | Sports facility | Construction of 8 lanes Athletics Tracks | 27 | Open soccer field | Completed earthworks and Master Plan drainage by June 2013 | Completed earthworks for 8 lanes Athletic facility | N/A | 2100000 | N/A | DS&R | 100% completion of earthworks for the athletic track - Phase 1 by 30 September 2012 | N/A | Tender awarded. Service Provider appointed by 31 December 2012 |  | Target Met | N/A | N/A | Letter of Appointment.
[8 empty] | N/A | 390 889 0600 | N/A |  | 2 100 000 | Nil | N/A | N/A | N/A | N/A | N/A | N/A
RSW 30 | Local Economic Development | Economic Developments Facilities | Construction of the Tourism Hub Building | 32 | Old bus, taxi terminus and roadway | Completed double story, state of the art tourism FACILITY BY November 2012 | 100% completed building | N/A | 6 500 000 | N/A | COGTA and CNL | Practical completion of double storey internal structural works by October 2012 | 100 % completion of tourism building and handing over to Economic Development | Appointed a new contractor to complete the project. |  | Nil Achieved | The original contractor abandoned the site without any reason. It was requested to return on site to no avail. | The contractor was cancelled and the new contractor appointed to complete the project. The revised schedule is a completion in April'13. Handover of complete contract by 9/01/2013 | BAC minutes/Letter of Appointed for completion contract.
[8 empty] | N/A | 511 630 1301 | N/A |  | 4 500 000 | 2 000 000 | N/A | N/A | N/A | N/A | N/A | N/A

## Landfill Overview
LANDFILL SITE OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | LANDFILL SITE OVERVIEW
| 1.1 | TOTAL PROJECTS: | 9
| 1.1.1 | OPERATING PROJECTS | 0
| 1.1.2 | CAPITAL PROJECTS | 9
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Landfill
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.6. LANDFILL SITE
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LFS 01 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed infrastructure upgrade i.t.o. permit requirements by 30/9/12 | Completed annual infrastructure upgrade by 30/9/12 | N/A | 2 053 000 | 7 500 000 | MIG | Completion of containment berms | Completion of top-soiling of berms | Top- soiling of berm completed | Target Met | N/A | N/A | Site Meeting Minutes
[8 empty] | N/A | 185 100 1680 | 185 469 8556 |  | 2 053 000 | N/A | N/A | N/A | N/A | N/A | N/A
LFS 02 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed infrastructure upgrade i.t.o. permit requirements by 30/9/12 | Completed annual infrastructure upgrade by 30/9/12 | N/A | N/A | N/A | MIG | Completion of access ramps | Installation of weighbridges and billing system | Installation completed | Target Met | N/A | N/A | Site Meeting Minutes
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 03 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed infrastructure upgrade i.t.o. permit requirements by 30/9/12 | Completed annual infrastructure upgrade by 30/9/12 | N/A | N/A | N/A | MIG | Completion of staff changerooms | Construction of changerooms | Construction completed | Target Met | N/A | N/A | Site Meeting Minutes
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 04 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed infrastructure upgrade i.t.o. permit requirements by 30/9/12 | Completed annual infrastructure upgrade by 30/9/12 | N/A | N/A | N/A | MIG | Installtion of new weighbridge | Upgrade of access and perimeter roads | Upgrade completed | Target Met | N/A | N/A | Site Meeting Minutes
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 05 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed infrastructure upgrade i.t.o. permit requirements by 30/9/12 | Completed annual infrastructure upgrade by 30/9/12 | N/A | N/A | N/A | MIG | Upgraded leachate pump system | Leachate pump system fully operational | System fully operational | Target Met | N/A | N/A | Site Meeting Minutes
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 06 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed infrastructure upgrade i.t.o. permit requirements by 30/9/12 | Completed annual infrastructure upgrade by 30/9/12 | N/A | N/A | N/A | MIG | Installation of fence and gates | Fencing complered | Additional fencing installed | Target Met | N/A | N/A | Site Meeting Minutes
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 07 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed infrastructure upgrade i.t.o. permit requirements by 30/9/12 | Completed annual infrastructure upgrade by 30/9/12 | N/A | N/A | N/A | MIG | Completion of road rehabilitation and creation of firebreak | Road rehabilitation completed | Road re-surfaced | Target Met | N/A | N/A | Site Meeting Minutes
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 08 | Basic Service Delivery & Infrastructure Devel. | Minimize waste to Landfill | Materials Recovery & Organic Waste Composting Facilities | All | Non-recycling & composting | Recycle/compost 30% of waste | Functional MRF | N/A | 20 000 000 (COGTA) 3 000 000 (UDM) 1 000 000 (CNL) | N/A | COGTA/UDM/CNL | Signed co-operation agreement with UDM | Signed co-operation agreement | Agreement signed by MM | Target Met | N/A | N/A | Signed Agreement by MM
[10 empty] | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 09 | Basic Service Delivery & Infrastructure Devel. | Minimize waste to Landfill | Establishment of recyclable collectin system | All | Non-collection of domestic recyclables | Waste recycling system at source | Established waste recycling system | N/A | N/A | N/A | COGTA/UDM/CNL | Signed co-operation agreement with UDM | Signed co-operation agreement | Agreement signed by MM | Target Met | N/A | N/A | Signed Agreement by MM
[9 empty] | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A

## CORP SERV COVER
ANNEXURE 1(I): CORPORATE SERVICES BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## CORP SERV overview
CORPORATE SERVICES BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
1 | CORPORATESERVICES BUSINESS UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 58
1.1.1 | OPERATING PROJECTS | 58
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## SOUND GOV overview
SOUND GOVERNANCE UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | SOUND GOVERNANCE UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 19
| 1.1.1 | OPERATING PROJECTS | 19
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Sound Governance
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.1 SOUND GOVERNANCE
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
SG 01 | Good Governance and Public Participation | Secretariat Services | Agendas | N/A | Council & Portfolios Agenda closed 7 days prior to meeting | Council & Portfolios Agenda closed 7 days prior to meeting | Number of Days prior closure of agenda | N/A | N/A | N/A | Council | Council & Portfolios Agenda closed 7 days prior to meeting | Council & Portfolios Agenda closed 7 days prior to meeting | 7 Days prior to meetings |  | Target met | N/A | N/A | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 02 | Good Governance and Public Participation |  |  |  | Exco agenda closed 7 days prior to meeting | Exco agenda closed 6 days prior to meeting |  | N/A | N/A | N/A |  | Exco agenda closed 7 days prior to meeting | Exco agenda closed 7 days prior to meeting | Agenda closed 7 days prior to meetings |  | Target met | N/A | N/A | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 03 | Good Governance and Public Participation |  | Agendas | N/A | Draft Council and Portfolio agenda to Chairperson 6 days prior to meeting | Draft Council and Portfolio agenda to Chairperson 8 days prior to meeting | Number of Days prior closure of agenda | N/A | N/A | N/A | Council | 7 days | 8 days | 8 days prior to meetings |  | Target met | N/A | N/A | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 04 | Good Governance and Public Participation |  |  |  | Draft Exco agenda not seen by Chairperson prior to meeting | Draft Exco agenda to Chairperson 7 days prior to meeting | Number of Days prior meeting | N/A | N/A | N/A |  | Weekly appointment with Chairperson 6 days prior to meeting | Weekly appointment with Chairperson 6 days prior to meeting | 4 days prior to meetings |  | Nil achieved | Chairperson not always readily available | Delegation to go through draft agenda | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 05 | Good Governance and Public Participation | Information Services | Distribution of official documents | N/A | Agenda dispatched to councillors 5 days before the meeting | Agenda dispatched to councillors 7 days before the meeting | Number of days within which agenda is dispatched | N/A | N/A | N/A | Council | Agenda dispatched to councillors 5 days before the mrrting | Agenda dispatched to councillors within 1 day of receipt | Agenda dispatched to councillors within 1 day of receipt |  | Target Met | N/A | N/A | Control sheet register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 06 | Good Governance and Public Participation | Secretariat Services | Minutes | N/A | Draft Minutes signed off with amendments | Draft Minutes signed off without amendments | Number of material amendments | N/A | N/A | N/A | N/A | Draft Minutes signed off without amendments | Draft Minutes signed off without amendments | Minutes signed off without material amendments |  | Target Met | N/A | N/A | Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 07 | Good Governance and Public Participation |  |  |  | Draft Minutes dispatched 7 days after meeting | Draft Minutes dispatched 7 days after meeting | Number of Days within which minutes are dispatcehd | N/A | N/A | N/A | Council | DraftMinutes dispatched 7 days after meeting | DraftMinutes dispatched 7 days after meeting | 3/4 days after meetings |  | Target Exceeded | N/A | N/A | Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 08 | Good Governance and Public Participation |  |  |  | DraftMinutes posted on Intranet 14 days after meeting | DraftMinutes posted on Intranet 7 days after meeting | Number of Days within which minutes are posted on the intranet | N/A | N/A | N/A | N/A | DraftMinutes posted on Intranet 7 days after meeting | DraftMinutes posted on Intranet 7 days after meeting | Draft Minutes posted on L-drive mostly 3/4 days after meetings |  | Target Exceeded | N/A | N/A | Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 09 | Good Governance and Public Participation |  |  |  | Draft Minutes sent for implementation 7 days after meeting (except Economic Development PC) | ALL Draft Minutes sent for implementation 7 days after meeting | Number of Days within which minutes are sent for implementation | N/A | N/A | N/A | Council | ALL Draft Minutes sent for implementation 7 days after meeting | ALL Draft Minutes sent for implementation 7 days after meeting | Actioning done mostly 3/4 days after meetings |  | Target Exceeded | N/A | N/A | Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 10 | Good Governance and Public Participation | Secretariat Services | Minutes | N/A | 3 Committee Officers trained in electronic minute capturing | 4 additional Committee Officers trained in electronic minute capturing | Number of staff undergone training |  | N/A | N/A | N/A | 1 staff member trained | 1 staff member trained | 1 staff member trained |  | Target Met | N/A | N/A | Exco Minutes (list of officials present)
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 11 | Good Governance and Public Participation |  | Calendars | N/A | Annual, monthly, weekly calendar of meetings | 12 weekly calendar of meetings circulated per quarter | Number of weekly calendars |  | N/A | N/A | Council | 12 weekly calendar of meetings circulated | 12 weekly calendar of meetings circulated | 12 weekly calendars) |  | Target Met | N/A | N/A | Weekly calendars)
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 12 | Good Governance and Public Participation |  | Public Participation | All | Secretariat support to public meetings | Secretariat support to public meetings as per demand | meetings attended and Minuted | N/A | N/A | N/A | Council | Secretariat support to public meetings as per demand | Secretariat support to public meetings as per demand | Serviced public participation meeting |  | Target Met | N/A | N/A | Minutes
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 13 | Good Governance and Public Participation | Secretariat Services | Public Participation | All | Minutes finalized within 7 days | Minutes finalized within 7 days | days |  | N/A | N/A | Council | Minutes finalized within 7 days | Minutes finalized within 7 days | Minutes finalized 10 days after meeting |  | Target Partially Met | Meeting Coincided with last Exco meeting before Recess | Meetings to be held weeks before Recess | Minutes
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 14 | Good Governance and Public Participation | Information Management | Document Management System | N/A | Service Level Agreement expired | Renewed SLA by 30/12/12 | date |  | N/A | N/A | Council | Report to PM: ICT | Renewed SLA by 30/12/12 | Renewed SLA by 30/12/12 |  | Nil Achieved | No support from ITC. | Meeting with ITC | Correspondence on file [e-mails]
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 15 | Good Governance and Public Participation |  |  |  | User licenses expired | 6 Renewed licenses by 30/12/12 | Number of licences by due date |  | N/A | N/A | Council | Report to PM: ICT | 6 Renewed licenses by 30/12/12 | 6 Renewed licenses by 30/12/12 |  | Nil Achieved | No support from ITC | Meeting with ITC | Correspondence with ITC on file [e-mails]
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 16 | Good Governance and Public Participation |  |  |  | Outdated ICT infrastructure | 2 New Workstations by 30/12/12 | Number of new workstations by date |  | N/A | N/A | Council | Report to PM: ICT | 2 Workstations: 30/12/12 | 2 Workstations: 30/12/12 |  | Target Met | N/A | N/A | 2 computers at the Info Centre
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 17 | Good Governance and Public Participation |  | Council/ Internal Mail | N/A | Dysfunctional system | 100% effective, efficient internal mail system: adopted plan by manco by 30 August. | date / % | N/A | N/A | N/A | Council | Report to MANCO by 30/8/12 | Internal Mail dispatched within 24 hours of receipt | Internal Mail dispatched within 24 hours of receipt |  | Target Met | N/A | N/A | Circular 34 of 2012
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 18 | Good Governance and Public Participation | Printing Services | Digital Copy Print Production | N/A | Printing completed within 2 working days | Printing completed within 2 working days of receivng requisition from business units | Number of Days |  | N/A | N/A | Council | Printing completed within 2 working days of receivng requisition from business units | Printing completed within 2 working days of receivng requisition from business units | Printing completed within 2 working days of receiving |  | Target Met | N/A | N/A | Record Book
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SG 19 | Good Governance and Public Participation |  | Lithographic print production | N/A | Print Production job completed within 10 working days | Printing completed within 10 working days of receivng requisition from business units | Number of Days | N/A | N/A | N/A | Council | Printing completed within 10 working days of receivng requisition from business units | Printing completed within 10 working days of receivng requisition from business units | Printing completed within 10 working days of receiving requisition |  | Target Met | N/A | N/A | Record Book
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## LEGAL overview
LEGAL SERVICES UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | LEGAL SERVICES UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 3
| 1.1.1 | OPERATING PROJECTS | 3
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Legal Services
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.2 LEGAL SERVICES
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LGL 01 | Good Governance and Public Participation | Bylaws | Bylaws Revision | All | Outdated Bylaws | Five specified bylaws promulgated: electricity; cemeteries; environmental health; informal trading; public amenities. | Specified bylaws promulgated per quarter | 300 000 | N/A | N/A | Council | Two promulgated electricity and cemeteries bylaws | One promulgated environmental health bylaws | First draft completed | Target Partially Met | Draft needs further discussions with Business Unit. | Finalise discussions and embark on promulgation procedure. | Draft Bylaw.
[8 empty] | 5021001056 | N/A | N/A |  | 75 000 | 75 000 | N/A | N/A | N/A | N/A | N/A
LGL 02 | Good Governance and Public Participation | Prosecutions | Review of fines | All | Amounts and penalties have to be reviewed in accordance with inflation/monetary value | Fines for all business units have to be reviewed | % of fines reviewed per quarter | N/A | N/A | N/A | N/A | 100% of fines reviewed for Corporate Services & Community Services | 100% of fines reviewed for Financial Services | Review Process finalised. | Target Met | N/A | N/A | Correspondences with Finance.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LGL 03 | Good Governance and Public Participation | Claims | Risk Guidance | All | Management and staff do not have sufficient knowledge of delictual liability | Key Managers & staff in all Business Units trained on delictual liability | Specified managers & staff from business units trained per quarter | N/A | N/A | N/A | N/A | Key Managers & staff in Corporate Services & Community Services trained on delictual liability | Key Managers & staff in Financial Services trained on delictual liability | Training completed | Target Met | N/A | N/A | Powerpoint presentation
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## ICT overview
INFORMATION COMMUNICATION TECHNOLOGY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | INFORMATION COMMUNICATION TECHNOLOGY UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 7
| 1.1.1 | OPERATING PROJECTS | 7
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## ICT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.3 INFORMATION COMMUNICATION TECHNOLOGY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
ICT 01 | Institutional Development and Transformation | Adoption of A Governance Framework | ICT Charter | N/A | None | Preparation of ICT Charter by 31 Aug 2012 | Date | N/A | N/A | N/A | Nil Required | IT Charter prepared by 31 Aug 2012 | Charter approved by Manco, Exco and Council by 30 Oct 2012 | ICT Charter submitted to portfolio committee in 27 Novcember 2012. Waiting for EXCO and Full Council in January 2013 to resume and be submitted. | Target Partially Met | Target set not realistic and not aligned to the mentioned committee dates. Target should be reworded to 'ICT Charter be submitted' rather than approved. | To set more realisitic targets and align quartely targets with EXCO and Council meeting dates. | Corporate Portfolio Committee of 27 November 2012 minutes.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ICT 02 | Institutional Development and Transformation |  | Master Systems Plan | N/A | None | Up to date MSP | Date | N/A | N/A | N/A | Nil Required | Audit approval of MSP by 31 Aug 2012 | MSP approved by Manco, Exco and Council by 30 Oct 2012 | Master Systems Plan (MSP) is being reviewed as the current one is outdated. | Target Partially Met | Target set not realistic. Input from various departments needs to be factored when developing ICT Plan and this is currently underway.approved. | To set more realisitic targets. To align the MSP targets with PM:ICT's workplan. | PM:ICT Workplan and the current MSP.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A
ICT 03 | Institutional Development and Transformation |  | ICT Steering Committee | N/A | A Committee is in place but attendance is erratic | Fully quorate ICT Steering Committee meets once a month | Number | N/A | N/A | N/A | Nil Required | 3 Meetings per quarter | 3 Meetings per quarter | 2 ICT Steercom meetings have been held. A 3rd (third) ICT Steercom meeting is scheduled for January 2013. | Target Partially Met | No full attendance to the ICT Steercom Meetings resulting in not meeting quoram. | ICT Steercom Terms of Reference to be drawn up and submitted for approval. This will assist in appointing appropriate memebers to the committee. THE ICT Steercom needs to be formalised and officiated via Sound Governace. | The last ICT Steercom Minutes.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ICT 04 | Institutional Development and Transformation | Policies and Procedures | Physical Security Policies | N/A | None | Approval and Implementation of 2 Physical Security Policies | Number | N/A | N/A | N/A | Nil Required | 2 Policies approved by Council by 30 Sep 2012 | 100% Compliance with these policies | Policies submitted to the portfolio committee meeting of the 27 November 2012. All scheduled to be submitted to EXCO in January 2013 once it resumes its functions. | Target Partially Met | Target set not realistic and not aligned to the mentioned committee dates. Target should be reworded to 'Draft ICT Policies be submitted' rather than approved or compliance. | To set more realisitic targets and align quartely targets with EXCO and Council meeting dates. Quarterly target will be revised. | Corporate Portfolio Committee of 27 November 2012 minutes.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ICT 05 | Institutional Development and Transformation |  | Logical Security Policies | N/A | None | Approval and Implementation of 11 Logical Security Policies | Date | N/A | N/A | N/A | Nil Required | 11 Policies approved by Council by 30 Sep 2012 | 100% Compliance with these policies | Policies submitted to the portfolio committee meeting of the 27 November 2012. All scheduled to be submitted to EXCO in January 2013 once it resumes its functions. | Target Partially Met | Target set not realistic and not aligned to the mentioned committee dates. Target should be reworded to 'Draft ICT Policies be submitted' rather than approved or compliance. | To set more realisitic targets and align quartely targets with EXCO and Council meeting dates. Quarterly target will be revised. | Corporate Portfolio Committee of 27 November 2012 minutes.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ICT 06 | Institutional Development and Transformation |  | Minimum Operating Standards | N/A | None | 14 Minimum Operating standards for Unix and Windows are available and complied with | Number | N/A | N/A | N/A | Nil Required | 14 Policies approved by Council by 30 Sep 2012 | 100% Compliance with these policies | Policies submitted to the portfolio committee meeting of the 27 November 2012. All scheduled to be submitted to EXCO in January 2013 once it resumes its functions. | Target Partially Met | Target set not realistic and not aligned to the mentioned committee dates. Target should be reworded to 'Draft ICT Policies be submitted' rather than approved or compliance. | To set more realisitic targets and align quartely targets with EXCO and Council meeting dates. Quarterly target will be revised. | Corporate Portfolio Committee of 27 November 2012 minutes.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ICT 07 | Institutional Development and Transformation |  | Environmental Control Policy for Data Centre | N/A | None | Approval and Implementation of 2 Environmental Controls Policies in Data Centre | Date | N/A | N/A | N/A | Nil Required | 2 Policies approved by Council by 30 Sep 2012 | 100% Compliance with these policies | Policies submitted to the portfolio committee meeting of the 27 November 2012. All scheduled to be submitted to EXCO in January 2013 once it resumes its functions. | Target Partially Met | Target set not realistic and not aligned to the mentioned committee dates. Target should be reworded to 'Draft ICT Policies be submitted' rather than approved or compliance. | To set more realisitic targets and align quartely targets with EXCO and Council meeting dates. Quarterly target will be revised. | Corporate Portfolio Committee of 27 November 2012 minutes.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## HRM, OH, SD, OD overview
HUMAN RESOURCE MANAGEMENT, OCCUPATIONAL HEALTH, ORGANIZATIONAL DEVELOPMENT & SKILLS DEVELOPMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | HRM, OCCUPATIONAL HEALTH, OD & SD UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 29
| 1.1.1 | OPERATING PROJECTS | 29
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## HRM, OD, SD, OH
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.4 HUMAN RESOURCES MANAGEMENT, ORGANIZATIONAL DEVELOPMENT, SKILL DEVELOPMENT & OCCUPATIONAL HEALTH
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | MONTHLY PROGRESS - NOVEMBER 2012 ACTUAL | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
HR 01 | Good Governance and Public Participation | Legislation, Policies and Collective Agreements | Develop and Approve Policy Manual, Employment Policy and Employment Procedure Manual, Parking Policy, Transfer Policy, Staff in Political Offices Policy, Acting Policy, Allocation/ Placement policy, EAP Policy, HIV Policy, Incapacity Policy, Dress Code/ Uniform Policy, Memorial Services and Funerals of Employees Policy, Training and Development Policy, Learnership Policy, Internship Policy, AET Policy, Career & Succession Policy | N/A | Draft Policy | Developed and Approved Policies by the end of the 2nd Quarter | Date | N/A | N/A | N/A | N/A | N/A | Policies Developed. Submitted to SMC | Policies Developed. Submitted to SMC |  | Target Met | N/A | N/A | Policy Document
HR 02 | Good Governance and Public Participation |  | Implement the Policy Manual, Employment Policy and Employment Procedure Manual, Parking Policy, Transfer Policy, Staff in Political Offices Policy, Acting Policy, Allocation/ Placement policy, EAP Policy, HIV Policy, Incapacity Policy, Dress Code/ Uniform Policy, Memorial Services and Funerals of Employees Policy, Training and Development Policy, Learnership Policy, Internship Policy, AET Policy, Career & Succession Policy | N/A | Draft Policy | Implementation of All Polices | Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
HR 03 | Good Governance and Public Participation |  | Sensitisation of Employees on the Policy Manual, Employment Policy and Employment Procedure Manual, Parking Policy, Transfer Policy, Staff in Political Offices Policy, Acting Policy, Allocation/ Placement policy, EAP Policy, HIV Policy, Incapacity Policy, Dress Code/ Uniform Policy, Memorial Services and Funerals of Employees Policy, Training and Development Policy, Learnership Policy, Internship Policy, AET Policy, Career & Succession Policy | N/A | Nil | Employees Sensitised | Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
HR 04 | Good Governance and Public Participation | Human Resources Management | Restructuring of Organisation | N/A | 2008 Re-aligned Structure | Approved organisational structure 30/09/2012 | Date of approval | N/A | N/A | N/A | N/A | Approved organisational structure 30/09/2012 | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
HR 05 |  |  |  | N/A | Job Descriptions for existing Structure Graded but not released | Evaluated JD's for all posts by the end of 4th quarter | Percentage | N/A | N/A | N/A | Business plan to be submitted to DBSA | N/A | Written and Signed off JD's by end of 2nd Quarter | Not Achieved |  | Nil Achieved | Non approval of Structure | Approve Structure | Draft Structure
HR 06 | Good Governance and Public Participation |  | Staff Service Charter (HR) | N/A | Nil | Implemented Staff Service Charter (HR) 30/04/2013 | Date of approval | N/A | N/A | N/A | Nil Required | Draft Charter 30/9/2012 | Stakeholders consulted 31/12/2012 | Stakeholders consulted 31/12/2012 |  | Target Achieved | N/A | N/A | Draft Structure
HR 07 | Good Governance and Public Participation |  | Employee Workshops on Collective agreements | N/A | Nil | Workshops on Collective agreements to all Business Units | Number of workshops | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
HR 08 | Good Governance and Public Participation |  | Industrial Action Strategy | N/A | Nil | Approved Industrial Action Strategy | Date | N/A | N/A | N/A | Nil Required | Stakeholders consulted 30/9/2012 | Industrial Action Strategy submitted to SMC 31/12/12 | Submitted to SMC |  | Target Met | N/A | N/A | Draft Industrial Action Strategy
HR 09 | Good Governance and Public Participation |  | Develop Staff Retention Policy and Strategy | N/A | loss of skilled staff | 100% employees interviewed on exit & quarterly reports and Implementation of Policy and Strategy | % of exit interviews; quarterly reports and Implementation of Policy and Strategy | N/A | N/A | N/A | N/A | 100% exit interviews ; identify scarce skills and 1 quarterly report | 100% exit interviews ; identify scarce skills and 1 quarterly report | Interviews being conducted |  | Target Met | N/A | N/A | Exit Interview Questionairre
HR 10 | Good Governance and Public Participation |  | Recruitment and selection strategy | N/A | None | Approved Recruitment and selection strategy 30/04/2013 | Date | N/A | N/A | N/A | N/A | Crital posts assessed & employment equity status evaluated | Staff Retirements evaluated | Staff Retirements evaluated. Draft Recruitment and Selection Policy |  | Target Met | N/A | N/A | Staff Retirement Report. Draft Policy
HR 11 | Good Governance and Public Participation |  |  |  |  | 100 % Annual Leave Sick-leave & overtime uploaded to payday 31/12/2012 | % annual sickleave & overtime uploaded to payday | 5261001539 | N/A | N/A | N/A | 50% Annual Leave Sick-leave & overtime uploaded to payday | 100 % Annual Leave Sick-leave uploaded to payday 31/12/2012 | 100 % Annual Leave Sick-leave uploaded to payday 31/12/2012 |  | Target Met | N/A | N/A | Leave/ Sickleave Database
[13 empty] | 100 % Annual Overtime uploaded. 31/12/2012 | 100 % Annual Overtime uploaded. 31/12/2012 |  | Target Met | N/A | N/A | Monthly Overtime report
HR 12 | Municipal Transformation & Institutional Development | Skills Development | Implement Workplace Skills Plan | N/A | 30 % of 2011/ 2012 WSP Implemented | 100% implementation of 2012/ 2013 WSP | % implementation of WSP | 2 750 000 | N/A | N/A | Internal and SETA | 25% implementation of WSP | 25% implementation of WSP | Tender Advertised. In evaluation |  | Target Partially Met | N/A | N/A | Tender documents
[8 empty] | 5301301415 | N/A | N/A |  | 600 000 | 600 000 | N/A | N/A | N/A | N/A | N/A | N/A
HR 13 | Municipal Transformation & Institutional Development |  | Develop 2013/ 2014 Workplace Skills Plan | N/A | 2012/ 2013 Work Place Skills Plan | Adopted Workplace Skills Plan | Date of adoption of 2012/ 2013 WSP | N/A | N/A | N/A | SETA | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
HR 14 | Municipal Transformation & Institutional Development | Skills Development | Provision of Learnership | All | Implementation of learnerships | 30 Learners on Learnership Programme | Number of learners | 600 000 | N/A | N/A | Internal and SETA | Appoint Service Provider | 2 Learnerships Implemented | 2 Learnerships Implemented |  | Target Met | N/A | N/A | MOU's / Service Level Agreement
[8 empty] | 5301301422 | N/A | N/A |  | N/A | 300 000 | N/A | N/A | N/A | N/A | N/A | N/A
HR 15 | Municipal Transformation & Institutional Development | Skills Development | Provision of Skills Programmes for Community Members | All –1 per Zone | 4 Skills Programme | 4 Community Skills Programmes Implemented | Number of skills programme implemented | 350 000 | N/A | N/A | Internal and SETA | Needs of Communities Identified and 1 Training programme implemented per Zone | Needs of Communities Identified and 1 Training programme implemented per Zone | Needs of Communities Identified and 1 Training programme to commence in january 2013 |  | Target Met | N/A | N/A | Tender documents
[8 empty] | 5301301420 | N/A | N/A |  | 87 500 | 87 500 | N/A | N/A | N/A | N/A | N/A | N/A
HR 16 | Municipal Transformation & Institutional Development | Skills Development | Trained Councillor's | All | 20 Trained Councillors | 45 Councillor's Trained | Number of Councillors trained | 680 000 | N/A | N/A |  | Training Needs Assessed | Councillors Trained | 15 Councillors Trained |  | Target Met | N/A | N/A | Registration Documents
[8 empty] | 5301301421 | N/A | N/A |  | N/A | 150 000 | N/A | N/A | N/A | N/A | N/A | N/A
HR 17 | Municipal Transformation & Institutional Development | Skills Development | Appoint Interns | All | 32 Interns | 35 Interns Appointed | Number of interns appointed | 1 000 000 | N/A | N/A | Internal | Business Units needs Assessed | 35 Interns Appointed | 25 Interns |  | Target partially Met | Budget Constrains | Re-allocation of funds | Internship Advert, Appointment Letters
[8 empty] | 5301301413 | N/A | N/A |  | N/A | 330 000 | N/A | N/A | N/A | N/A | N/A | N/A
HR 18 | Municipal Transformation & Institutional Development | Skills Development | Awarding of Study Assistance to employees | N/A | 49 | 15 Study Assistance Awarded and 49 Bursaries carried over | Number | 500 000 | N/A | N/A | Internal | Needs of the Municipality Assessed | 15 Study Assistance bursaries awarded | Advertised. Matrix Done |  | Target Partially Met | Reports delayed at SMC | N/A | Reports and Adverts
[8 empty] | 5301001050 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HR 19 | Municipal Transformation & Institutional Development |  | Awarding of External Bursaries | All | 7 External Bursaries Awarded | 10 External Bursaries Awarded | Number of external bursaries awarded | 600 000 | N/A | N/A | Internal | Critical and scarce skills needs of the Municipality Assessed | Awarding 10 Bursaries | Advertised. Matrix Done |  | Target Partially Met | Reports delayed at SMC | N/A | Reports and Adverts
[8 empty] | 5301001055 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HR 20 | Municipal Transformation & Institutional Development | Skills Development | Section 28 Apprenticeships and RPL in Critical and Scarce Skills Areas. | All | 10 Section 28 Apprenticeships | 15 Section 28 Apprenticeships Awarded and RPL conducted | Number of Section 28 Apprenticeships Awarded and RPL conducted | 150 000 | N/A | N/A | Internal and SETA | Assessing critical techical skills needs of the Municipality | Awarding of Section 28 Apprenticeships and RPL | 5 Section 28 Apprenticeships and RPL awarded |  | Target Met | N/A | N/A | Section 28 LGSETA Registration forms
[8 empty] | 5301001404 | N/A | N/A |  | N/A | 50 000 | N/A | N/A | N/A | N/A | N/A | N/A
HR 21 | Municipal Transformation & Institutional Development | Occupational Health and Safety | Occupational Health awareness events | N/A | 2 Occupational Health Events 2011/2012 | 2 Occupational Health awareness events | Number of occupational health awareness events | 200 000 | N/A | N/A | Council | Event Planning | 1 Occupational Health awareness event | 1 Occupational Health awareness event |  | Target Met | N/A | N/A | Posters, Reports
[8 empty] | 3461001670 | N/A | N/A |  | N/A | 100 000 | N/A | N/A | N/A | N/A | N/A | N/A
HR 22 | Municipal Transformation & Institutional Development |  | Risk employee medicals | N/A | Nil | 100% Risk Employee Database | % Risk Employee Database | N/A | N/A | N/A | Nil Required | 100% Employee Risk Database | Maintain Database | Database Maintained |  | Target Met | N/A | N/A | Database
HR 23 |  |  |  |  | 10% | 50% of identified high risk employees medicals conducted | % Risk employees medicals conducted |  | N/A | N/A | Council | 15% of identified high risk Employee medicals conducted | 15% of identified high risk Employee medicals conducted | 15% of identified high risk Employee medicals conducted |  | Target Met | N/A | N/A | Medical Documents
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HR 24 | Municipal Transformation & Institutional Development |  | Risk Assessments of work environments | N/A | Nil | Risk Environment database | % of Database Complete | N/A | N/A | N/A | Nil Required | 100% Risk Environment database | Maintain Database | Database Maintained |  | Target Met | N/A | N/A | Database
HR 25 |  |  |  |  | 50% | 100% Risk Assessments of Work environments | % | 100 000 | N/A | N/A | Council | 25% Risk Assessments of Work environments | 50% Risk Assessments of Work environments | 50% Risk Assessments of Work environments |  | Target Met | N/A | N/A | Assessment Schedules
[8 empty] | 3461001670 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HR 26 | Municipal Transformation & Institutional Development | Organisational Development | Conduct climate survey in order to determine baseline | N/A | Climate Survey 2007 | Climate survey Outcomes Report 30/03/2012 | Date of outcomes report | 100 000 | N/A | N/A | Council | N/A | Approved Plan | Outcomes report Completed |  | Target Exceeded | N/A | N/A | Outcomes Report
[8 empty] | 5301001612 | N/A | N/A |  | N/A | 100 000 | N/A | N/A | N/A | N/A | N/A | N/A
HR 27 | Municipal Transformation & Institutional Development |  | Process Mapping | N/A | No Written Processes | Approved Process Manuals (4) | Number of approved process manuals | N/A | N/A | N/A | Council | Traffic, Waste, Parks Processes Mapped | 3 Process Manuals completed & approved | Development of KPA |  | Target Partially Met | Lack of commitment from BU | Training for Process Managers 3rd Quarter | KPA Manual
HR 28 | Municipal Transformation & Institutional Development |  | Team Building | N/A | None | Team Building for Senior Managers 28/02/2013 | Date | 100 000 | N/A | N/A | Council | N/A | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | 100 000 | N/A | N/A | N/A | N/A | N/A | N/A
OTS 01 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, | Capacity Enhancement | Ward Committee Training | All | N/A | 20 ward committee training sessions | Number of sessions held | 350 000 | N/A | N/A | MSIG | Specifications and award of tender | N/A | N/A |  | Not Applicable | N/A | N/A | N/A
[8 empty] | 201001643 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## ECON DEV COVER
ANNEXURE 1(J): ECONOMIC DEVELOPMENT BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## Econ Dev Overview
ECONOMIC DEVELOPMENT BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | DEVELOPMENT SERVICES BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 38
| 1.1.1 | OPERATING PROJECTS | 38
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## LOCAL Eco DEV Overview
LOCAL ECONOMIC DEVELOPMENT BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
| 1 | LOCAL ECONOMIC DEVELOPMENT BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 12
| 1.1.1 | OPERATING PROJECTS | 12
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Local Economic Development
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
6.1 ECONOMIC DEVELOPMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LED 01 | Social and Economic Development | Job Creation | Job Creation and income opportunities | All wards | 1000 job opportunities | 1000 job opportunities created | Number of job opportunities created | 2 000 000 | N/A | N/A | Cogta funding | 250 job opportunities created | 250 job opportunities created | 250 | Target Exceeded | N/A | N/A | CWP Report
[9 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 02 | Social and Economic Development | Municipal wide LED strategy development | Review of LED strategy | N/A | 2008 LED Strategy | Reviewed and Approved strategy by 28 February 2013; 100% implementation of strategy by June 2013 | Date of approval and % of implementation of strategy | N/A | N/A | N/A | No funding required | 2008 strategy and benchmark process reviewed | Stakeholder consultation completed and first draft produced | Approved terms of reference Cogta consultation process completed and draft report produced | Target Met | N/A | N/A | Led Bench mark report
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 03 | Social and Economic Development | Business retention and expansion | Business retention and expansion (BR&E) survey | All wards | 0 | 100% completed BR&E programme | % completion | 40 000 | N/A | N/A | TIKZN | Volunteers trained and business visitation completed | Data analysed, and action plans completed and approved | Nil | Nil Achieved | MIDI withdrew from programme | Project Move to the third quarter | nil
[9 empty] | N/A | N/A | N/A | 20 000 | 20 000 | N/A | N/A | N/A | N/A | N/A
LED 04 | Social and Economic Development |  | Facilitate registration and mentorship of co-operatives | All wards | 0 | Facilitate registration and mentorship of 8 co-operatives | number of co-operatives established | N/A | N/A | N/A | No funding required | 2 co-operatives | 2 co-operatives | 3Registered | TARGET exceeded | N/A | N/A | registration certificates and Business Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 05 | Social and Economic Development | SMME infrastructure development | Upgrading of 2 satellite markets (Kwa-Shange & Kwa Mncane) | 4 and 8 | 0 | Completed business plan and funding application by 31 December 2012 | Date of completed business plan and funding application | N/A | N/A | N/A | N/A | Business plan completed 100% | Funding application completed -100% | Funding Application document completed | Target Exceeded | N/A | N/A | Business Plan
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 06 | Social and Economic Development | Compilation of informal economy database | Compilation and review of informal economy data base | All wards | 0 | completed informal economy data base by 30 June 2013 | Date of completed informal economy database | N/A | N/A | N/A | No funding required | Survey of Street trading sector completed | Survey of waste collectors/ recyclers completed | Survey of waste pickers completed | Target met | N/A | N/A | Database of wate Pickers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 07 | Social and Economic Development | SMME Development | Training workshops: Health and safety, basic business, finance | All wards | 6 workshops | 8 training workshops conducted | Number of workshops conducted | N/A | N/A | N/A | No funding required | 2 training workshops conducted | 2 training workshops conducted | 3 tourism training workshops held with PMB tourism | Target Exceeded | N/A | N/A | Attendance Registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Social and Economic Development | Informal traders development | Training workshops: Health and safety | All wards | 8 workshops | 8 training workshops | Number of workshops conducted | N/A | N/A | N/A | No funding required |  | 2 training workshops conducted | 3 Workshpos Conducted | Target Exceeded | N/A | N/A | Attendance Registers
LED 08 | Social and Economic Development | AirPort Development | Develop an Airport Master Plan | N/A | N/A | Complete and approved Airport Master Plan before 31 December 2012 | Date of completed, approved masterplan | 250 000 | N/A | N/A | KZN TREASURY | Consultant's appointment extended; review of master plan commenced | Master plan completed and approved by 31 December 2012 | MasterPlan approved | Target Met | N/A | N/A | MasterPlan Report
[9 empty] | N/A | N/A |  | N/A | 250 000 | N/A | N/A | N/A | N/A | N/A
LED 09 | Social and Economic Development | Municipal Market Operations | Maintain relations with Agents through monthly meetings | N/A | Monthly meetings | 10 monthly meetings to be held | number of monthly meetings | N/A | N/A | N/A | N/A | 3 monthly meetings | 2 monthly meetings | 4 | Target Exceeded | N/A | N/A | Minutes of meetings
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 10 | Social and economic development | Job creation and expansion of rates base | Sale of commercial land | All | 2 commercial sites | 2 (commercial) land sales by 30/06/2013 | Number of commercial land sales | 50 000 | N/A | N/A | Council | Dept. circulation 30/09/2012 | Council approval 30/11/2012 | Draft advert put on hold | Nil Achieved | Application from adjoining landowner received | Finalize application for expansion | Application for expansion
[8 empty] | 2401001000 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 11 | Social and Economic Development | Job creation and expansion of rates base | Sale of industrial land | All | 4 industrial sites | 4 (industrial) land sales by 30/06/2013 | Number of industrial land sales | N/A | N/A | N/A | Council | 1 industrial land sale | 1 industrial land sale | 1 site allocated; price finalized | Target Met | N/A | N/A | Site diagram and valuation certificate
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 12 | Social and Economic Development | Compliance with MPRA | New GV for July 2014 | All | Previous GV in 2008 | 60% of GV in 2012/2013 | Percentage | 11200000 | N/A | N/A | Council | Data collection and land audit 15% | Data collection and land audit 15% | Bid spec report for advertising tender approved; council stood down report | Target Partially Met | Awaiting decision from council on tender | Fast track the appointment of a service provider. | N/A
[8 empty] | 242 100 1575 and 242 100 3090 | N/A | N/A |  | 3 300 000 | 3 300 000 | N/A | N/A | N/A | N/A | N/A
.

## Infra Planing overview
INFRASTRUCTURE PLANNING & SURVEY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
1 | INFRASTRUCTURE PLANNING & SURVEY UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 19
1.1.1 | OPERATING PROJECTS | 19
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Infra planning & Survey
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
6.2 INFRASTRUCTURE PLANNING & SURVEY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
HS 01 | Basic Service Delivery | Housing Delivery | Edendale J2 & Quarry | 15 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies | Date of submission of application | N/A | N/A | N/A | DOHS | Applied to DOHS for appointment of Implementing Agent (IA) for Stage 1 feasibility Studies | N/A (Completed Quarter 1) | N/A | Not Applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 02 | Basic Service Delivery |  | Willowfountain: Bulwer | 14 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies | Date of submission of application | N/A | N/A | N/A | DOHS | Applied to DOHS for appointment of Implementing Agent (IA) for Stage 1 feasibility Studies | N/A (Completed Quarter 1) | N/A | Not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 03 | Basic Service Delivery |  | Khalanyoni | 12 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies | Date of submission of application | N/A | N/A | N/A | DOHS | Applied to DOHS for appointment of Implementing Agent (IA) for Stage 1 feasibility Studies | N/A (Completed Quarter 1) | N/A | Not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 04 | Basic Service Delivery |  | Kwa Thirty | 10 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies | Date of submission of application | N/A | N/A | N/A | DOHS | Applied to DOHS for appointment of Implementing Agent (IA) for Stage 1 feasibility Studies | N/A (Completed Quarter 1) | N/A | Not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 05 | Basic Service Delivery |  | Hollingwood | 35 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies | Date of submission of application | N/A | N/A | N/A | DOHS and NHFC | Applied to DOHS for appointment of Implementing Agent (IA) for Stage 1 feasibility Studies | N/A | N/A | Not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 06 | Basic Service Delivery |  | Edendale S - 8 Ext | 10 | IA appointed | Monitoring and Management of IA for completion of feasibility Studies by 30/06/2013 | Date of completion of Stage 1 feasibility studies. | N/A | N/A | N/A | DOHS | Management of IA - To assemble professional team, and Start Feasibility studies | Management of IA - To achieve 50% completion of feasibility Studies. | feasibility studies 50% completed. | Target Met | N/A | N/A | Project Status Report.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 07 | Basic Service Delivery |  | Edendale S - 3 to 8 | 10 & 15 | Incomplete Services | Outstanding services for 2,010 Sites completed by IA by 30/06/2013 | No. of Sites completed with services | N/A | N/A | N/A | DOHS | 500 Sites completed with services | 355 Sites completed with services | Meetings | Target Partially Met | Rain Delays | Ext of time granted | Minutes of Site meetings
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 08 | Basic Service Delivery |  | Edendale T2 & T3 | 15 | Incomplete Services | Outstanding Services for 231 Sites completed by IA by 30/06/2013 | No. of Sites completed with services | N/A | N/A | N/A | DOHS | 75 Sites completed with services | 75 Sites completed with services | 50 Sites completed with services | Target Partially Met | Rain Delays | Ext of time granted | Minutes of Site meetings
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 09 | Basic Service Delivery |  | Msunduzi Wirewall | Various | 1100 | Management of IA for the competion of 340 Units by 30/06/2013. | No. of Houses completed | N/A | N/A | N/A | DOHS | N/A | 100 Houses completed | Nil | Nil Achieved | Awaiting approval by the National Department. | Currently being managed by Provincial DoHS. | Correspondence from DOHS
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 10 | Basic Service Delivery |  | Willowfountain EE - Phase1 | 14 | 127 | Management of IA to Construct 73 units completed by 30/03/2013 | No. of Houses completed | N/A | N/A | N/A | DOHS | Tripartite Agreement signed by 30/9/12 | 30 units to be completed by IA | Nil | Nil Achieved | Delays in finalizing the Agreement. And rain delays. | All issues have been resolved. | Signed Agreement and Development Programme
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 11 | Basic Service Delivery | Housing Delivery | Lot 182 Snating | 11 | 0 | Management of IA to construct 133 Units completed by 30/06/2013 | No. of Houses completed | N/A | N/A | N/A | DOHS | Tripartite Agreement signed by 30/9/12 | 40 units to be completed by IA | Nil | Nil Achieved | Delays in finalizing the Agreement. And rain delays. | All issues have been resolved. | Signed Agreement and Development Programme
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 12 | Basic Service Delivery |  | Edendale T2 & T3 | 15 | 113 | Management of IA to construct 357 Units completed by 30/06/2013 | No. of Houses completed | N/A | N/A | N/A | DOHS | N/A | 100 Houses completed | Nil | Nil Achieved | Building Plan approval. | Approve building plan | Project status report.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 13 | Basic Service Delivery |  | Transfer of Houses | Various Wards | Nil | Land Legal issues resolved | Date | N/A | N/A | N/A | DOHS | Land Legal issues resolved by 30/09/2012 | N/A | N/A | Not Applicable | Draft report awaiting comments of CFO. | Obtain comments of CFO. | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 14 | Basic Service Delivery |  | Cleaning of ablutions for Masukwane Emergency Housing Scheme | 33 | Nil | Ablutions cleaned weekly | Weekly cleaning | 560 000 | N/A | N/A | Council | Repairs completed and cleaned weekly | Masukwane Ablutions Cleaned weekly | Nil | Nil Achieved | Meeting held with Community, people are reluctant to stop illegal activities. | Further discussions and engagement with community and security needed. | Notice of Meeting and Minutes
[8 empty] | 5601001195 | N/A | N/A |  | 200 000 | 120000 | N/A | N/A | N/A | N/A | N/A
HS 15 | Basic Service Delivery | Rental Housing | Maintenance of rental stock | 24, 33 | R498,000 spent in 2010/11 on maintenance | 100% implementation of 2012/13 Maintenance Plan | % implementation of maintenance plan | 1 200 000 | N/A | N/A | Council | 25% implementation of 2012/13 Maintenance Plan | 25% implementation of 2012/13 Maintenance Plan | 10% | Nil Achieved | Delays with Expenditure Committee & Procurement Proc ess (unpaid accounts) | To procure service providers. To liaise with workshop manager on means and ways to speed up repairs & mainteance work. | Procurement Proformas & motivations. Time sheets & works orders for work done.
[8 empty] | All 1327 votes 586 - 695 | N/A | N/A |  | 300 000 | 300 000 | 117200 | N/A | N/A | N/A | N/A
HS 16 | Basic Service Delivery | Rental Housing | Transfer of Rental Stock under EEDBS Policy | All Wards | Nil | Progress reports on Investigation on transfer of flats submitted to MANCO & Council | Quarterly Progress Reports | N/A | N/A | N/A | DOHS | Report submitted to MANCO & Council | Report submitted to MANCO & Council | Quarterly report in progress | Target Partially Met | Difficulty with getting information from DOHS during December period | Make contact early January 2013 | Draft Report. Records of phone calls.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 17 | Basic Service Delivery | Housing Needs | Housing Needs Register (Waiting List) | All Wards | Inefficient operations | Operational Housing Needs Register in place by 31/12/2012 | Date of operational register in place | 33 106 | N/A | N/A | Council | Training of staff | Operational Housing Needs Register in place by 31/12/2012 | Housing Needs Register software in place. Registered on HSS system. | Target Partially Met | Delays at National level | Ensure link up with National database provided to begin capturing names. | Emails from Provincial DOHS.
[8 empty] | 265-100-1195 | N/A | N/A |  | N/A | 33 106 | Nil | N/A | N/A | N/A | N/A
HS 18 | Basic Service Delivery |  |  | All Wards | Nil | 5,000 names captured on Housing Register | Number of names captured on Register | N/A | N/A | N/A | Nil Required | 500 names captured on Housing Register | 1500 names captured on Housing Register | N/A | Nil Achieved | Awaiting above | Commence capturing names and other data on site ASAP | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HS 19 | Basic Service Delivery | Building Plan Approval / Archival | Installation of Electronic Plan Approval System | All Wards | Inefficient operations | New Electronic Plan Approval system installed by 30/06/2013 | Date of installed system | 1 500 000 | N/A | N/A | CNL / COGTA | Advertise tender | Service Provider appointed | Report submitted to Bid Spec Committee for start of Procurement Process | Nil Achieved | Delays in getting specifications approved through ICT Steering Committee | Fast-track through Procurement Process | Report to Bid Spec Committee
[8 empty] | 547-100- | N/A | N/A |  | 30 000 | 140 000 | N/A | N/A | N/A | N/A | N/A

## Gedi overview
GEDI, PLANNING, ENVIRONMENTAL & LICENSING UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 2 (OCTOBER - DECEMBER 2012) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
NIL ACHIEVED
TARGET PARTIALLY MET
TARGET MET
TARGET EXCEEDED
NOT APPLICABLE
NO INFORMATION RECEIVED
1 | GEDI, PLANNING, ENVIRONMENTAL & LICENSING UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 7
1.1.1 | OPERATING PROJECTS | 7
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## GEDI, EH, Plan & Lic
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
6.3 GEDI, PLANNING, ENVIRONMENTAL & LICENSING
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 2 - ENDING DECEMBER 2012
[8 empty] | VOTE | VOTE | VOTE |  | Q1 PERFORMANCE TARGET | QUARTERLY TARGET (OCTOBER - DECEMBER) | QUARTERLY PROGRESS (OCTOBER - DECEMBER) | ACTUAL (Target Met, Nil Achieved, Target Partially Met, Target Exceeded, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
PLN 01 | Social & Economic Development | Tenure upgrades and anomaly rectification | Property tenure upgrades | All wards | 21762 | 1500 property tenure upgrades | Number Of Property tenures upgraded | 20 000 | N/A | N/A | DoHS / DRDLR | Resolve underlying land issues | Resolve underlying land issues | Gazette notice still not published, 14 weeks overdue | target partially met | Gazette notice still not published, 14 weeks overdue | Pressure DoHS to publish Gazette notice | emails and correspondence relating to gazette publishing
[8 empty] | 2851001643 | N/A | N/A |  | 5000 | 5000 | N/A | N/A | N/A | N/A | N/A
PLN 02 | Social & Economic Development | Land Expropriation | Private Property expropriation | All wards | No properties expropriated as yet | 63 properties expropriated | Number Of Properties expropriated | 10 000 000 | N/A | N/A | DoHS / DRDLR | Legal matters dealt with prior to expropriation | Legal matters dealt with prior to expropriation | designation of properties gazetted, tho not fully | target partially met | Gazette from DRDLR was incorrect. | Republish gazette notice for all properties | Gazette notice from DRDLR
[8 empty] | 2851001643 | N/A | N/A |  | 50 000 | 50 000 | N/A | N/A | N/A | N/A | N/A
PLN 03 | Spatial Planning | LOCAL AREA PLANS | South Eastern District Local area Plan | 18 | No local area plans yet completed | Inception Report for South Eastern District completed by 30th June 2013 | Date of completed inception report | 500 000 | N/A | N/A | COGTA, Council | Bid Adjudication Process Completed | Consultants Appointed | Consultants Appointed | Target Met | N/A | N/A | Consultants letter of appointment
[8 empty] | No Vote assigned yet | N/A | N/A |  | 0 | 20000 | N/A | N/A | N/A | N/A | N/A
PLN 04 | Spatial Planning |  | Inner City Development and Regeneration Plan | 37 | No local area plans yet completed | Inception Report for Inner City Development completed by 30th June 2013 | Date of completed inception report | 500 000 | N/A | N/A | COGTA, Council | Bid Adjudication Process Completed | Consultants Appointed | Consultants Appointed | Target Met | N/A | N/A | Consultants letter of appointment
[8 empty] | 548100…. | N/A | N/A |  | 0 | 20 000 | N/A | N/A | N/A | N/A | N/A
PLN 05 | Spatial Planning | TOWN PLANNING SCHEME EXTENSION | Edendale & Sobantu Town Planning Scheme | 18, 21, 33 | No Town Planning schemes for these two areas | Inception Report for Town Planning scheme extension completed by 30th June 2013 | Date of completed inception report | 500 000 | N/A | N/A | COGTA, Council | Bid Adjudication Process Completed | Consultants Appointed | Consultants Appointed | Target Met | N/A | N/A | Consultants letter of appointment
[8 empty] | 548100…. | N/A | N/A |  | 0 | 20 000 | N/A | N/A | N/A | N/A | N/A
PLN 06 | Spatial Planning | Climate change | Climate change adaptation policy | All wards | No policy | Policy Approved by Council by 30/6/13 | Date of approved policy | N/A | N/A | N/A | Nil Required | Carbon disclosure program completed | Climate change draft policy completed | Draft Policy Completed | Target Met | N/A | N/A | Draft Policy document
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLN 07 | Spatial Planning | Ecosystem Services Plan | Interim Ecosystem Services Plan | All wards | No Ecosystems Plan in place | 3 zonal reports completed by 30th June 2013 | Date of completed zonal reports | N/A | N/A | N/A | Nil | Priority zones identified,prioritised, and top 3 chosen. | Research first zone in detail, report completed | 1st Zonal report completed ( Albany Park) | Target Met | N/A | N/A | 1st Zonal Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Sheet1 (hidden)
.
Nil Achieved
Target Partially Met
Target Met
Target Exceeded
Not Applicable

## Sheet5 (hidden)
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 4.02% | 8.36%
TARGET PARTIALLY MET | 25.83% | 21.73%
TARGET MET | 47.31% | 42.8% | organisational rep - operating projects
TARGET EXCEEDED | 7.38% | 9.36%
NOT APPLICABLE | 15.43% | 17.72%
NO INFORMATION RECEIVED | 0.68%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 1.49% | 11.94%
TARGET PARTIALLY MET | 38.9% | 32.83%
TARGET MET | 47.76% | 34.22% | organisational rep - capital projects
TARGET EXCEEDED | 10.44% | 19.4%
NOT APPLICABLE | 1.49% | 1.49%
NO INFORMATION RECEIVED | 1.09%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 7.24% | 7.24%
TARGET PARTIALLY MET | 23.18% | 20.28%
TARGET MET | 36.23% | 34.78% | business unit rep - cbu - operating
TARGET EXCEEDED | 2.89% | 1.44%
NOT APPLICABLE | 30.43% | 36.23%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 6.66% | 1.33%
TARGET PARTIALLY MET | 20% | 6.66%
TARGET MET | 6.66% | 33.33% | sub unit rep - internal audit - operating
TARGET EXCEEDED | 13.3% | 6.66%
NOT APPLICABLE | 53.3% | 40%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 5.4% | 2.7%
TARGET PARTIALLY MET | 24.32% | 21.62%
TARGET MET | 43.24% | 35.13% | sub unit rep - office of the mm - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 27.02% | 40.54%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100%
NIL ACHIEVED | 18.18%
TARGET PARTIALLY MET | 9.1%
TARGET MET | 72.72% |  | sub unit rep - mayoral special projects - capital
TARGET EXCEEDED | 0%
NOT APPLICABLE | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 18.18% | 18.18%
TARGET PARTIALLY MET | 0% | 18.18%
TARGET MET | 54.54% | 27.27% | sub unit rep - IDP - Operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 27.27% | 36.36%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 66.66% | 50%
TARGET MET | 33.33% | 50% | sub unit rep - marketing - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 2.08% | 0%
TARGET PARTIALLY MET | 22.91% | 20.83%
TARGET MET | 45.83% | 50% | business unit rep - finance - operating
TARGET EXCEEDED | 2.08% | 6.25%
NOT APPLICABLE | 27.08% | 22.91%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 9.09% | 0%
TARGET PARTIALLY MET | 27.27% | 18.18%
TARGET MET | 18.18% | 36.36% | sub unit rep - budget & treasury - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 45.45% | 45.45%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 23.07% | 0%
TARGET MET | 53.84% | 69.23% | sub unit rep - expenditure - operating
TARGET EXCEEDED | 0% | 23.07%
NOT APPLICABLE | 23.07% | 7.69%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 15.38% | 46.15%
TARGET MET | 46.15% | 53.84% | sub unit rep - revenue management - operating
TARGET EXCEEDED | 7.69% | 0%
NOT APPLICABLE | 30.76% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 27.27% | 18.18%
TARGET MET | 63.63% | 36.36% | sub unit rep - SCM - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 9.09% | 45.45%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 4.05% | 8.1%
TARGET PARTIALLY MET | 27.02% | 21.62%
TARGET MET | 43.24% | 45.94% | business unit rep - community services - operating
TARGET EXCEEDED | 20.27% | 20.27%
NOT APPLICABLE | 5.4% | 4.05%
NO INFORMATION RECEIVED | 3.5%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 50% | 50%
TARGET MET | 50% | 50% | business unit rep - community services - capital
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 3.03%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 16.16%
TARGET PARTIALLY MET | 8.33% | 16.16%
TARGET MET | 66.66% | 41.66% | sub unit rep - ABM - operating
TARGET EXCEEDED | 8.33% | 8.33%
NOT APPLICABLE | 16.66% | 16.66%
NO INFORMATION RECEIVED
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 8.33% | 0%
TARGET PARTIALLY MET | 8.33% | 33.33%
TARGET MET | 28% | 20.83% | sub unit rep - HSS - operating
TARGET EXCEEDED | 44% | 41.66%
NOT APPLICABLE | 8.33% | 4.16%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 4% | 16.16%
TARGET PARTIALLY MET | 40% | 16.16%
TARGET MET | 52% | 68% | sub unit rep - community development - operating
TARGET EXCEEDED | 4% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 50% | 50%
TARGET MET | 50% | 50% | sub unit rep - community development - capital
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 53.84% | 15.38% | sub unit rep - psdm - operating
TARGET MET | 30.7% | 53.84%
TARGET EXCEEDED | 15.38% | 30.76%
NOT APPLICABLE | 0% | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 16.66% | 33.33%
TARGET MET | 75% | 58.33% | business unit rep - ISF - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 8.33% | 8.33%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 1.53% | 12.3%
TARGET PARTIALLY MET | 38.46% | 32.3%
TARGET MET | 47.69% | 33.84% | business unit rep - ISF - capital
TARGET EXCEEDED | 10.76% | 20%
NOT APPLICABLE | 1.78% | 1.53%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 7.14% | 57.14%
TARGET MET | 64.28% | 35.71% | sub unit rep - water & sanitation - capital
TARGET EXCEEDED | 21.42% | 7.14%
NOT APPLICABLE | 7.14% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 0% | 0%
TARGET MET | 100% | 100% | sub unit rep - Electricity - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 8.33% | 8.33%
TARGET PARTIALLY MET | 41.66% | 33.33%
TARGET MET | 41.66% | 8.33% | sub unit rep - Electricity - capital
TARGET EXCEEDED | 8.33% | 50%
NOT APPLICABLE | 0% | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 40% | 60%
TARGET MET | 40% | 20% | sub unit rep - Fleet - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 20% | 20%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 0% | 16.16%
TARGET MET | 100% | 83.83% | sub unit rep - PMU - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 23.33%
TARGET PARTIALLY MET | 53.33% | 30%
TARGET MET | 36.66% | 23.33% | sub unit rep - roads & stormwater - capital
TARGET EXCEEDED | 10% | 20%
NOT APPLICABLE | 0% | 3.33%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 6.89%
TARGET PARTIALLY MET | 26.31% | 24.13%
TARGET MET | 64.91% | 50% | business unit rep - corporate services - operating
TARGET EXCEEDED | 0% | 6.89%
NOT APPLICABLE | 8.77% | 12.06%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 15.78%
TARGET PARTIALLY MET | 15.78% | 5.26%
TARGET MET | 84.21% | 63.15% | sub unit rep - sound governance - operating
TARGET EXCEEDED | 0% | 15.78%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 66.66% | 33.33%
TARGET MET | 33.33% | 66.66% | sub unit rep - legal - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 71.42% | 100%
TARGET MET | 28.57% | 0% | sub unit rep - ICT - operating
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 3.44%
TARGET PARTIALLY MET | 17.85% | 17.24%
TARGET MET | 64.28% | 51.72% | sub unit rep - HRD, OCC H, SD, OD - operating
TARGET EXCEEDED | 0% | 3.44%
NOT APPLICABLE | 17.85% | 24.13%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 7.89% | 26.31%
TARGET PARTIALLY MET | 34.21% | 18.42%
TARGET MET | 42.1% | 26.31% | business unit rep - economic development - operating
TARGET EXCEEDED | 10.52% | 13.15%
NOT APPLICABLE | 5.26% | 15.78%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 16.66%
TARGET PARTIALLY MET | 33.33% | 8.33%
TARGET MET | 50% | 33.33% | sub unit rep - ED - operating
TARGET EXCEEDED | 16.66% | 41.66%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 15.78% | 42.1%
TARGET PARTIALLY MET | 26.31% | 21.05%
TARGET MET | 42.1% | 5.26% | sub unit rep - housing - operating
TARGET EXCEEDED | 5.26% | 0%
NOT APPLICABLE | 10.52% | 31.57%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 57.14% | 28.57%
TARGET MET | 28.57% | 71.42% | sub unit rep - Gedi, EH, Plan & Licensing - operating
TARGET EXCEEDED | 14.28% | 0%
NOT APPLICABLE | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100%
NIL ACHIEVED | 0% | 0%
TARGET PARTIALLY MET | 33.33% | 0%
TARGET MET | 66.66% | 100% | sub unit rep - landfill capital
TARGET EXCEEDED | 0% | 0%
NOT APPLICABLE | 0% | 0%

## Sheet6 (hidden)
Organisational Representation - 365
| Capital Projects |  | 67 | Operating Projects |  | 299
| Colour | Number | % | Colour | Number | %
| Red | 8 | 11.94% | Red | 25 | 8.36%
| Orange | 22 | 32.83% | Orange | 65 | 21.73%
| Green | 23 | 34.22% | Green | 128 | 42.8%
| Blue | 13 | 19.4% | Blue | 28 | 9.36%
| Yellow | 1 | 1.49% | Yellow | 53 | 17.72%
Business Unit Representation - CBU 69
|  |  |  | Operating Projects |  | 69
|  |  |  | Colour | Number | %
|  |  |  | Red | 5 | 7.24%
|  |  |  | Orange | 14 | 20.28%
|  |  |  | Green | 24 | 34.78%
|  |  |  | Blue | 1 | 1.44%
|  |  |  | Yellow | 25 | 36.23%
Sub Unit Representation - Internal Audit 15
|  |  |  | Operating Projects |  | 15
|  |  |  | Colour | Number | %
|  |  |  | Red | 2 | 1.33%
|  |  |  | Orange | 1 | 6.66%
|  |  |  | Green | 5 | 33.33%
|  |  |  | Blue | 1 | 6.66%
|  |  |  | Yellow | 6 | 40%
Sub Unit Representation - Office of the MM - 37
|  |  |  | Operating Projects |  | 37
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 2.7%
|  |  |  | Orange | 8 | 21.62%
|  |  |  | Green | 13 | 35.13%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 15 | 40.54%
Sub Unit Representation - IDP 11
|  |  |  | Operating Projects |  | 11
|  |  |  | Colour | Number | %
|  |  |  | Red | 2 | 18.18%
|  |  |  | Orange | 2 | 18.18%
|  |  |  | Green | 3 | 27.27%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 4 | 36.36%
Sub Unit Representation - Marketing 6
|  |  |  | Operating Projects |  | 6
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 3 | 50%
|  |  |  | Green | 3 | 50%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Business Unit Representation - Finance 48
|  |  |  | Operating Projects |  | 48
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 10 | 20.83%
|  |  |  | Green | 24 | 50%
|  |  |  | Blue | 3 | 6.25%
|  |  |  | Yellow | 11 | 22.91%
Sub Unit Representation - Budget & Treasury 11
|  |  |  | Operating Projects |  | 11
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 18.18%
|  |  |  | Green | 4 | 36.36%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 5 | 45.45%
Sub Unit Representation - expenditure management 13
|  |  |  | Operating Projects |  | 13
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 0 | 0%
|  |  |  | Green | 9 | 69.23%
|  |  |  | Blue | 3 | 23.07%
|  |  |  | Yellow | 1 | 7.69%
Sub Unit Representation - Revenue Management 13
|  |  |  | Operating Projects |  | 13
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 6 | 46.15%
|  |  |  | Green | 7 | 53.84%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - supply chain Management 11
|  |  |  | Operating Projects |  | 11
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 18.18%
|  |  |  | Green | 4 | 36.36%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 5 | 45.45%
Business Unit Representation - Community Services 76
| Capital Projects |  | 2 | Operating Projects |  | 74
| Colour | Number | % | Colour | Number | %
| Red |  |  | Red | 6 | 8.1%
| Orange | 1 | 50% | Orange | 16 | 21.62%
| Green | 1 | 50% | Green | 34 | 45.94%
| Blue |  |  | Blue | 15 | 20.27%
| Yellow |  |  | Yellow | 3 | 4.05%
Sub Unit Representation - ABM 12
|  |  |  | Operating Projects |  | 12
|  |  |  | Colour | Number | %
|  |  |  | Red | 2 | 16.16%
|  |  |  | Orange | 2 | 16.16%
|  |  |  | Green | 5 | 41.66%
|  |  |  | Blue | 1 | 8.33%
|  |  |  | Yellow | 2 | 16.66%
Sub Unit Representation - HSS 24
|  |  |  | Operating Projects |  | 24
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 8 | 33.33%
|  |  |  | Green | 5 | 20.83%
|  |  |  | Blue | 10 | 41.66%
|  |  |  | Yellow | 1 | 4.16%
Sub Unit Representation - comm dev - 27
| Capital Projects |  | 2 | Operating Projects |  | 25
PKS 08 | Colour | Number | % | Colour | Number | %
PKS 10 | Red |  |  | Red | 4 | 16.16%
| Orange | 1 | 50% | Orange | 4 | 16.16%
| Green | 1 | 50% | Green | 17 | 68%
| Blue |  |  | Blue | 0 | 0%
| Yellow |  |  | Yellow | 0 | 0%
Sub Unit Representation - PSDM - 13
|  |  |  | Operating Projects |  | 13
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 15.38%
|  |  |  | Green | 7 | 53.84%
|  |  |  | Blue | 4 | 30.76%
|  |  |  | Yellow | 0 | 0%
Business Unit Representation - Infrastructure Services 77
| Capital Projects |  | 65 | Operating Projects |  | 12
| Colour | Number | % | Colour | Number | %
| Red | 8 | 12.3% | Red | 0 | 0%
| Orange | 21 | 32.3% | Orange | 4 | 33.33%
| Green | 22 | 33.84% | Green | 7 | 58.33%
| Blue | 13 | 20% | Blue | 0 | 0%
| Yellow | 1 | 1.53% | Yellow | 1 | 8.33%
Sub Unit Representation - water & sanitation 14
| Capital Projects |  | 14
| Colour | Number | %
| Red | 0 | 0%
| Orange | 8 | 57.14%
| Green | 5 | 35.71%
| Blue | 1 | 7.14%
| Yellow | 0 | 0%
Sub Unit Representation - fleet 5
|  |  |  | Operating Projects |  | 5
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 3 | 60%
|  |  |  | Green | 1 | 20%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 1 | 20%
Sub Unit Representation - PMU 6
|  |  |  | Operating Projects |  | 6
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 1 | 16.16%
|  |  |  | Green | 5 | 83.83%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - Roads & Stormwater 30
| Capital Projects |  | 30
| Colour | Number | %
| Red | 7 | 23.33%
| Orange | 9 | 30%
| Green | 7 | 23.33%
| Blue | 6 | 20%
| Yellow | 1 | 3.33%
Sub Unit Representation - Electricity
| Capital Projects |  | 12 | Operating Projects |  | 1
| Colour | Number | % | Colour | Number | %
| Red | 1 | 8.33% | Red | 0 |  | EL 12 oper
| Orange | 4 | 33.33% | Orange | 0
| Green | 1 | 8.33% | Green | 1 | 100%
| Blue | 6 | 50% | Blue | 0
| Yellow | 0 | 0% | Yellow | 0
|  |  | Sub Unit Representation - Landfill Site |  | 9
| Capital Projects |  | 9
| Colour | Number | %
| Red | 0
| Orange | 0
| Green | 1 | 100%
| Blue | 0
| Yellow | 0
Business Unit Representation - Corporate Services 58
|  |  |  | Operating Projects |  | 58
|  |  |  | Colour | Number | %
|  |  |  | Red | 4 | 6.89%
|  |  |  | Orange | 14 | 24.13%
|  |  |  | Green | 29 | 50%
|  |  |  | Blue | 4 | 6.89%
|  |  |  | Yellow | 7 | 12.06%
Sub Unit Representation - Sound Governance 19
|  |  |  | Operating Projects |  | 19
|  |  |  | Colour | Number | %
|  |  |  | Red | 3 | 15.78%
|  |  |  | Orange | 1 | 5.26%
|  |  |  | Green | 12 | 63.15%
|  |  |  | Blue | 3 | 15.78%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - legal 3
|  |  |  | Operating Projects |  | 3
|  |  |  | Colour | Number | %
|  |  |  | Red | 0
|  |  |  | Orange | 1 | 33.33%
|  |  |  | Green | 2 | 66.66%
|  |  |  | Blue | 0
|  |  |  | Yellow | 0
Sub Unit Representation - ICT - 7
|  |  |  | Operating Projects |  | 7
|  |  |  | Colour | Number | %
|  |  |  | Red | 0
|  |  |  | Orange | 7 | 100%
|  |  |  | Green | 0
|  |  |  | Blue | 0
|  |  |  | Yellow | 0
Sub Unit Representation - HRM, OD, SD, OC 29
|  |  |  | Operating Projects |  | 29
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 3.44%
|  |  |  | Orange | 5 | 17.24%
|  |  |  | Green | 15 | 51.72%
|  |  |  | Blue | 1 | 3.44%
|  |  |  | Yellow | 7 | 24.13%
Business Unit Representation - Economic Development 38
|  |  |  | Operating Projects |  | 38
|  |  |  | Colour | Number | %
|  |  |  | Red | 10 | 26.31%
|  |  |  | Orange | 7 | 18.42%
|  |  |  | Green | 10 | 26.31%
|  |  |  | Blue | 5 | 13.15%
|  |  |  | Yellow | 6 | 15.78%
Sub Unit Representation - LED 12
|  |  |  | Operating Projects |  | 12
|  |  |  | Colour | Number | %
|  |  |  | Red | 2 | 16.66%
|  |  |  | Orange | 1 | 8.33%
|  |  |  | Green | 4 | 33.33%
|  |  |  | Blue | 5 | 41.66%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - Housing 19
|  |  |  | Operating Projects |  | 19
|  |  |  | Colour | Number | %
|  |  |  | Red | 8 | 42.1%
|  |  |  | Orange | 4 | 21.05%
|  |  |  | Green | 1 | 5.26%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 6 | 31.57%
Sub Unit Representation - GEDI etc 7
|  |  |  | Operating Projects |  | 19
|  |  |  | Colour | Number | %
Red
Orange
Green
Blue
Yellow
Brown
| KPI |  | 2
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
| KPI |  | 3
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
| KPI |  | 4
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
| KPI |  | 5
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
Comparative summary 3rd Quarter 2010/11 & 2011/12
| Capital Projects |  | 91 | Operating Projects |  | 291
| Colour | 2010/11 | 2011/12 |  | 2010/11 | 2011/12
| Red | 81% | 37.3% | Red | 32% | 17.52%
| Orange | 15% | 30.7% | Orange | 25% | 39.86%
| Green | 2% | 28.5% | Green | 36% | 25.77%
| Blue | 2% | 2.1% | Blue | 7% | 5.84%
| Yellow | 0% | 1% | Yellow | 0% | 10.99%
| Brown | 0% | 0% | Brown | 0% | 0%
|  |  |  | Operating Projects |  | 7
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 28.57%
|  |  |  | Green | 5 | 71.42%
|  |  |  | Blue | 0 | 0%
|  |  |  | Yellow | 0 | 0%

## Sheet2 (hidden)
.
Nil Achieved
Target Partially Met
Target Met
Target Exceeded
Not Applicable