## ANNEX A (hidden)
ANNEXURE A: MONTHLY PROJECTION OF REVENUE BY EACH SOURCE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2011/12
Revenue By Source
Property rates | 28820083.7 | 46112133.92 | 51876150.66 | 57640167.4 | 63404184.14 | 28820083.7 | 46112133.92 | 57640167.4 | 57640167.4 | 80696234.36 | 28820083.7 | 28820083.7 | 576401674
Property rates - penalties & collection charges | 1690613.2058 | 2704981.1293 | 3043103.7704 | 3381226.4116 | 3719349.0527 | 1690613.2058 | 2704981.1293 | 3381226.4116 | 3381226.4116 | 4733716.9762 | 1690613.2058 | 1690613.2058 | 33812264.1157
Service charges - electricity revenue | 70845834.95 | 113353335.92 | 127522502.91 | 141691669.9 | 155860836.89 | 70845834.95 | 113353335.92 | 141691669.9 | 141691669.9 | 198368337.86 | 70845834.95 | 70845834.95 | 1416916699
Service charges - water revenue | 15867682.8 | 25388292.48 | 28561829.04 | 31735365.6 | 34908902.16 | 15867682.8 | 25388292.48 | 31735365.6 | 31735365.6 | 44429511.84 | 15867682.8 | 15867682.8 | 317353656
Service charges - sanitation revenue | 5700000 | 9120000 | 10260000 | 11400000 | 12540000 | 5700000 | 9120000 | 11400000 | 11400000 | 15960000 | 5700000 | 5700000 | 114000000
Service charges - refuse revenue | 3937610.1 | 6300176.16 | 7087698.18 | 7875220.2 | 8662742.22 | 3937610.1 | 6300176.16 | 7875220.2 | 7875220.2 | 11025308.28 | 3937610.1 | 3937610.1 | 78752202
Service charges - other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment | 976688.6 | 1562701.76 | 1758039.48 | 1953377.2 | 2148714.92 | 976688.6 | 1562701.76 | 1953377.2 | 1953377.2 | 2734728.08 | 976688.6 | 976688.6 | 19533772
Interest earned - external investments | 605000 | 968000 | 1089000 | 1210000 | 1331000 | 605000 | 968000 | 1210000 | 1210000 | 1694000 | 605000 | 605000 | 12100000
Interest earned - outstanding debtors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dividends received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines | 173728.55 | 277965.68 | 312711.39 | 347457.1 | 382202.81 | 173728.55 | 277965.68 | 347457.1 | 347457.1 | 486439.94 | 173728.55 | 173728.55 | 3474571
Licences and permits | 3719.35 | 5950.96 | 6694.83 | 7438.7 | 8182.57 | 3719.35 | 5950.96 | 7438.7 | 7438.7 | 10414.18 | 3719.35 | 3719.35 | 74387
Agency services | 19101.27 | 30562.0319 | 34382.2859 | 38202.5399 | 42022.7939 | 19101.27 | 30562.0319 | 38202.5399 | 38202.5399 | 53483.5559 | 19101.27 | 19101.27 | 382025.3992
Transfers recognised - operational | 91301000 |  |  | 91301000 |  |  | 91301000 |  |  | 91301000 |  | 0 | 365204000
Other revenue | 2489241.4356 | 3982786.297 | 4480634.5842 | 4978482.8713 | 5476331.1584 | 2489241.4356 | 3982786.297 | 4978482.8713 | 4978482.8713 | 6969876.0198 | 2489241.4356 | 2489241.4356 | 49784828.7128
Gains on disposal of PPE | [11 empty] | 0 | 0
Total Revenue (excluding capital transfers and contributions) | 222430303.9614 | 209806886.3382 | 236032747.1305 | 353559607.9228 | 288484468.7151 | 131129303.9614 | 301107886.3382 | 262258607.9228 | 262258607.9228 | 458463051.0919 | 131129303.9614 | 131129303.9614 | 2987790079.2277

## ANNEX B (hidden)
ANNEXURE B: MONTHLY PROJECTION OF REVENUE COLLECTED BY EACH VOTE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2011/12
Revenue by Vote
Vote 1 - Corporate Services and Planning | 17300539.9789 | 16318695.6107 | 18358532.562 | 27499724.7355 | 22438206.4647 | 10199184.7567 | 23420050.8329 | 20398369.5133 | 20398369.5133 | 35659072.5409 | 10199184.7567 | -219269705.2654 | 2920226
Vote 2 - Financial Management Area | 18261003.154 | 17224650.3508 | 19377731.6446 | 29026409.6232 | 23683894.2323 | 10765406.4692 | 24720247.0355 | 21530812.9385 | 21530812.9385 | 37638734.7986 | 10765406.4692 | 408517165.2065 | 643042274.8608
Vote 3 - Infrastructure Development, Service Delivery and Maintenance Management | 156367695.5575 | 147493478.8315 | 165930163.6854 | 248551119.8272 | 202803533.3933 | 92183424.2697 | 211677750.1193 | 184366848.5393 | 184366848.5393 | 322297859.2429 | 92183424.2697 | 290768911.7248 | 2298991058
Vote 4 - Sustainable Community Service Delivery Provision Management | 30501065.271 | 28770061.5453 | 32366319.2385 | 48482353.7369 | 39558834.6248 | 17981288.4658 | 41289838.3505 | 35962576.9316 | 35962576.9316 | 62867384.5095 | 17981288.4658 | -348886238.0715 | 42837350
Total Revenue by Vote | 222430303.9614 | 209806886.3382 | 236032747.1305 | 353559607.9228 | 288484468.7151 | 131129303.9614 | 301107886.3382 | 262258607.9228 | 262258607.9228 | 458463051.0919 | 131129303.9614 | 131130133.5945 | 2987790908.8608
0

## ANNEX C (hidden)
ANNEXURE C: MONTHLY PROJECTION OF OPERATIONAL EXPENDITURE BY VOTE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2011/12
Expenditure - Standard
Governance and administration | 27392410.25 | 43827856.4 | 49306338.45 | 54784820.5 | 60263302.55 | 27392410.25 | 43827856.4 | 54784820.5 | 54784820.5 | 76698748.7 | 27392410.25 | 27392410.25 | 547848205
Executive and council | 3554723.25 | 5687557.2 | 6398501.85 | 7109446.5 | 7820391.15 | 3554723.25 | 5687557.2 | 7109446.5 | 7109446.5 | 9953225.1 | 3554723.25 | 3554723.25 | 71094465
Budget and treasury office | 10328299.45 | 16525279.12 | 18590939.01 | 20656598.9 | 22722258.79 | 10328299.45 | 16525279.12 | 20656598.9 | 20656598.9 | 28919238.46 | 10328299.45 | 10328299.45 | 206565989
Corporate services | 13509387.55 | 21615020.08 | 24316897.59 | 27018775.1 | 29720652.61 | 13509387.55 | 21615020.08 | 27018775.1 | 27018775.1 | 37826285.14 | 13509387.55 | 13509387.55 | 270187751
Community and public safety | 18828913.15 | 30126261.04 | 33892043.67 | 37657826.3 | 41423608.93 | 18828913.15 | 30126261.04 | 37657826.3 | 37657826.3 | 52720956.82 | 18828913.15 | 18828913.15 | 376578263
Community and social services | 1935958 | 3097532.8 | 3484724.4 | 3871916 | 4259107.6 | 1935958 | 3097532.8 | 3871916 | 3871916 | 5420682.4 | 1935958 | 1935958 | 38719160
Sport and recreation | 3851892 | 6163027.2 | 6933405.6 | 7703784 | 8474162.4 | 3851892 | 6163027.2 | 7703784 | 7703784 | 10785297.6 | 3851892 | 3851892 | 77037840
Public safety | 8883453.15 | 14213525.04 | 15990215.67 | 17766906.3 | 19543596.93 | 8883453.15 | 14213525.04 | 17766906.3 | 17766906.3 | 24873668.82 | 8883453.15 | 8883453.15 | 177669063
Housing | 1827714 | 2924342.4 | 3289885.2 | 3655428 | 4020970.8 | 1827714 | 2924342.4 | 3655428 | 3655428 | 5117599.2 | 1827714 | 1827714 | 36554280
Health | 2329896 | 3727833.6 | 4193812.8 | 4659792 | 5125771.2 | 2329896 | 3727833.6 | 4659792 | 4659792 | 6523708.8 | 2329896 | 2329896 | 46597920
Economic and environmental services | 8072605.7925 | 12916169.268 | 14530690.4265 | 16145211.585 | 17759732.7435 | 8072605.7925 | 12916169.268 | 16145211.585 | 16145211.585 | 22603296.219 | 8072605.7925 | 8072605.7925 | 161452115.85
Planning and development | 3283402.5 | 5253444 | 5910124.5 | 6566805 | 7223485.5 | 3283402.5 | 5253444 | 6566805 | 6566805 | 9193527 | 3283402.5 | 3283402.5 | 65668050
Road transport | 4789203.2925 | 7662725.268 | 8620565.9265 | 9578406.585 | 10536247.2435 | 4789203.2925 | 7662725.268 | 9578406.585 | 9578406.585 | 13409769.219 | 4789203.2925 | 4789203.2925 | 95784065.85
Environmental protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trading services | 92783261.1 | 148453217.76 | 167009869.98 | 185566522.2 | 204123174.42 | 92783261.1 | 148453217.76 | 185566522.2 | 185566522.2 | 259793131.08 | 92783261.1 | 92783261.1 | 1855665222
Electricity | 60779507.2 | 97247211.52 | 109403112.96 | 121559014.4 | 133714915.84 | 60779507.2 | 97247211.52 | 121559014.4 | 121559014.4 | 170182620.16 | 60779507.2 | 60779507.2 | 1215590144
Water | 23803408.6 | 38085453.76 | 42846135.48 | 47606817.2 | 52367498.92 | 23803408.6 | 38085453.76 | 47606817.2 | 47606817.2 | 66649544.08 | 23803408.6 | 23803408.6 | 476068172
Waste water management | 4750926 | 7601481.6 | 8551666.8 | 9501852 | 10452037.2 | 4750926 | 7601481.6 | 9501852 | 9501852 | 13302592.8 | 4750926 | 4750926 | 95018520
Waste management | 3449419.3 | 5519070.88 | 6208954.74 | 6898838.6 | 7588722.46 | 3449419.3 | 5519070.88 | 6898838.6 | 6898838.6 | 9658374.04 | 3449419.3 | 3449419.3 | 68988386
Other | 2055124 | 3288198.4 | 3699223.2 | 4110248 | 4521272.8 | 2055124 | 3288198.4 | 4110248 | 4110248 | 5754347.2 | 2055124 | 2055124 | 41102480
Total Expenditure - Standard | 149132314.2925 | 238611702.868 | 268438165.7265 | 298264628.585 | 328091091.4435 | 149132314.2925 | 238611702.868 | 298264628.585 | 298264628.585 | 417570480.019 | 149132314.2925 | 149132314.2925 | 2982646285.85

## ANNEX D (hidden)
ANNEXURE D: MONTHLY PROJECTION OF CAPITAL EXPENDITURE BY VOTE
Description | Budget Year 2012/13
R thousand | July | August | Sept. | October | Nov. | Dec. | January | Feb. | March | April | May | June | Budget Year 2011/12
Multi-year expenditure to be appropriated
Vote 1 - Corporate Services and Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5150000 | 5150000
Vote 2 - Financial Management Area | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
Vote 3 - Infrastructure Development, Service Delivery and Maintenance Management | 0 | 0 | 14300000 | 17876000 | 25025000 | 8938000 | 8938000 | 17876000 | 19663000 | 25025000 | 26813000 | 14299000 | 178753000
Vote 4 - Sustainable Community Service Delivery Provision Management |  |  | 3689000 | 4612000 | 6455000 | 2306000 | 2306000 | 4612000 | 5073000 | 6455000 | 6916000 | 3687000 | 46111000
Capital multi-year expenditure sub-total | 0 | 0 | 17989000 | 22488000 | 31480000 | 11244000 | 11244000 | 22488000 | 24736000 | 31480000 | 33729000 | 23136000 | 230014000

## COMPULSORY INDICATORS (hidden)
MSUNDUZI MUNICIPALITY SDBIP 2012/2013
THE FOLLOWING ARE KEY PERFORMANCE INDICATORS EMANATING FROM SECTION 43 OF THE LOCAL GOVERNMENT MUNICIPAL SYSTEMS ACT AND REGULATIONS 5 (1)
No. | National Key Performance Areas | Strategic Business Unit | Compulsory Key Performance Indicators | Unit of Measure / Calculations | Annual |  |  | Annual |  | Quarterly |  | Blockages | Corrective Measures | Support needed in terms of unblocking | Portfolio of Evidence
[5 empty] | Demand | Baseline | Backlog | Target |  | Target
[8 empty] | Projected | Actual | Projected | Actual
1 | MUNICIPAL TRANSFORMATION AND INSTITUTION/AL DEVELOPMENT | Corporate Services | Budget spent on Work Skills Plan | Budgeted amount
Actual amount spent
Percentage spent
2 |  |  | Number of people from employment equity target groups employed in the three highest levels of management | Number
3 | BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | Infrastrucuture Services | Number (as well as percentage) of households with access to potable (drinkable) water | Number
Percentage
4 |  |  | Number (as well as percentage) of households with access to sanitation | Number
Percentage
5 |  |  | Number of households with access to refuse removal at least once per week | Number
6 |  |  | Number (as well as percentage) of households with access to electricity | Number
Percentage
7 |  | Financial Services | Percentage of households earning less than R1100 per month with access to free basic services | Percentage
8 | LOCAL ECONOMIC DEVELOPMENT | Development Services | Number of work opportunities created through LED development initiatives including Capital Projects | Number
9 | FINANCIAL VIABILITY AND FINANCAIL MANAGEMENT | Financial Services | Percentage of a municipality's capital budget actually spent on capital projects identified in the IDP | Percentage : Total spending on capital projects divided by total capital budget x 100
10 |  |  | Financial viability in terms of debt coverage | Ratio: Total operating revenue received minus operating grants divided by debt service payments (ie. Interests plus redemption)
11 |  |  | Financial viability in terms of cost coverage | Ratio: Available cash plus investments divided by monthly fixed operating expenditure
12 |  |  | Financial viability in terms of outstanding service debtors to revenue | Ratio: Outstanding service debtors divided by annual revenue actually received for services

## ANNEXURE 1
ANNEXURE 1: SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
SDBIP 2012/2013

## CONTENTS PAGE
SDBIP 2012/2013 QUARTER 3 (MONTH 8 - FEBRUARY 2013) PROGRESS REPORT
CONTENTS PAGE
| NO. | DESCRIPTION | PAGE / S
| 1 | ANNEXURE 1: SDBIP 2012 / 2013 COVER PAGE | Page 1
| 2 | ORGANIZATIONAL OVERVIEW | Page 2
| 3 | ANNEXURE 1 (E) - CBU COVER PAGE | Page 3
| 4 | CORPORATE BUSINESS UNIT OVERVIEW | Page 4
| 5 | INTERNAL AUDIT OVERVIEW | Page 5
| 6 | INTERNAL AUDIT REPORT | Pages 6 - 8
| 7 | OFFICE OF THE MUNICIPAL MANAGER OVERVIEW | Page 9
| 8 | OFFICE OF THE MUNICIPAL MANAGER REPORT | Pages 10 - 16
| 9 | INTERGRATED DEVELOPMENT PLAN OVERVIEW | Page 17
| 10 | INTERGRATED DEVELOPMENT PLAN REPORT | Pages 18 - 19
| 11 | MARKETING OVERVIEW | Page 20
| 12 | MARKETING REPORT | Page 21 - 22
| 13 | ANNEXURE 1 (F) - FINANCE COVER PAGE | Page 23
| 14 | FINANCE OVERVIEW | Page 24
| 15 | BUDGET & TREASURY OVERVIEW | Page 25
| 16 | BUDGET & TREASURY REPORT | Pages 26 - 28
| 17 | EXPENDITURE MANAGEMENT OVERVIEW | Page 29
| 18 | EXPENDITURE MANAGEMENT REPORT | Pages 30 - 32
| 19 | REVENUE MANAGEMENT OVERVIEW | Page 33
| 20 | REVENUE MANAGEMENT REPORT | Pages 34 - 36
| 21 | SUPPLY CHAIN MANAGEMENT OVERVIEW | Page 37
| 22 | SUPPLY CHAIN MANAGEMENT REPORT | Pages 38 - 39
| 23 | ANNEXURE 1 (G) - COMMUNITY SERVICES COVER PAGE | Page 40
| 24 | COMMUNITY SERVICES OVERVIEW | Page 41
| 25 | AREA BASED MANAGEMENT OVERVIEW | Page 42
| 26 | AREA BASED MANAGEMENT REPORT | Pages 43 - 44
| 27 | HEALTH & SOCIAL SERVICES OVERVIEW | Page 45
| 28 | HEALTH & SOCIAL SERVICES REPORT | Pages 46 - 49
| 29 | COMMUNITY DEVELOPMENT OVERVIEW | Page 50
| 30 | COMMUNITY DEVELOPMENT REPORT | Pages 51 - 55
| 31 | PUBLIC SAFETY ENFORCEMENT & DISASTER MANAGEMENT OVERVIEW | Page 56
| 32 | PUBLIC SAFETY ENFORCEMENT & DISASTER MANAGEMENT REPORT | Pages 57 - 60
| 33 | ANNEXURE 1 (H) - INFRASTRUCTURE SERVICES COVER PAGE | Page 61
| 34 | INFRASTRUCUTURE SERVICES OVERVIEW | Page 62
| 35 | WATER & SANITATION OVERVIEW | Page 63
| 36 | WATER & SANITATION REPORT | Pages 64 - 66
| 37 | ELECTRICITY OVERVIEW | Page 67
| 38 | ELECTRICITY REPORT | Page 68 - 69
| 39 | PROJECT MANAGEMENT UNIT OVERVIEW | Page 70
| 40 | PROJECT MANAGEMENT UNIT REPORT | Page 71 - 72
| 41 | FLEET MANAGEMENT OVERVIEW | Page 73
| 42 | FLEET MANAGEMENT REPORT | Page 74
| 43 | ROADS, TRANSPORTATION & PUBLIC WORKS OVERVIEW | Page 75
| 44 | ROADS, TRANSPORTATION & PUBLIC WORKS REPORT | Page 76 - 81
| 45 | LANDFILL SITE OVERVIEW | Page 82
| 46 | LANDFILL SITE REPORT | Pages 83 - 84
| 47 | ANNEXURE 1 (I) - CORPORATE SERVICES COVER PAGE | Page 85
| 48 | CORPORATE SERVICES OVERVIEW | Page 86
| 49 | SOUND GOVERNANCE OVERVIEW | Page 87
| 50 | SOUND GOVERNANCE REPORT | Pages 88 - 90
| 51 | LEGAL SERVICES OVERVIEW | Page 91
| 52 | LEGAL SERVICES REPORT | Page 92
| 53 | INFORMATION COMMUNICATION TECHNOLOGY OVERVIEW | Page 93
| 54 | INFORMATION COMMUNICATION TECHNOLOGY REPORT | Pages 94 - 96
| 55 | HUMAN RESOURCE MANAGEMENT, OCCUPATIONAL HEALTH, ORGANIZATIONAL DEVELOPMENT & SKILLS DEVELOPMENT UNIT OVERVIEW | Page 97
| 56 | HUMAN RESOURCE MANAGEMENT, OCCUPATIONAL HEALTH, ORGANIZATIONAL DEVELOPMENT & SKILLS DEVELOPMENT UNIT REPORT | Pages 98 - 104
| 57 | ANNEXURE 1 (J) - ECONOMIC DEVELOPMENT COVER PAGE | Page 105
| 58 | ECONOMIC DEVELOPMENT OVERVIEW | Page 106
| 59 | LOCAL ECONOMIC DEVELOPMENT OVERVIEW | Page 107
| 60 | LOCAL ECONOMIC DEVELOPMENT REPORT | Pages 108 - 110
| 61 | HOUSING OVERVIEW | Page 111
| 62 | HOUSING REPORT | Pages 112 - 114
| 63 | GEDI, PLANNING, ENVIRONMENTAL & LICENSING OVERVIEW | Page 115
| 64 | GEDI, PLANNING, ENVIRONMENTAL & LICENSING REPORT | Pages 116 - 117

## Organizational overview
ORGANISATIONAL OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | ORGANISATIONAL OVERVIEW
| 1.1 | TOTAL PROJECTS: | 344
| 1.1.1 | OPERATING PROJECTS | 279
| 1.1.2 | CAPITAL PROJECTS | 65
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 1.1.1 | A total of 279 Operating Projects were reported on the SDBIP for the Quarter ending March 2013 2012/2013 financial year
| 1.1.2 | 3.58% of the projects were reported as having Nil Achievements for the Quarter ending March 2013 2012/2013 financial year
| 1.1.3 | 18.63% of the projects were reported as having been partially met for for the Quarter ending March 2013 2012/2013 financial year
| 1.1.4 | 42.65% of the projects were reported as having been met for the Quarter ending March 2013 2012/2013 financial year
| 1.1.5 | 6.81% of the projects were reported as having exceeded the target for the Quarter ending March 2013 2012/2013 financial year
| 1.1.6 | 2.50% of the projects were reported as having exceeded the target by 100% for the Quarter ending March 2013 2012/2013 financial year
| 1.1.7 | 25.80% of the projects were reported as not applicable due to not having any targets set for the Quarter ending March 2013 2012/2013 financial year.
| 1.1.7 | 0% of the projects were not reported on by Business Units for the 3rd Quarter.
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS
| 2.1.1 | A total of 67 Capital Projects were reported on the SDBIP for the Quarter ending March 2013 2012/2013 financial year
| 2.1.2 | 4.61% of the projects were reported as having Nil Achievements for the Quarter ending March 2013 2012/2013 financial year
| 2.1.3 | 30.76% of the projects were reported as having been partially met for for the Quarter ending March 2013 2012/2013 financial year
| 2.1.4 | 38.46% of the projects were reported as having been met for the Quarter ending March 2013 2012/2013 financial year
| 2.1.5 | 1.53% of the projects were reported as having exceeded the target for the Quarter ending March 2013 2012/2013 financial year
| 2.1.6 | 1.53% of the projects were reported as having exceeded the target by 100% for the Quarter ending March 2013 2012/2013 financial year
| 2.1.6 | 23.07% of the projects were reported as not applicable due to not having any targets set for the Quarter ending March 2013 2012/2013 financial year.
2.1.7

## CBU COVER
ANNEXURE 1(E): CORPORATE BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
SDBIP 2012/2013

## CBU overview
CORPORATE BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
1 | CORPORATE BUSINESS UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 64
1.1.1 | OPERATING PROJECTS | 64
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## IA overview
INTERNAL AUDIT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | INTERNAL AUDIT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 11
| 1.1.1 | OPERATING PROJECTS | 11
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Internal Audit
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.1 INTERNAL AUDIT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
IA 01 | Institutional Development and Transformation/Governance | Annual Audit Plan | Development of the Annual Audit Plan | N/A | Annual Plan for 2011/12 was approved on 25 February 2012 | Annual plan for 2012/13 approved by Audit Committee by 31 August 2012 | Date of approval of the Annual Audit Plan | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IA02 | Institutional Development and Transformation/Governance | Risk Management Function | Risk Management Policy | N/A | Current Risk Management Policy adopted by Council on 12 February 2009 | Revised Risk Management Policy adopted by Council by 30 September 2012 | Date of adoption of the Risk Management Policy | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
IA03 | Institutional Development and Transformation/Governance | Risk Management Function | Risk Assessment | N/A | Risk Assessment finalised 25/02/12 | Risk Profile/Register of the completed & submitted to SMC by 28 February 2013 | Date of adoption of the Risk Profile/Register | N/A | N/A | N/A | Nil Required | Risk Profile/Register completed & submitted to SMC by 28 February 2013 | Risk Profile/Register completed by 28 February 2013 | 2 | Waiting for tabling at the Risk Management Committee | Date for the meeting of the Risk Management Committee to be fast tracked. | Risk Profile/Register & Resolution of SMC
IA04 | Institutional Development and Transformation/Governance | Risk Management Function |  | N/A | Risk Management Strategy not in place | Risk Management Strategy submitted to SMC by 28 February 2013 | Date of adoption of Risk Management Strategy | N/A | N/A | N/A | Nil Required | Risk Management Strategy submitted to SMC by 28 February 2013 | Risk Management Strategy completed by 28 February 2013 | 2 | Waiting for tabling at the Risk Management Committee | Date for the meeting of the Risk Management Committee to be fast tracked. | Risk Management Strategy & Resolution of SMC
IA05 | Institutional Development and Transformation | Anti-Fraud & Corruption | Anti-Fraud & Corruption Policy | N/A | Anti-Fraud & Corruption Policy developed in 2009 | Revised Anti-Fraud & Corruption submitted to SMC by 31 January 2013 | Date of adoption of Anti-Fraud & Corruption Policy | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
IA06 | Institutional Development and Transformation | Anti-Fraud & Corruption | Anti-Fraud & Corruption Strategy | N/A | Anti-Fraud & Corruption Strategy developed in 2009 | Revised Anti-Fraud & Corruption Strategy submitted to SMC by 31 January 2013 | Date of adoption of the Anti-Fraud & Corruption Strategy | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
IA07 | Institutional Development and Transformation/Governance | Anti-Fraud & Corruption | Anti-Fraud/Ethics Awareness Campaign | N/A | Never done | Anti-Fraud & Corruption/Ethics workshops Rollout Plan submitted to SMC by 31 May 2013 | Date of Anti-Fraud & Corruption / Ethics workshops Rollout Plan | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
IA09 | Governance | Anti-Fraud & Corruption | Adhoc Forensic Investigations | N/A | No record | Forensic Investigations done as per request/need | Forensic investigations done within the timeframe prescribed in the project plan | N/A | N/A | N/A | Nil Required | Forensic investigations done within the timeframe prescribed in the project plan | Forensic investigations done within the timeframe prescribed in the project plan | 3 | N/A | N/A | Reports to MM.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IA10 | Institutional Development and Transformation/Governance | Annual Audit Plan 2012/13 | Internal Audit Assignments | N/A | 11 projects completed 2011/12 | Internal Audit assignments done as per Annual Audit Plan per annum | Number of projects completed as per the annual plan | 1120000 | N/A | N/A | Council | Internal Audit Assignments Completed as per the annual plan | Internal Audit Assignments Completed as per the annual plan | 3 | Delays in submitting portfolio of evidence. Portfolio of evidence that is not properly filed & referenced. Extention of scope due to high reisks identified | MM & DMMs have to start disciplining their subordinate for failure to submit properly filed & referenced portfolio of evidence timeously | Reports
[8 empty] | 0361001100 | N/A | N/A |  | 220000 | N/A | N/A | N/A | N/A | N/A
IA11 | Institutional Development and Transformation/Governance | Internal Audit Methodology | Internal Audit Methodology | N/A | Not in place | Internal Audit Methodology developed by 31 December 2012 | Date by which the methodology is completed | N/A | N/A | N/A | Nil Required | Internal Audit Methodology implementation & monitoring | Internal Audit Methodology was implemented in October 2012 in phases & is an ongoing project. | 4 | N/A | N/A | Reports produced in the new format
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IA13 | Institutional Development and Transformation/Governance | Annual Audit Plan | Development of the Annual Audit Plan | N/A | Annual Plan for 2011/12 was approved on 25 February 2012 | Annual plan for 2013/14 approved by Audit Committee by 30 June 2013 | Date of approval of the Annual Audit Plan | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## MMs OFFICE overview
OFFICE OF THE MUNICIPAL MANAGER OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | OFFICE OF THE MUNICIPAL MANAGER OVERVIEW
| 1.1 | TOTAL PROJECTS: | 36
| 1.1.1 | OPERATING PROJECTS | 36
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## OFFICE OF THE MM
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.2 OFFICE OF THE MUNICIPAL MANAGER
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
MSP 01 | Good Governance and Public Participation | Sports Programme | Salga Games | All | Annual Games | Participated in SALGA Games with 15 codes by December 2012. | Date and number of sports codes | 300 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 02 | Good Governance and Public Participation |  | Golden Games | All | Annual Games | Participated in Games with 120 participants by 31 August 2012 | Date and number of participants | 286 808 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 03 | Good Governance and Public Participation | Junior Council Outreach Programme | Back to School | All | N/A | Visit 5 schools 29 February 2013 | Number of schools visited | 10 000 | N/A | N/A | Council | Visit 5 schools to address social ills i.e teenage pregnancy etc | Visit 5 schools to address social ills i.e teenage pregnancy etc | 3 | N/A | N/A | Letters to schools
[8 empty] | 0131151015 | N/A | N/A |  | 10 000 | N/A | N/A | N/A | N/A | N/A
MSP 04 | Good Governance and Public Participation |  | Child Protection Campaign | All | N/A | child protection campaign in July 2012 | Number of campaigns | 20 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 05 | Good Governance and Public Participation |  | School Exchange | All | N/A | sharing of resources between 4 rural and 4 urban schools | Number of schools | 7 000 | N/A | N/A | Council | Sharing resources | Sharing resources | 3 | N/A | N/A | List of schools
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 06 | Good Governance and Public Participation |  | Child to Work | All | N/A | provision of work experience to children by 28 June 2013 | Number of children placed | 10 000 | N/A | N/A | Council | Meeting with Msunduzi Municipality Business Units | Meeting with Msunduzi Municipality Business Units | 3 | N/A | N/A | list of learners
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 07 | Good Governance and Public Participation |  | JCC Festival | All | N/A | Participation by 14 schools in sports activities by 28 June 2013 | Number of schools participated | 35 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 08 | Good Governance and Public Participation |  | Leadership Training | All | N/A | 30 JCC members trained on leadership skills 30 April 2013 | Number of members trained | 30 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 09 | Good Governance and Public Participation | Annual Events/Campaigns Programme | Annual Reed dance | All | Annual Event | Annual Reed dance held on 14-16 September 2012 with 440 participants | Date of event and number of participants | 90 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 10 | Good Governance and Public Participation | Annual Events/Campaigns Programme | 16 Days Activism | All | Annual Awareness Programme | Annual Awareness Programme held on 25 November – 10 December 2012 with 500 participants | Date of event and number of participants | 227 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 11 | Good Governance and Public Participation |  | Annual Information Week | All | Annual Event | Participation of 60 high schools in the Annual Information Week to be held from 6-9 May 2013 | Number of schools participating | 350 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 12 | Good Governance and Public Participation | Educational Programmes | Blindness Education/ Awareness | All | N/A | provision of sign language training to parents of children with hearing impairment by 31 May 2013 | Number of participants | 140 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 13 | Good Governance and Public Participation |  | Human Trafficking Education/ Awareness | All | N/A | Participation of 5 primary schools in educating them on Human Trafficking by 30 November 2012 | Number of participants |  | N/A | N/A | Council | Zone 4 | Human trafficking took place in October 2012 | 3 | N/A | N/A | list of schools / attendance registers
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 14 | Good Governance and Public Participation |  | Human Rights Education | All | N/A | 100 persons with disabilities educated on Human Rights in March 2013 | Number of participants | 90 000 | N/A | N/A | Council | Human Rights education for 100 People with disabilities in March 2013 | Human Rights education for 100 People with disabilities in March 2013 | 3 | N/A | N/A | list of participants / attendance registers
[8 empty] | 0131151015 | N/A | N/A |  | 90 000 | N/A | N/A | N/A | N/A | N/A
MSP 15 | Good Governance and Public Participation |  | Blind & Deaf Literacy Programme | All | N/A | provision of Braille training to visually impaired people by 29 June 2013 | Number of participants | 320 000 | N/A | N/A | Council | Braille training | SCM to appoint service provider | 2 | exp schedule was not considered due to the unavailability of funds in the vote | Funds released, exp schedule forwarded to SCM for their processes to commence | Specifications / SCM documentation
[8 empty] | 0131151015 | N/A | N/A |  | 139200 | N/A | N/A | N/A | N/A | N/A
MSP 16 | Good Governance and Public Participation | Orphans & Vulnerable Children | Drivers Licences | All | N/A | Provision of driver’s licences to 78 orphans and vulnerablechildren by 29 June 2013 | Number of orphans/ vulnerable children getting drivers licences | 195 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 17 | Good Governance and Public Participation |  | 2) School Uniforms | All | N/A | Provision of school uniforms to 10 schools by 29 June 2013 | Number of orphans/ vulnerable children getting school uniforms | 300 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151015 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OTS 02 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act | Ward Committee Support | Computers | All | N/A | Acquire 37 computers for 37 ward offices | date | N/A | 245 000 | N/A | MSIG | 37 computers | 37 computers purchased awaiting to be distributed (distribution to be completed by the 8th of April 2013) | 2 | Centralisation of computer order | Process of programming computers | SCM documents (GRS/Delivery Note)
[8 empty] | N/A |  | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OTS 03 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act | Functioning of Ward Committees | Annual schedule of meetings | All | 1 | Completed schedule of ward committee meetings submitted to Cogta by 30/6/13 | completed schedule and date | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OTS 04 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act |  | Monthly Ward Reports | All | N/A | 1) Submission of monthly reports from each of the 37 ward committees by the 5th monthly to the Speaker’s Office | Monthly report from each ward by the 5th monthly | N/A | N/A | N/A | N/A | 111 monthly reports from each of the 37 ward committees submitted by the 5th monthly to the Speaker’s Office | 98 monthly reports from each of the 37 ward committees submitted by the 5th monthly to the Speaker’s Office | 2 | Other ward committees have reported directly to the CC or business unit | Deadline for all reports has been set for 2 April 2013 | Monthly reports (January - March)
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTS 05 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act |  |  |  |  | 2) Forward report to relevant business unit/ Customer Care Centre for actioning | Register of forwarded items | N/A | N/A | N/A | N/A | 3 monthly reports forwarded to relevant business unit/ Customer Care Centre for actioning | 3 monthly reports forwarded to relevant business unit/ Customer Care Centre for actioning | 3 | N/A | N/A | Register of items forwarded (December to February)
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTS 06 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act |  | Submission of minutes by Ward Assistants | All | N/A | Submission of Ward Committee minutes and Community meetings by Ward Assistants 5 days after each meeting | Minutes from each ward within 5 days of each meeting | N/A | N/A | N/A | N/A | 90 Ward Committee and Community meetings minutes submitted by Ward Assistants 5 days after each meeting (as per annual schedule of meetings) | 45 Ward Committee and Community meetings minutes submitted by Ward Assistants 5 days after each meeting (as per annual schedule of meetings) | 2 | Lack of resources (computers) | Computers to be installed in all offices by 08 Aprl 2013 | Minutes received (January - March)
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 01 | Municipal Transformation & Institutional Development | Organizational Performance Management | SDBIP | All | SDBIP 2012/2013 was approved within 28 days after the approval of the budget & IDP | Approved SDBIP 2013 / 2014 - Submitted to the Mayorby 30 June 2013 | Date of approval | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 02 | Municipal Transformation & Institutional Development |  |  | All | SDBIP 2011/2012 was not made public within 14 days after the approval by the Mayor | Approved SDBIP 2012 / 2013 made public within 14 days after the approval of the Mayor - Placed on Muncipal Website | Date of publishing | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 03 | Municipal Transformation & Institutional Development |  |  | All | Nil monthly reports on the SDBIP produced in 2011/2012. | 8 Monthly reports on the SDBIP submitted the Operational Management Committee | Number of monthly reports | N/A | N/A | N/A | Nil Required | January & February SDBIP montly Reports submitted to the Operational Management Committee | January & February SDBIP montly Reports submitted to the Operational Management Committee | 3 | N/A | N/A | January & February monthly reports / minutes of meetings where reports were discussed
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 04 | Municipal Transformation & Institutional Development | Performance Management Reporting | SDBIP Quarterly Reports | All | 4 | 4 Quarterly reports on the SDBIP submitted to PF’s, MPAC, EXCO & Full Council | Number of quarterly reports | N/A | N/A | N/A | Nil Required | 3rd Quarterly report submitted to the Operational Management Committee | 3rd Quarterly report submitted to the Operational Management Committee | 3 | N/A | N/A | 3rd Quarter report / minutes of meeting
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 05 | Municipal Transformation & Institutional Development |  | Annual performance report | All | 1 | Completed Annual Performance Report submitted to the Auditor General by 31st August 2012 | Date of submission | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 06 | Municipal Transformation & Institutional Development |  | Mid-year performance review | All | 1 | Mid-Year Performance Review submitted to Council by the end of January 2013 | Date of approval | N/A | N/A | N/A | Nil Required | Mid-Year Performance Review submitted to Council by the end of January 2013 | Mid-Year Performance Review tabled in Council on the 25th of January 2013 | 3 | N/A | N/A | Minutes of the full council meeting / Mid-Year Performance Review
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 07 | Municipal Transformation & Institutional Development |  | Annual report | All | 1 | Annual Report tabled in Council by the 31st January 2013 | Date Annual Report tabled in Council | 250 000 | N/A | N/A | Council | Annual Report tabled in Council by the 31st January 2013 | Annual Report tabled in Council on the 25th of January 2013 | 3 | N/A | N/A | Minutes of the full council meeting / draft AR 11/12
[8 empty] | 011 100 1031 | N/A | N/A |  | 250 000 | N/A | N/A | N/A | N/A | N/A
OPMS 08 | Municipal Transformation & Institutional Development |  | Oversight Report | All | 1 | Oversight Report tabled and adopted by Council by the 31st March 2013 | Date Oversight report tabled in Council | 50 000 | N/A | N/A | N/A | Oversight Report tabled and adopted by Council by the 31st March 2013 | Draft Oversight Report tables at OS Committee meeting on the 22nd of March, to be tabled on the 27th of March 13 at FC | 3 | N/A | N/A | Draft OS report, Miunutes of the OS meetings
[8 empty] | To identify savings at mid-year review | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 09 | Municipal Transformation & Institutional Development | Performance Management System | PMS Policy | All | 0 | Annual Performance Management Policy Framework adopted by 31 July 2012 | Date of adoption | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 10 | Municipal Transformation & Institutional Development |  |  |  | N/A | 100 % implementation of approved Annual Performance Management Policy Framework | 100% implementation | N/A | N/A | N/A | Nil Required | 100% implementation | 100% implementation | 3 | N/A | N/A | SDBIP Monthly Reports, Quarterly Reports, Annual Report, 1st Qtr Performance assessments of s57 & 58 managers. Council Resolutions
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 11 | Municipal Transformation & Institutional Development | Performance Management System | Performance Agreements | All | 2 | 30 x signed performance agreement for Managers up to level 3 within 1 month of the beginning of the financial year | Date of signed performance agreements | 410 400 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | savings in 2011/ 2012 year to be identified | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 12 | Municipal Transformation & Institutional Development |  |  | All | 0 | S57 Managers Annual Performance agreements made public within 14 days after the approval of the SDBIP | Date of published performance agreements | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 13 | Municipal Transformation & Institutional Development |  |  | All | 0 | 30 Quarterly Assessments of all Managers up to level 3 | Number of quarterly assessments | N/A | N/A | N/A | N/A | 30 Quarterly Assessments of all Managers up to level 3 | 28 Quarterly Assessments of all Managers up to level 3 | 2 | PMU Manager off sick, Fleet Manager does not have a Workplan | Assessments to be conducted prior to the commencement of the 3rd Quarter assessments | 2nd Quarter assessment report/assessment schedules/attendance registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
OPMS 14 | Municipal Transformation & Institutional Development |  | Automation of Performance Management System | All | 0 | Reporting template (SDBIP) Automated & available online via Council’s Intranet | Date of Automation (live system) | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## IDP overview
INTERGRATED DEVELOPMENT PLAN UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | INTERGRATED DEVELOPMENT PLAN UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 11
| 1.1.1 | OPERATING PROJECTS | 11
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## IDP
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.3 INTERGRATED DEVELOPMENT PLAN
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
IDP 01 | Good Governance & Public Pariticpation | IDP Review | IDP Process Plan 2013/14 | N/A | Approved IDP Process Plan 2012/13 | Submission of IDP Process Plan 2013/14 for approval and adoption by Council on 30 August 2012 | Date of submission of an adopted IDP Process Plan | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IDP 02 | Good Governance & Public Pariticpation |  | Situational Analysis Presentation (Backlogs, baseline data | All Wards | Stats SA Community Survey | Submission of baseline data and backlogs to Couincil by 15 October 2012 | Date of submission of baseline data and backlogs | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IDP 03 | Good Governance & Public Pariticpation |  | Corporate Reviews for Corporate Strategies and Sector plans | All Wards | Five Year Sector Plans in the 2012/13-2016/17 IDP | Completed Approved, Agreed and Revised Strategies and revised sector plans to Council by 30 November 2012 | Date of approved strategies and revised sector plans | 90 000 | N/A | N/A | COGTA | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 141001643 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IDP 04 | Good Governance & Public Pariticpation |  | Conduct Projects Prioritization Process | All Wards | Prioritized projects in the IDP 2012/13-2016/17 | Submission of approved Priority Projects to Council by 30 November 2012 | Date of submission of approved priority projects | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IDP 05 | Good Governance and Public Participation | Public Participation | Stakeholders and Ward Committees Consultations | All Wards | Stakeholders Forum and izimbizo | Conduct stakeholders and community needs engagements by 15 November 2012 & 15 April 2013 | Dates of community needs engagements | 15 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 141001643 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IDP 06 | Good Governance and Public Participation |  | Sector Departments (IGR engagements) |  | Quarterly engagements on agreed priorities for Local Municipality and District | Conducted quarterly IGR Engagements between the Msunduzi Municipality and District Municipality; and Sector departments. | Quarterly meetings | N/A | N/A | N/A | Nil Required | Conducted quarterly IGR Engagements between the Msunduzi Municipality and District Municipality; and Sector departments. | Conducted quarterly IGR Engagements between the Msunduzi Municipality and District Municipality; and Sector departments. | 3 | N/A | N/A | Attendance registers, minutes of the meeting and Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IDP 07 | Good Governance and Public Participation |  | IDP Representative Foum | All Wards | Previous Prioritised needs | Conducted quarterly meetings of the IDP Representative Forum | Quarterly meetings | N/A | N/A | N/A | Nil Required | Quarterly meetings of the IDP Representative Forum-End of March 2013 | Nil | 1 | IDP tabled at Council only on the 20th of March 13 | Community engagements to commence in April 13 | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
IDP 08 | Good Governance and Public Participation | IDP Review | Publication and Printing | N/A | Public Notices and adverts published | Conducted 5 x Public notices and Adverts for public engagements | Number of public notices and adverts | 24 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 141001643 | N/A | N/A |  | 6 000 | N/A | N/A | N/A | N/A | N/A
IDP 09 | Good Governance and Public Participation | IDP Review | Publication and Printing | N/A | IDP Document printed and approved | IDP Document designed, printed and approved by 30 April 2012 | Published IDP Book | 170 000 | N/A | N/A | Council & COGTA | Draft IDP document | Draft IDP document | 3 | N/A | N/A | Minutes of the FC meeting, agenda
[8 empty] | 141001643 | N/A | N/A |  | 40 000 | N/A | N/A | N/A | N/A | N/A
IDP 10 | Good Governance and Public Participation | MDB Plan | Facilitation the MDB Process | 7, 26, 37 AND DEM 4155 | MDB Action Plan Guideline towards 2016 LG Elections | Ficilitated re-determination of municipal boundaries through public participation and stakeholders involvement | Completed engagements for re-determination of municipal boundaries | N/A | N/A | N/A | N/A | As per the MDB Action Plan | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
MSP 18 | Good Governance and Public Participation | Public Participation | Izimbizo | All | 2011/12 Izimbizo | Conduct imbizo in November 2012 & April 2013 | Number and date of imbizo | 250 000 | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | 0131151013 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## MARKETING overview
MARKETING UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | MARKETING UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 6
| 1.1.1 | OPERATING PROJECTS | 6
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## MARKETING
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
1.4 MARKETING
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
M&C 01 | Municipal Transformation and Institutional Development | Corporate Image | Corporate Identity | N/A | No Corporate identity. | Approved Corporate Identity Manual and implementation. | Adoption Date | N/A | N/A | N/A | Nil Required | 50% Implementation | Corporate Communication documents issued as per corporate identity manual | 3 | N/A | N/A | Communication Documents
[7 empty] | % Implementation | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
M&C 02 | Social and Economic Development. | Marketing | City Marketing Strategy | N/A | No Marketing Strategy. | Approved Marketing Strategy, and 100% implementation. | Adoption Date | N/A | N/A | N/A | Nil Required | 50% Implementation | Has been discussed at E.D Portfolio Committee | 2 | Delays in Committee meetings | N/A | SMC and Portfolio Committees resolutions. Draft Document.
[7 empty] | % Implemented | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
M&C 03 | Good Governance | Communication | Municipal Newspaper | N/A | No existing Municipal Newspaper. | Monthly copies of newspaper published & distributed. | Number of newspapers published and distributed monthly | 1 200 000 | N/A | N/A | Council | Monthly copies of newspaper published & distributed. | Published and distributed 50 000 copies per month | 3 | N/A | N/A | Copies
[8 empty] | 0111001330 | N/A | N/A |  | 300 000 | N/A | N/A | N/A | N/A | N/A
M&C 04 | Good Governance |  | Communication Strategy | N/A | Approved Communication Strategy needing review. | Reviewed Communication Strategy and 100% Implementation | 100% implementation. | N/A | N/A | N/A | Nil Required | 100 % Implementation | Implementation: Newspaper, media, newsletter, MCF, Website, events, billboards | 3 | N/A | N/A | Minutes, website, records, pictures, newsletter, newspaper.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
M&C 05 | Good Governance |  | Communications Forum. | N/A | No Forum. | Established Communicator's Forum | Existance of a functional MCF by 30 June 2013 | N/A | N/A | N/A | Nil Required | Established Msunduzi Communicato'rs Forum. | Inaugural meeting of MCF. | 3 | N/A | N/A | Minutes of MCF Meeting
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
M&C 06 | Good Governance |  | Municipal Website | N/A | Operational but not compliant nor effective. | 100% compliant website | 100 % compliant | N/A | N/A | N/A | Nil Required | uploading of approved documents | Uploaded two by laws and two policies, and one indigent application form. | 3 | N/A | N/A | Municipal Website under By laws and Policies.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## FINANCE COVER
ANNEXURE 1(F): FINANCE BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## FINANCE overview
FINANCE BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | FINANCE BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 42
| 1.1.1 | OPERATING PROJECTS | 42
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## BUDGET overview
BUDGET & TREASURY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | BUDGET & TREASURY UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 11
| 1.1.1 | OPERATING PROJECTS | 11
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Budget & Treasury
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.1 BUDGET & TREASURY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
B&T 01 | Financial Viability and Management | Compliance | IDP/BUDGET Process Plan | N/A | 2011/2012 process plan approved on the 31 August 2011 | Submission of IDP/Budget process plan for 2013/14 on the 01 July 2012 | Date of approved process plan being 31 August 2012 | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 02 | Financial Viability and Management |  | Reporting | N/A | N/A | 12 Section 71 monthly reports produced within 10 working days after the month ends | All reports in terms of S 71 to be produced and submitted within 10 working days after month end | N/A | N/A | N/A | Nil Required | monthly reports produced within 10 days after the month ends and submitted | January and February reports have been produced, March will only be done @ end of month | 2 | Until the end of the month then a report shall be prepared | N/A | NT feedback report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 03 | Financial Viability and Management |  |  | N/A | N/A | 4 quarterly reports produced within 10 working days after the quarter ends | 1 x quarterly report produced within 10 working days after the end of each quarter | N/A | N/A | N/A | Nil Required | 1 x quarterly report produced within 10 working days after the end of each quarter | Second quarter reports were produced and submitted | 3 | N/A | N/A | Council resolution and NT treasury feedback report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 04 | Financial Viability and Management |  |  | N/A | N/A | 1 mid year / adjustment budget review S72 report produced by 01 December 2012 | Date of submission of mid year adjustment budget to SMC | N/A | N/A | N/A | Nil Required | 1 mid year / adjustment budget review S72 report produced by 25 January 2013 | Mid-year budget was tabled to Council in January 2013 | 3 | N/A | N/A | Council resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 05 | Financial Viability and Management |  | Budget Policy | N/A | 2011/2012 Budget policy approved on the 2012/05/28 | Reviewed Budget Policy by 31 May 2013 | Date of submission of draft budget policy to SMC | N/A | N/A | N/A | Nil Required | Submission of draft budget to SMC | Second round of budget discussion by SMC was on 18 March 2013 | 3 | N/A | N/A | SMC resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 06 | Financial Viability and Management |  | Virement Policy | N/A | 2011/2012 Virement policy approved on the 2012/05/28 | Reviewed Virement Policy by 31 May 2013 | Date of submission of draft Virement policy to SMC | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 07 | Financial Viability and Management | Annual Financial Statements | Cash flow | N/A | Daily, weekly, monthly and quarterly monitoring and reporting | Sound cash coverage ratio is maintained | Daily, weekly, montly & quarterly monitoring and reporting. | N/A | N/A | N/A | Nil Required | 66 daily, 12 weekly, 3 monthly & 1 quarterly reports produced | Daily reports for January and February have were produced, Second quarter | 3 | N/A | N/A | SMC resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 08 | Financial Viability and Management |  | Financial Control | N/A | NIL | Submission of budget procedure manual to SMC by 30/09/12 | Budget procedure manual to be submitted to SMC for approval | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 09 | Financial Viability and Management |  |  |  | NIL | undertake workshop on budget procedure manual | Workshop to be facilitated on budget procedure manual | N/A | N/A | N/A | Nil Required | Upon completion of workshop on budget procedure manual then ensure full implementation | Joint workshop is planned for all finance related policies | 2 | Most of finance related draft policies were approved by Council on 20th March 2013 | Joint workshop for all finance related policies will take place during April 2013 | Draft Policies
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
B&T 10 | Financial Viability and Management |  | Annual Financial Statements | N/A | 2010/2011 Audited Annual financial statements tabled on the 25th of January 2012. | Submission to Internal Auditors for review on the 10th August 2013 | 1. Date of review of Annual Financial Statements by Internal Auditors | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | 2. Submission of Annual Financial Statements to the Auditor General on 31 August 2013 | 2. Date of submission of Annual Financial Statements | N/A | N/A | N/A |  | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
B&T 11 | Financial Viability and Management |  | Audit Compliance | N/A | Matters of emphasis | Clean audit report | Reduction of matters of emphasis in connection AFS amendments | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## EXP MGT overview
EXPENDITURE MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | EXPENDITURE MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 10
| 1.1.1 | OPERATING PROJECTS | 10
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Expenditure
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.2 EXPENDITURE MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
EXM 01 | Financial viability and Management | Trade and Sundry Paments | Cost containment strategy | N/A | Nil | 1.Submit Draft Cost Containment Startegy to SMC by 31st of Janaury 2013 | Submission of Draft Strategy. | N/A | N/A | N/A | N/A | Draft Strategy to SMC by 31 January 2013. | Draft Strategy considered by SMC. | 3 | N/A | N/A | Minutes of SMC and Draft Strategy.
EXM 02 | Financial viability and Management | Payment of all invoices within 30 days | N/A | N/A | About 10 % of supplier paid long after 30 days. | All invoices are paid within 30 days from date of receipt of invoice. | Report of payments made after 30 days. | N/A | N/A | N/A | N/A | Payment within 30 days of receipt of invoice. | 93% of Payments are made within 30 Days of receipt of invoice. | 2 | Internal Delays | Review of payment prcedures has been undertaken. | Age Analysis.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EXM 03 | Financial viability and Management | Payment of all invoices within 30 days | Management of expenditure | N/A | 100 % of payments to have Expenditure Committee approval | All of payments to have Expenditure Committee approval | All payments have expenditure committee approval. | N/A | N/A | N/A | N/A | All payments made to have Expenditure Committee approval. | All payments made to have Expenditure Committee approval. | 3 | N/A | N/A | Expenditure Committee Register.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EXM 04 | Financial viability and Management | Management of General insurance fund | Management of claims by ensuring that all claims honoured are valid | N/A | 100 % of claims are properly assessed | All insurance claims received are assessed within a week. | All insurance claims have assessors report. | N/A | N/A | R17m | N/A | 100% of claims are properly assessed prior to payment | 100% of claims are properly assessed prior to payment | 3 | N/A | N/A | Insurance Claim Register.
EXM 05 | Financial viability and Management | Management of General insurance fund | Prepare monthly reports on insurance claims to Council | N/A | Monthly reports are prepared and presented | 12 Monthly Insurance claims reports are prepared and submitted to OMC by 30 June 2013. | 12 monthly reports. | N/A | N/A | N/A | N/A | 3 reports | 3 Reports | 3 | N/A | N/A | Minutes fo OMC and Report.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EXM 06 | Financial viability and Management | Management of General insurance fund | Operationalisation of the insurance bank account | N/A | Bank account not utilised | All receipts of insurance and payments go through the insurance bank account | All insurance transactions go through the insurance bank account. | N/A | N/A | N/A | N/A | Transfer funds as per cash flow requirements. | Transfer funds as per cash flow requirements. | 3 | N/A | N/A | Bank Account.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EXM 07 | Financial viability and Management | Remuneration Management | All salaries are paid on due date. There are sufficient funds to pay salaries on a monthly basis. | N/A | Salaries are paid on the 24th each month | Payroll to be submitted to Municipal Manager by 19th of each month for payment by 24th each month. Other statutory payments by the 6th of the following month. | Payroll submitted by 19th of each month. | N/A | N/A | N/A | N/A | 3 payments per quarter | 3 payments per quarter | 3 | N/A | N/A | Payroll.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EXM 09 | Financial viability and Management | MFMA compliance | Ensure compliance with all MFMA requirements | N/A | Audit report for 2010-2011 with irregular expenditure, fruitless expenditure and wasteful expenditure | Submit monthly report to SMC of Fruitless and Wastefull Expenditure. | 12 monthly reports. | N/A | N/A | N/A | N/A | 3 reports | 3 reports | 3 | N/A | N/A | Minutes of SMC and Report.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EXM 11 | Financial viability and Management | Development of Financial Policy | Develop a new financial policies in line with treasury regulations, MFMA, council resolutions etc | N/A | Outdated financial regualations issued in 2005 | Submit draft financial policy to SMC by 28 February 2013. | Draft financila policy by 28 February 2013. | N/A | N/A | N/A | N/A | Draft policy to SMC by 28 February 2013. | Draft policy to SMC by 28 February 2013. | 3 | N/A | N/A | Draft policy.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EXM 12 | Financial viability and Management | Financial Management Systems | Sourcing of the new FMS to deal with the legacy | N/A | 41 Different systems | Ensure that, the specifications for the new financial system are advertised by 31th March 2013. | Advertisement by 31 March 2013. | 11 000 000 | N/A | N/A | Council | Advertise specifications. | Draft Advert | 2 | NT Circular 57 requirements. | Meeting with NT to take place on 2 and 3 April 2013. | Draft Advert.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## REV MGT overview
REVENUE MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | REVENUE MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 13
| 1.1.1 | OPERATING PROJECTS | 13
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Revenue
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.3 REVENUE MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
RVM 01 | Financial Viability and Management | Credit Control and billing | Reduction in estimates | All | 71% of meters read | 90% of meters read | % of meters read | N/A | N/A | N/A | Nil Required | 85% of meters read | Total :113497 meters , Read 87 472 : Progress 77% | 3 | Meter Audit is still in progress | Reconciliation of billing records to Meters audit | Meter Reading Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
RVM 02 | Financial Viability and Management | Credit Control and billing | Accurate billing of rates | All | 85% accuracy of billing iro rates | 100% accurate billing iro rates | % of accurate billing iro rates | N/A | N/A | N/A | Nil Required | 97% accurate billings ito names | 113 497 Bills sent and only 400 returned / 99.65% accurate ito names | 4 | This difference will be solved by Data Cleansing | Data Cleansing | BiIling Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
RVM 03 | Financial Viability and Management | Credit Control and billing | Debtors | All | 80% debt collection | 100% debt collection | % of Debt collection | N/A | N/A | N/A | Nil Required | 95% debt collection - current | 92 % of current Debtors Collected | 2 | Returning Bills and Bills unbundling for Govt Departments | Finish Data Cleansing and Bills unbundling | Debtors Age analysis
[8 empty] | N/A | N/A | N/A |  | 25% debt collection - outstanding (historical debt) | R23 Million has been collected and this mainly from government debt | 2 | The credit controllprocesses has just been and it will take time and more in particular the private household | Implementation of credit controll | Debtors Age analysis
RVM 04 | Financial Viability and Management | Credit Control and billing | Database clean-up | All | 14 000 accounts | 14 000 returned mail accounts delivered to consumer | Number of accounts cleaned | N/A | N/A | N/A | Nil Required | 4000 consumers reached | only 400 came back last month | 4 | only those bills that getsent out but we still have a number of unbilled customers | Data Cleansing | BiIling Report versus Valuation Roll
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
.
.
RVM 05 | Financial Viability and Management | Policies | Credit Control & Debt Collection Policy | All | 2013-05-31 | Review Credit Control & Debt Collection policy by 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Required | First Draft Credit Control & Debt Collection Policy | First draft Completed and awaiting to be approved by the council | 3 | Waiting for council approval | Submitted for council approval | Draft Policy
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
RVM 06 | Financial Viability and Management | Policies |  | All | 2012-05-31 | 100% Implementation and monitoring of the Credit Control & Debt Collection policy | 100% Implementation and monitoring of the Credit Control & Debt Collection policy | N/A | N/A | N/A | Nil Require | 100% Implementation and monitoring of the Credit Control & Debt Collection policy | More staff has been appointed and credit control procedure manual has been communicated to the staff | 3 | The credit controll policy is still to be adopted by the council | Policy adoption | Draft Policy and procedure manual workshop minutes
RVM 07 | Financial Viability and Management | Policies | Tariff Policy | All | 2013-05-31 | Review Tariff Policy by 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Require | First Draft Tariff Policy | Draft finished | 3 | Still being considered for inputs | Finalising inputs and submitt the policy for council adoption | Draft policy
RVM 08 |  |  |  | All | 2012-05-31 | 100% Implementation and monitoring of Tariff Policy | % implementation and monitoring of Tariff Policy | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Tariff Policy | Draft finished | 2 | Cannot be implemented without council adoption | Draft being circulated for inputs with a view of final council adoption | Draft policy
RVM 09 | Financial Viability and Management | Policies | Rates Policy | All | 2013-05-31 | Review Rates policy by the 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Required | First Draft Rates Policy | Draft finished | 2 | Inputs are still being incorporated into the policy | finalising inputs and submitt the policy for council adoption | Draft policy
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
RVM 10 | Financial Viability and Management | Policies |  | All | 2012-05-31 | 100% Implementation and monitoring of Rates policy | % Implementation and monitoring of Rates Policy | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Rates policy | Current is implemented 100% and reviewed one is still being considered for inputs | 3 | Draft is till up for council adoption | Adpoting policy for the new financial year | Draft policy
RVM 11 | Financial Viability and Management | Policies | Indigent Policy | All | 2013-05-31 | Review Indigent policy by 31 May 2013 | Date of adopted policy | N/A | N/A | N/A | Nil Required | First Draft Indigent Policy | Ready for council adpotion | 4 | Hick ups interms of langauge and content but the policy almost ready for council adpotion | Adpoting policy for the new financial year | Draft policy
RVM 12 |  |  |  | All | 2012-05-31 | 100% Implementation and monitoring of Indigent policy | % Implementation and monitoring of Indigent policy | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Indigent policy | Only the current one is being implemented | 4 | Council adoption of the new policy | Adpoting policy for the new financial year | Old policy and the reviewed one
RVM 13 | Financial Viability and Management | Policies | Indigent Register | All | 2012-07-01 | 100% Implementation and monitoring of Indigent register | % Implementation and monitoring of Indigent register | N/A | N/A | N/A | Nil Required | 100% Implementation and monitoring of Indigent register | Advert is out and we have received 1200 applications for registration so far | 3 | The date for registration is still open until the 15 April 2013 | Prossesing the applications received | Applications regsiter

## SCM overview
SUPPLY CHAIN MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | SUPPLY CHAIN MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 8
| 1.1.1 | OPERATING PROJECTS | 8
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## SCM
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
2.4 SUPPLY CHAIN MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
SCM 01 | To promote sound financial management and reporting, effective budgeting & revenue enhancement | Supply Chain Management | Annual Procurement Plan | N/A | 30/09/2011 | Submission of the Procurement Plan to SMC by 30 June 2013 | Date of submission of procurement plan | N/A | N/A | N/A | Nil Required | N/A | N/A | not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SCM 02 | To promote sound financial management and reporting, effective budgeting & revenue enhancement | Supply Chain Management | Annual Procurement Plan | N/A | Nil | Monitoring of the Annual Procurement Plan | monitoring of the Annual Procurement Plan | N/A | N/A | N/A | Nil Required | Monitoring of the Annual Procurement Plan | Monitoring of the Annual Procurement Plan | 3 | N/A | N/A | contract register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SCM 03 | To promote sound financial management and reporting, effective budgeting & revenue enhancement | Supply Chain Management (SCM) | SCM Policy Review | N/A | 30/05/2012 | Submission of SCM Policy by 31/10/2012 | Date of submission reviewed SCM Policy | N/A | N/A | N/A | Nil Required | N/A | N/A | not applicable | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SCM 04 | To promote sound financial management and reporting, effective budgeting & revenue enhancement |  | SCM Policy Implementation | N/A | 30/07/2012 | communication of SCM Policy to all Council staff | communication of SCM Policy to all Council staff | N/A | N/A | N/A | Nil Required | communication of SCM Policy to all Council staff | communication of SCM Policy to all Council staff | 3 | N/A | N/A | communication/minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SCM 07 | To promote sound financial management, effective budgeting & revenue enhancement |  | Monitoring of Irregular Expenditure | N/A | 2011-07-01 | Report of Irregular expenditure on quaterly basis | Report of Irregular expenditure on quaterly basis | N/A | N/A | N/A | Nil Required | Report on irregular expenditure on quaterly basis | Report on irregular expenditure on quaterly basis | 3 | N/A | N/A | SMC AGENDA
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SCM 09 | To promote sound financial management, effective budgeting & revenue enhancement | Supply Chain Management | Bid Processing | N/A | 120 days | Bid time processing not to exceed the stipulated time, 7 day quatation 21 days turnaround time, competitive bidding 75 days turnaround time | Bid time processing not to exceed the stipulated time, 7 day quatation 21 days turnaround time, competitive bidding 75 days turnaround time | N/A | N/A | N/A | Nil Required | Bid time processing not to exceed the stipulated time, 7 day quatation 21 days turnaround time, competitive bidding 75 days turnaround time | Bid time processing not to exceed the stipulated time, 7 day quatation 21 days turnaround time, competitive bidding 75 days turnaround time | 2 | Most contractors are unable to meet the 14 day period for the submission of insurances and surities, BSC and BEC lack of quorum, Objections | Bid committees to meet on regular basis | CONTRACT REGISTER
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SCM10 | To promote sound financial management, effective budgeting & revenue enhancement | Supply Chain Management | Reporting | N/A | N/A | 4 Quaterly report on tenders awarded submitted to Council within 10 days after the monthends | 4 Quaterly report on tenders awarded submitted to Council within 10 days after the monthends | N/A | N/A | N/A | Nil Required | 1 Quaterly report on tenders awarded submitted to SMC within 10 days after the monthends | 1 Quaterly report on tenders awarded submitted to SMC within 10 days after the monthends | 3 | N/A | N/A | OMC AGENDA
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SCM11 | To promote sound financial management, effective budgeting & revenue enhancement | Supply Chain Management | Reporting | N/A | 2011-06-30 | 1 X Implementation and monitoring of SCM policy report submitted to SMC annually by 31 July 2012 | 1 X Implementation and monitoring of SCM policy report submitted to SMC annually by 31 July 2012 | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A

## COMM SERV COVER
ANNEXURE 1 (G): COMMUNITY SERVICES BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
SDBIP 2012/2013

## COMM SERV overview
COMMUNITY SERVICES BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | COMMUNITY SERVICES BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 69
| 1.1.1 | OPERATING PROJECTS | 67
| 1.1.2 | CAPITAL PROJECTS | 2
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## ABM overview
AREA BASED MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | AREA BASED MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 8
| 1.1.1 | OPERATING PROJECTS | 8
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## ABM
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.1 AREA BASED MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
ABM 01 | Good Governance Public Participation | Community Participation | Public Participation Policy | All | N/A | Public Participation Policy adopted by 30/9/12 | Date of approval | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ABM 02 | Good Governance Public Participation | Community Participation |  |  | N/A | 37 public participation policy ward committee workshops conducted by 28 June 2013 | 37 public participation workshops conducted by 28 June 2013 | N/A | N/A | N/A | Nil Required | Conduct 18 ward committeePublic Participation workshops | 18 ward committee presentations done | 3 | N/A | N/A | PPP presentations file (Att Register)
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ABM 06 | Basic Service Delivery | Community Participation | Conduct Ward audits | All | No ward audits | 37 ward audits reviewed and updated by 28/06/2013 | 37 ward audits completed by 28/06/2013, reviewed& updated quarterly | N/A | N/A | N/A | Nil Required | Ward audits reviewed & updated quarterly | ward audits reviewed | 3 | N/A | N/A | Ward Audits file
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ABM 07 | Good Governance Public Participation | Community Participation | Monitor functioning of war rooms | All | No tool to monitor functioning of War Rooms | Develop tool to monitor functioning of war rooms by 30/09/2012 | Developed tool to monitor functioning of war rooms | N/A | N/A | N/A | Nil Required | Submit Progress report on functioning of war rooms to OMC by 31/03/2013 | Submit Progress report on functioning of war rooms to OMC by 31/03/2013 | 3 | N/A | N/A | Progress reports
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ABM 09 | Good Governance Public Participation | Community Participation | Vulindlela Rural Development Strategy | 1 to 9 | No Rural Strategy | Rural Development Strategy for Vulindlela by 30/06/13 | Developed Rural Strategy by 30/06/13 | N/A | N/A | N/A | Nil Required | Submit Draft Strategy for consideration by MANCO | strategy approved & discussed with ward cllr & amakhosi | 3 | N/A | N/A | rural Devel Strategy file (Att register)
ABM 10 | Good Governance Public Participation | Community Participation | Review ABM management boundaries | All | 5 Outdated ABM management boundaries | Adopted ABM boundaries by 30/06/13 for 5 Areas | All 5 areas having developed ABM boundaries | N/A | N/A | N/A | Nil Required | Approve ABM boundaries by EXCO | Boundaries approved by EXCO | 3 | N/A | N/A | ABM Boundaries file (Resolution)
ABM 11 | Good Governance Public Participation | Community Participation | Conduct IDP Budget need survey | All Council Izimbizos | Outdated completed Izimbizo Budget/IDP survey | Completed IDP/Budget needs survey completed | IDP/Budget needs survey completed | N/A | N/A | N/A | Nil Required | Conduct Budget/IDP izimbizo survey | N/A | NOT APPLICABLE | No budget izimbizo this quarter | Budget/IDP Izimbizo to be held in April 2013 | N/A
ABM 12 | Good Governance Public Participation | Community Participation | Operation Sukuma Sakhe functionality monthly reports | All | No broad/reconciled/consolidated Operation Sukuma Sakhe reports | Submission of Operation Sukuma Sakhe monthly reports | Monthly report on Operation Sukuma Sakhe submitted | N/A | N/A | N/A | Nil Required | 3 monthly Sukuma Sakhe Reports produced | 3 monthly Reports submitted | 3 | N/A | N/A | OSS report s file

## HS SS overview
HEALTH & SOCIAL SERVICES UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | HEALTH & SOCIAL SERVICES UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 23
| 1.1.1 | OPERATING PROJECTS | 23
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Health & Social Serv
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.2 HEALTH & SOCIAL SERVICES
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
HIV 01 | Social and Economic Development | HIV&AIDS | Community Counselling Course | All wards | 9 | 12 Counselling Course sessions Conducted by 30.06.2013 | Number of counseling Course conducted | N/A | N/A | N/A | N/A | 3 Counselling Course sessions Conducted by31.03.2013 | 3 Counselling Course sessions Conducted | 3 | N/A | N/A | Counselling Attendance Registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HIV 02 | Social and Economic Development |  | Community Peer Education Training | Not available, dependent on requests | 4 | 6 Peer Education training Conducted by 30.06. 2013 | Number of Peer Education Training conducted | N/A | N/A | N/A | N/A | 2 Peer Education training Conducted by 31.03.2013 | 2 Peer Education Training conducted | 3 | N/A | N/A | Peer Educator Register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HIV 03 | Social and Economic Development |  | Community Awareness Programmes | Not available, dependent on finalized year plan. | 3 | 5 Community Awareness programmes conducted by 30.06 .2013 | Number of programmes conducted | N/A | N/A | N/A | N/A | 2 Community Awareness programmes conductedby 31.03.2013 | 13 Community Awareness programmes conducted. | 5 | N/A | N/A | Registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HIV 04 | Social and Economic Development |  | Condom Distribution Outlets | 1;3;4;6;7;8;9;14;16;17;19;21;26;29;31;32;33;36 & 37 | 18 | Additional 19 wards with condom distribution outlets by 30.06. 2013 | number of Wards with Condom Distribution outlets | N/A | N/A | N/A | N/A | Additional 5 wards with condom distribution outlets by 31.03.2013 | 8 Wards.Wards 11,12,22,24,27, 28, 32and34 | 4 | N/A | N/A | HIV/AIDS Register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HIV 05 | Social and Economic Development |  | Home Based Care Groups | All wards | 32 | Additional 4 wards with fully functioning Home Based Care groups by 30.06. 2013 | Number of wards with fully functioning Home Based Care groups | N/A | N/A | N/A | N/A | Additional 1 ward with fully functioning Home Based Care groups by 31.03.2013 | The Councillor indicated there is no need for Home Based Care Group presently | 1 | The Councillor indicated there is no need for Home Based Care Group presently | Await Ward Councillor's decision | Letter from Councillor in Ward 36
[8 empty] | N/A | N/A | N/A |  | NA | N/A | N/A | N/A | N/A | N/A
HIV 06 | Social and Economic Development |  | Local AIDS Council meetings | N/A |  | 4 LAC meetings Held in the year by 30.06.2013 | Number of LAC meetings conducted | N/A | N/A | N/A | N/A | 1 LAC meeting Held by 31.03.2013 | 1 LAC meeting held on the 1/3/2013 | 3 | N/A | N/A | LAC Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HIV 08 | Social and Economic Development |  | Ward AIDS Committees | All wards | 25 | 16 additional Ward AIDS Committeesestablished by 30.06.2013 | Number of new Ward AIDS Committees in place | N/A | N/A | N/A | N/A | 4 additional Ward AIDS Committees established by 31.03.2013 | 15 additional Ward AIDS Committees established Wards 4,5,9,10,14,,16,17,19,20,23,24,26,28,29 and 35 | 5 | N/A | N/A | Ward AIDS Committee Membership Document
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HIV 09 | Social and Economic Development |  | Ward AIDS Strategy | All | Nil | Adopted Ward AIDS Strategy by the 31 July 2012 | Date of adoption of Ward AIDS Strategy | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HIV 10 | Social and Economic Development |  | Ward AIDS Strategy | All | Nil | Two Quarterly reports on implementation of Ward AIDS Strategy submitted to the Strategec Management Committee by 30.06.2013 | % Implementation of Ward AIDS Strategy | N/A | N/A | N/A | N/A | Quarterly report on implementation of Ward AIDS Strategy submitted to the Strategec Management Committee by 18.03.2013 | Quarterly report on implementation of Ward AIDS Strategy submitted to the Strategec Management Committee for 25/03/2013 | 3 | N/A | N/A | Quarterly Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 03 | Social and Economic Development | Environmental Health | Air Pollution Control | 12; 22; 23; 24; 26; 29; 33; 35 ; 36 | 120 premises inspected annually | 120 premises to be inspected annually by 30.06.2013 | Number of premises inspected annually | N/A | N/A | N/A | Nil Required | 30 premises to be inspected by 31.03.2013 | 22 premises inspected | 2 | Increased work load of the Acting Manager | Appointment of Manager: Environmental Health | property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 04 | Social and Economic Development |  | Water Quality Control | All wards | 900 samples taken/ analyzed annually | 19, 25,28 samples taken weekly on a rotation by 30.06.2013 | Number of samples taken weekly from reservoirs/ consumer points | 40 000 | n/a | nil | Council | 225 samples taken weekly on a rotation by 31.03.2013 | 288 Samples taken | 4 | N/A | N/A | Sample database and reports in Laboratory
[8 empty] | 3471001030 |  |  |  | 10 000 | N/A | N/A | N/A | N/A | N/A
EHS 05 | Social and Economic Development |  | Food Quality Control | All wards | 1600 premises inspected annually | 1600 premises inspected annually by 30.06.2013 | Number of premises inspected annually | N/A | N/A | N/A | Nil Required | 400 premises inspected by 31.03.2013 | 440 food premises inspected | 4 | N/A | N/A | property files in records room
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 06 | Social and Economic Development |  | Food Sampling | All wards | 360 food samples and 120 swabs taken/ analyzed annually | 90 food samples and 30 swabs to be taken/ analyzed quarterly by 30.06.2013 | Number of Samples taken quarterly | 40 000 | n/a | nil | CNL | 90 food & 30 swabs to be taken/ analyzed quarterly by 31.03.2013 | 110 food samples and 110 swabs taken | 3 | N/A | N/A | Sample database and reports in Laboratory
[8 empty] | 3471001030 | N/A | N/A |  | 10 000 | 1 664 | N/A | N/A | N/A | N/A
EHS 07 | Social and Economic Development |  | Vector Control | All wards | 1200 sites Baited/ Treated annually | 1200 sites annually: 100 sites baited, treated monthly by 30.06.2013 | Number of sites treated annually | 70 000 | N/A | N/A | Council | 300 (100 sites baited, treated monthly) by 31.03.2013 | 883 sites treated | 5 | N/A | N/A | monthly vector control programme files
[8 empty] | 3471001560 | N/A | N/A |  | 17 500 | 6 478 | N/A | N/A | N/A | N/A
EHS 08 | Social and Economic Development |  | Public Complaint investigations | All wards | Investigate and finalize complaints | 100% Investigations in a turnaround time of 5 days by 30.06.2013 | % investigated in 5 days | N/A | N/A | N/A | Nil Required | 100% Investigations in a turnaround time of 5 days by 31.03.2013 | 100% (274) complaints investigated within a turnaround time of 5 days) | 3 | N/A | N/A | Complaints register/file
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 09 | Social and Economic Development |  | Health Care Risk Waste Control | All wards | 480 premises inspected annually | 480 premises inspected annually by 30.06.2013 | Number of Inspections/ Registrations annually | N/A | N/A | N/A | Nil Required | 120 (40 Inspections/ Registrations monthly) by 31.03.2013 | 123 premises inspected | 3 | N/A | N/A | data base and property files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 10 | Social and Economic Development |  | Tobacco Control | All wards | 1680 premises inspected annually | 1680 premises inspected annually by 30.06.2013 | Number of Inspections annually | N/A | N/A | N/A | Nil Required | 420 (140 Inspections monthly) by 31.03.2013 | 516 premises inspected | 3 | N/A | N/A | property files in records room
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 11 | Social and Economic Development |  | Places of Care | All wards | 240 premises inspected annually | 240 premises to be inspected by 30.06.2013 | Number of Inspections/ Registrations annually | N/A | N/A | N/A | Nil Required | 60 (20 Inspections/ Registrations monthly) by 31.03.2013 | 120 premises inspected | 5 | N/A | N/A | property files in records room
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 12 | Social and Economic Development |  | Funeral Undertakers; cemeteries and crematoria Control | All wards | 30 premises inspected annually | 30 premises inspected annually by 30.06.2013 | Number of Inspections/ Registrations annually | N/A | N/A | N/A | Nil Required | 7 Inspections/ Registrations quarterly by 31.03.2013 | 13 premises inspected | 4 | N/A | N/A | property files in records room
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 13 | Social and Economic Development |  | Health Surveillance of commercial, industrial and residential premises | All wards | 800 premises inspected annually | 800 premises inspected annually by 30.06.2013 | Number of premises inspected annually | N/A | N/A | N/A | Nil Required | 200 premises inspected by 31.03.2013 | 599 premises inspected | 5 | N/A | N/A | property files in records room
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 14 | Social and Economic Development |  | Communicable Disease Control | All wards | Investigate and finalise disease notifications | 100% investigations in a turnaround time of 5 days by 30.06 2013 | % investigated within 1 to 5days | N/A | N/A | N/A |  | 100% investigations in a turnaround time of 5 days by 31.03.2013 | 80% (110) notifications investigated in a turnaround time of 5 days | 2 | Jan 2013 staff on leave & municipal vehicles unavailable | Practitioners were to assist to ensure targets met going forward. | data base and CDC files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 15 | Social and Economic Development |  | Health Education/ Promotion | All wards | 60 programs annually | Conduct 60 health education/ promotion programs annually by 30.06.2013 | Number of programmes annually | N/A | N/A | N/A | Nil Required | Conduct 15 health education/ promotion programs by 31.03.2013 | 133 health education sessions conducted | 5 | N/A | N/A | training files
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EHS 16 | Social and Economic Development |  | Compliance and Enforcement Measures | All wards | Follow up and finalize all notices and prosecutions | 100% Notices/ summonses issued when contraventions occur | % summonses issued when contraventions occur | N/A | N/A | N/A | Nil Required | 100% Notices/ summonses issued when contraventions occur by 31.03.2013 | 100% (232) notices issued | 3 | N/A | N/A | property files in records room
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## Comm DEv overview
COMMUNITY DEVELOPMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | AIRPORT, CREMATORIA, ART GALLERY, CEMETERIES UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 25
| 1.1.1 | OPERATING PROJECTS | 23
| 1.1.2 | CAPITAL PROJECTS | 2
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Community Development
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.3 COMMUNITY DEVELOPMENT (LIBRARIES, ART GALLERIES, CREMATORIA & CEMETERIES, PARKS, COMMUNITY FACILITIES, WASTE MANAGEMENT, LANDFILL SITE)
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LBS 01 | Basic Service Delivery | Library Services | To assess and develop a maintainance plan for libraries | 12,35,28,32,34,37,27,36 | 9 Libraries | 9 Libraries maintained in an operating order | Number of Libraries maintained | 3 000 000 | N/A | N/A | Council/ Arts & Culture | 3 Libraries maintained as per assessment | Nil | Nil Achieved | insufficient funds | allocation of funds | Maintainance plan documents
[8 empty] | 513 100 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LBS 02 | Basic Service Delivery | Library Services | Purchasing of books & processing material | 12,35,28,32,34,37,27,36 | 15000 -2011/2012 6 Rolls of material | Purchased books to a value of R693 000 | value of bookspurcased. | 1 700 000 | N/A | N/A | Council/ Arts & Culture | book selection process | Report submitted to BAC | Target Partially Met | Report submitted to BAC requesting authorisation for the purchasing of books and other information resources rejected 25/10/12- | Have to devise a new tender process for acquisition of books | BAC report
[8 empty] | 5131001643 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
TAG 01 | Art & Culture Community out Reach Programme | Art & Culture Community out Reach Programme | Arts Exhibitions | N/A | 12 | Conducted 8 exhibitions per annum | Number of Exhibitions | 693 000 | N/A | N/A | Council & Prov Arts & Culture Department | 2 x Art Exhibitions Conducted | 2 x Art Exhibitions Conducted | 3 | N/A | N/A | Exhibition schedule
[8 empty] | 4804668337 | N/A | N/A |  | 173 250 | N/A | N/A | N/A | N/A | N/A
PKS 01 | Basic Service Delivery | Grass Cutting | City Grass Cutting | All | Once every four months | Cut grass twice per season ( Sept t- April) | Number of Cuts per surburb |  | N/A | N/A | Council & Cogta | second cut 63 per surburb | 32 out of 63 surburbs cut | 2 | vacancies, breakdowns with vehicles, tractors and brushcutters. | Continuos weekly meeting with fleet manager for effective turnaruond time | weekly and monthly perfomance schedule
[8 empty] | 402404412 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 02 | Basic Service Delivery | Development of new parks. | Two Parks in Greater Edendale | Greater Edendale | 16 community parks zero parks in edendale and vulindlela | Develop Busines plan for the establishment of two parks in Greater Edendale | draft plan approved by SMC. | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | Business Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 03 | Basic Service Delivery | Parks | maintainance and rehabilitation of the regional park. | 27 | 1 regional park delapidated alexandra regional park. | Revitalization business plan completed by December 2012 | Completed business plan submitted in December 2012 | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 04 | Basic Service Delivery | Parks | Traffic islands and city entrances beautified | All | 10 traffic islands and main entrances into the city require grass cutting. | monthly grass cutting at 10 traffic islands and main entrances | Number of traffic islands and main entrances maintained |  | N/A | N/A | Council | 10 traffic islands and main entrances grass cut | 10 traffic islands and main entrances grass cut | 3 | N/A | N/A | Traffic Island Maintenance Monthly Report
[8 empty] | 402404412 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 05 | Basic Service Delivery | Community facilities | Halls | All | Sixty halls requiring Maintenance | Develop Maintenance plan for sixty halls | Completed maintenance plan for sixty halls | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | Business Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 06 | Basic Service Delivery | Community facilities | Sport facilities | All | Sixty five sports facilities requiring Maintenance | Develop Maintenance plan for sixty five Sports facilities. | Completed maintenance plan for sixty five Sports facilities. | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | Business Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 07 |  | Sport Development | Msunduzi Sport and Recretion Plan | All | 20 Satellites | Develop Msunduzi Sport & Recreation Plan gy 31 Mar 2013 | Completed Msunduzi sport & Recreation Plan Dec 2012 | N/A | N/A | N/A | Nil Required | Msunduzi sport/Rec. Business plan | Draft Msunduzi Sport/Rec. Business plan | 2 | Alignment with National Sport and Recreation Plan and sector plans | Include NSRP strategic objectives and Prov. Dept. of Sport/Rec sector plans | Draft Business Plan
PKS 08 | Basic Service Delivery | Community facilities | Athletics track | All | No athletic track in Msunduzi | fencing and drainage levels at Alexandra Park athletic track | Completed drainage and fencing athletics track 31 Dec 2012 | N/A |  | N/A | Dept. sports and Recreation -MIG Funding | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | 4316411201 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 09 | Basic Service Delivery | Community facilities | Winston Churchill theatre | All | Currently under construction | Develop and Implement annual operational Plan for Winston Churchill theatre | draft agreement approved 31 Dec 2012 | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | Approved Winston Churchill Operation Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 10 | Basic Service Delivery | Cemetries and Crematoria | Cremators | All | Three cremators (1 functional and 2 non-functional) | Purchase of two new cremators | Purchase of two new cremators by 30/12/2012 | N/A | 2 800 000 | N/A | Council | N/A | IS/RSW21 | NOT APPLICABLE | N/A | N/A | IS/RSW21
[8 empty] | N/A |  | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 11 | Basic Service Delivery | Cemetries and Crematoria | Fencing of Cemeteries Plan | All | Mountain Rise, Azalea, Snathing and Community Cemeteries not fenced. | Develop business plan for the fencing of Cemeteries (as per the requirements of the Act) | Completed business Plan | N/A | N/A | N/A | Nil Required | Identify savings during mid year review and implement fencing | Report submitted 15/01/2013 withdrawn for further invetigation | 2 | Still waiting for City Planner for measurements | Proper survey to measure the perimeter | Report dated 15/01/2013
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PKS 12 | Basic Service Delivery | Cemetries and Crematoria | Cemeteries & Crematoria Sector Plan | All | Nil | cemetries and sector plan submitted to SMC by 28 Feb 2013 | Completed sector Plan | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | Sector Plan
PKS 14 | Basic Service Delivery | Community facilities | Harry Gwala sustainability Plan | All | Harry Gwala is not self sustainable | develop a sound sustainable Business plan for Harry Gwala . | Developed sustainable business Plan | N/A | N/A | N/A | Nil Required | Final business Plan completed and submitted for approval and implementation | Nil | 1 | change of scope | Master Plan for Harry Gwala Phase 2 Cataliytic | Report dated 05/06/2012 submitted to SMC
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
WMS 01 | Infrastructure & Basic Service Delivery | Cleansing | Domestic refuse collection | 10-37 | 83 994 houses weekly refuse collection | 94 073 houses collection 1x week | Number of households with weekly refuse collection | 230004 | N/A | 43 268 858 | Council | 94 073 households with weekly refuse collection | 83994+600 Jika joe informal settlement | 2 | awaiting Resolution on the alternative measures | Implementation of SMME's - community based maintenance | Report with DMM:CS Acting.
[8 empty] | 182… | N/A | 1824698439 |  | 50571 | N/A | N/A | N/A | N/A | N/A
WMS 02 | Infrastructure & Basic Service Delivery |  | Business refuse collection | 10-37 | 5 757 busineses weekly refuse collection | 5 757 businesses weekly refuse collection | Number of business with weekly refuse collection | 30000 | N/A | 20 778 254 | Council | 5 757 of business with weekly refuse collection | 5757 | 3 | N/A | N/A | monthly revenue report
[8 empty] | 183… | N/A | 1834698046 |  | 7500 | N/A | N/A | N/A | N/A | N/A
WMS 03 | Infrastructure & Basic Service Delivery |  | Street sweeping | 10-37 | 300 kms swept per quarter | 300 kms of street swept per quarter | kms of street swept per quarter | 178952 | N/A | N/A | Council | 300 kms of street swept per quarter | 300kms | 3 | N/A | N/A | foreman's report
[8 empty] | 181.... | N/A | N/A |  | 44738 | N/A | N/A | N/A | N/A | N/A
WMS 04 | Infrastructure & Basic Service Delivery | Integrated Waste Management | Garden refuse | 10-37 | 8 garden sites serviced daily | 8 garden sites serviced daily | Number | 30000 | N/A | N/A | Council | 8 garden sites serviced daily | 5 Garden sites serviced | 2 | lack containers and only 1 off 4 rigid arm vehicles | containers repaired. Availability increasing. Vehicle availability still poor. | vehicle availability lists
[8 empty] | 184... | N/A | N/A |  | 7500 | N/A | N/A | N/A | N/A | N/A
WMS 05 | Infrastructure & Basic Service Delivery |  | Plan for Garden refuse sites income | All | Nil income | Revenue Plan for garden refuse sites adopted by December 2012. | Date of adoption of business plan Dec 2012. | N/A | N/A | N/A | Nil | Communication of plan to public stakeholders | Draft Plan | 2 | Plan is being prapared | N/A | Draft Plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
WMS 06 | Infrastructure & Basic Service Delivery |  | Illegal dumping | All | Unknown | Illegal dumping measured and reduced by 10% | * extent of illegal dumping; * reduced % in illegal dumping | 12496 | N/A | N/A | Council | 3% reduction in illegal dumping | 1% reduction in illegal dumping | 1 | fleet unable to supply f.e.l. Only 1 available and reliable | Fleet to supply vehicles. | vehicle time sheets.
[8 empty] | 187 | N/A | N/A |  | 3124 | N/A | N/A | N/A | N/A | N/A
WMS 07 | Infrastructure & Basic Service Delivery |  | Education and awareness | All | Unknown | 104 education and awareness initiatives conducted (2 per week) | Number of initiatives conducted | 208 000 | N/A | N/A | Keep Pietermaritzburg Clean Association | 26 education and awareness initiatives conducted (2 per week) | 24 education and awareness initiatives conducted (2 per week) | 2 | Education and awareness initiatives ere not conducted | 2 Education and awareness programmes to be conducted | KPCA Report
[9 empty] | N/A | N/A |  | 52 000 | N/A | N/A | N/A | N/A | N/A
WMS 09 | Infrastructure & Basic Service Delivery |  | Integrated Waste Management Plan (IWMP) | All | District IWMP | IWMP Adopted by 30/3/13 | Date of adopted IWMP | N/A | N/A | N/A | Nil | Adopted IWMP by 30/3/13 | first draft prepared | 3 | N/A | N/A | first draft
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
WMS 10 | Infrastructure & Basic Service Delivery | Cleansing | Public Conveniences/Toilets | 27,32,33 | 29 conveniences | 29 conveniences operated daily | number of conveniences | 50004 | N/A | N/A |  | 29 conveniences operated daily | 29 serviced | 3 | N/A | N/A | Convenience schedule
[8 empty] | 181.... | N/A | N/A |  | 12501 | N/A | N/A | N/A | N/A | N/A

## PS DM overview
PUBLIC SAFETY & DISASTER MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | PUBLIC SAFETY & DISASTER MANAGEMENT UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 13
| 1.1.1 | OPERATING PROJECTS | 13
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Public Safety Enf & Dis Mng
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
3.4 PUBLIC SAFETY ENFORCEMENT & DISASTER MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
FDMS 01 | Basic Service Delivery | Fire Services | Northdale Fire Station Business plan developed for Northdale Fire Station | 28,29,30,31,32,34,35 | No Fire Station in Northdale. | Northdale Fire Station Business Plan submitted to Manco by 30/10/12 | Date of completed Business Plan | N/A | N/A | N/A | Nil Required | N/A | Project has been included on the business units strategic planning with a view to combine Traffic /Fire Stations in Northdale | 4 | N/A` | N/A` | Strat Plan Resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 02 | Basic Service Delivery |  | Fire Training Facility Business plan developed for Fire Training facility. | Nil | Current training facility not to the Nat. Standard | Fire Training Facility Business Plan submitted to Manco by 30/11/12 | Date of completed Business Plan | N/A | N/A | N/A | Nil Required | N/A | Premises for the facility has been identified and it will in cooperate the Traffic Training and Disaster | 3 | N/A` | N/A` | Resolution of Strat Plan
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 03 | Basic Service Delivery |  | Business Premises inspected as per Fire Bylaws and regulations. | All | 800 Businesses Premises inspected as per Fire Bylaws and regulations. | 800 Businesses Premises inspected as Fire Bylaws and regulations by 30/ 04/13 | Number of inspected Premises as per Fire Bylaws and Regulations | N/A | N/A | N/A | Nil Required | 200 Businesses Premises inspected as per Fire Bylaws and regulations. | 200 Businesses Premises inspected as per Fire Bylaws and regulations. | 3 | N/A | N/A | Schedule of Inspection
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 04 | Basic Service Delivery | Fire Services | Major hazardous installation meetings | All | 36 Major hazardous installation meetings per annum | 36 Major hazardous installation meetings by 30/06/13 | Major hazardous installation meetings | N/A | N/A | N/A | Nil Required | 6 Major hazardous installation meetings per quarter | 6 Major hazardous installation meetings per quarter | 3 | N/A` | N/A | Agenda of Meetings & resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 05 | Basic Service Delivery |  | Fire awareness sessions conducted to public | All | 80 public fire awareness sessions conducted per annum | 80 public fire awareness sessions conducted by 03/06/13 | Number of public fire awareness sessions conducted. | N/A | N/A | N/A | Nil Required | 20 public fire awareness sessions conducted | 20 public fire awareness sessions conducted | 3 | N/A` | N/A | daily stats
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 06 | Basic Service Delivery | Disaster Management | Reviewed Disaster Risk Management Plan | All | non- compliance with Disaster Management Act | Disaster Risk Management Plan reviewed by 30/06/13 | Date of approved Disaster Risk Management Plan | N/A | N/A | N/A | Nil Required | PDMC Meeting 8 Feb to make Request to assign person to assist with risk identification/analysis | At the PDMC Forum dated 8 feb 2013, the forum announced that they commencing the process of recruiting the officials at level of Deputy Managers to assist District municipalities to development, review DM plans (Risk analysis) and they will be deployed at the district level. A request was made to the UMDM for to have that person as soon as the process starts. | 2 | N/A` | It is requested that during the MM Forum meeting our MM to shadow the matter of assigning Deputy managers that will assist with developing and reviewing DM plan (Risk Analysis). | Agenda of the PDMC forum or attendance register
[8 empty] | N/A | N/A | N/A |  | N/A |  | .
FDMS 07 | Basic Service Delivery |  | Workshops of Disaster Risk Management Plan | All | Nil | 37 wards workshops conducted in all wards by 30/06/13 | Number of wards workshops conducted | N/A | N/A | N/A | Nil Required | 7 Wards workshops conducted | Wards were divided into two first 4 workshops were conducted on the 14/02/2013 and the last 3 to make 7 was conducted on the 20/03/2013 | 3 | N/A` | N/A | Attendance registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
FDMS 08 | Basic Service Delivery |  | Disaster Management Advisory Planning Committee | All | Nil | Disaster Management Advisory Planning Committee established by 30/03/2013 | Date Disaster Management Advisory Planning Committee established | N/A | N/A | N/A | Nil Required | DMAPC Meeting held on 27/02/2013 as it will be in quaterly bases. | DMAPC meeting held as its 1 per Q | 3 | N/A` | N/A | Attendance register
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
TMS 01 | Basic Service Delivery |  | Traffic Sector Policing Business Plan developed | All | no Traffic Sector Policing Business Plan. | Traffic Sector Policing Business Plan submitted to SMC by 30 06/13 | Date of completed Traffic Sector Policing Business Plan. | N/A | N/A | N/A | Nil Required | Final Traffic Sector Policing Business Plan submitted to SMC By 30/06/2013 | Currently benchmarking with Metropoliatain Police Departments on the roll-out plan awaiting dates from Durban Metro | 3 | N/A` | The Office of the MM Msunduzi Municipality to lobby the Office of the MM eThekwini Municipality | Awaiting confirmation from Durban Metro
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
TMS 02 | Basic Service Delivery |  | Business Plan developed for Vulindlela Traffic Station. | All | 1 Traffic Station Central | Completed Vulindlela Traffic Station Business Plan submitted to MANCO BY 30/10/12 | Date of completed Vulindlela Traffic Station Business Plan | N/A | N/A | N/A | Nil Required | N/A | Project has been included on the business units strategic planning with a view to combine Traffic /Fire Stations in Vulindlela and | 4 | N/A` | N/A` | Strat Plan resolution
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
TMS 03 | Basic Service Delivery |  | Compliance Fire Arms Controls Act | N/A | 50% Compliance | 60 Officers trained on fire arms by 30/06/2013 | Date and number of officers trained on fire arms. | N/A | N/A | N/A | Council | 25 officers trained on fire arms | 25 officers trained on fire arms | 1 | The Metropolitan Police has stopped the training as a result of Security Officers being trained on Fire-Arm without PSIRA & Fingerprint clearance | Skills Development Unit is facilitating the process of PSIRA accreditation including fingerprints clearance | PSRIA forms & email from Durban Metropolitan Police Academy
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
TMS 04 | Basic Service Delivery |  | Compliance Fire Arms Controls Act | n/a | non compliance with Fire Arm Control Act | Fire Arm Audit ConduCted by 31/10/12 | date fire arm audit completed | N/A | N/A | N/A | N/A | Fire Arm Audit Completed by 31/10/12 | Firearm Audit Completed | 3 | N/A` | N/A | N/A
TMS 05 | Basic Service Delivery |  | Road Safety awareness conducted at schools | all | 80 schools sessions conducted per annum | 120 school sessions per annum | number of school sessions conducted. | N/A | N/A | N/A | N/A | 30 school safety awareness sessions conducted. | 18 school safety awareness sessions conducted. | 2 | Suspension of Traffic Officers | Awaiting finalization of disciplinary hearing | Suspension Letters

## INFRA COVER
ANNEXURE 1(H): INFRASTRUCTURE SERVICES BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## INFRA overview
INFRASTRUCTURE SERVICES BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | INFRASTRUCTURE SERVICES BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 73
| 1.1.1 | OPERATING PROJECTS | 10
| 1.1.2 | CAPITAL PROJECTS | 63
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## WATER overview
WATER & SANITATION UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | WATER & SANITATION UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 14
| 1.1.1 | OPERATING PROJECTS | 0
| 1.1.2 | CAPITAL PROJECTS | 14
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Water & Sanitation
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.1 WATER & SANITATION
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
W&S 01 | Basic Service Delivery and Infrastructure Development | Sanitation | Rehabilitation :Sanitation Infrastructure | 15, 19, 16, 30, 35, 32, 33, 26, 25, 29, 31 | 50 km of sewer pipe to be upgraded and 6 Pump Stations upgraded | Replace 2 km of Sewer pipe and upgrade 1 Pump Station by the 30 June 2013 | km of sewer pipe replaced, no of pump stations upgraded | N/A | 7 500 000 | N/A | MIG | Constructed 0.5 km of sewer pipe, 1 pump Station upgraded | 1 Pump Station upgraded in 1st Quarter. Tenders for a further 6 pump station upgrades in currently prepared. 256 meters of sewer pipe was upgraded | 2 | Digital information in relation CCTV information was outstanding, hence priority replacements could not be indentified. | Information now received and 7 day tender processes are to advertised and implemented in 4th quarter. | Capital Projects Progress Worksheets from Operations Technologist. Consultants correpondence.
.
.
[8 empty] | N/A | 2026051303 | N/A |  | 2500000 | 264402 | N/A | N/A | N/A | N/A
W&S 02 | Basic Service Delivery and Infrastructure Development |  | Shenstone Ambleton Sanitation System | 18, 13 | 0 | 3.1km of Sewer pipe installed by the 30 June 2013 | Km of pipe installed | N/A | 8 692 765 | N/A | MIG | Constructed 0.5 km of outfall sewer. | Contract Awarded on 11 Jan 2013. Construction delayed due to Community disputes. Constructed 0,0km of sewer pipe. Site Established, materials ordered and delivered on site. Setting of pipeline and route. Commencement of Pipe Jacking contract. | 1 | Community issues regarding the employmment of labour and CLO resulted in a 3 week delay. Informal grave sites where encounted on site. | Meeting held with community to resolve. Resources to be increased to meet target and material have been ordered. Pipe jack under road has started | Payment BoQ. Email regarding community meeting
[8 empty] | N/A | 2026051302 | N/A |  | 2100000 | 2124049 | N/A | N/A | N/A | N/A
W&S 03 | Basic Service Delivery and Infrastructure Development |  | Sewer Pipes unit H-Ward 16 | 16 | N/A | Completed Design and Tender Document for Unit H Sanitation System by 30 June 2013 | Date | N/A | 900 000 | N/A | MIG | Completed Draft Design | Completed Draft Design; Draft Design Report submitted 2013-03-15 | 3 | N/A | N/A | draft design report and payment certificate
[8 empty] | N/A | 2026051304 | N/A |  | 400000 | 403000 | N/A | N/A | N/A | N/A
W&S 04 | Basic Service Delivery and Infrastructure Development |  | Sewer Pipes Azalea - Phase 2 | 10 | N/A | Completed Draft Design and Tender Document for Azalea : Phase 2 Sanitation System by 30 June 2013 | Date | N/A | 900 000 | N/A |  | Completed Draft Design | Completed Draft Design; Draft Design Report submitted 2013-03-15 | 3 | N/A | N/A | draft design report and payment certificate
[8 empty] | N/A | 2026051305 | N/A |  | 400000 | 575645 | N/A | N/A | N/A | N/A
W&S 05 | Basic Service Delivery and Infrastructure Development |  | Infrastructure Feasibility | 15, 19, 16, 30, 35, 32, 33, 26, 25, 29, 31 | High levels of Storm Water Infiltration | Completed Infiltration assessment report by 30 June 2013 | Date of completion | N/A | 750 000 | N/A | MIG | Draft Infiltration Report | Draft Infiltration Assessment and Reduction Strategy Report completed dated 20 March 2013 | 3 | N/A | N/A | Draft Infiltration Assessment and Reduction Strategy Report dated 20 March 2013 and INV No. 30644
[8 empty] | N/A | 2026051301 | N/A |  | 250000 | 0 | N/A | N/A | N/A | N/A
W&S 06 | Basic Service Delivery and Infrastructure Development |  | Elimination of Conservancy Tanks-Sewer | 20.21 | N/A | 2.3km of sewer pipe installed by the 30 June 2013 | km of sewer installed | N/A | 6 483 000 | N/A | MIG | 1.0km of sewer installed | 310m of sewer installed. Site established and materials ordered and delivered on site. This target is as of the 20th March 2013. | 1 | Excessive groundwater encountered during construction which slowed progress | Instruction given to construct stone bedding for drainage. It is envisaged that approximately 0.5km would be completed by the 31 March 2013. Remainder of Target to fall part of 4th Quarter. | Payment certificate and BoQ.
[8 empty] | N/A | 2026081301 | N/A |  | 2183000 | 42338 | N/A | N/A | N/A | N/A
W&S 07 | Basic Service Delivery and Infrastructure Development |  | Service Midblock Eradication | 23 | N/A | 1.5km of sewer pipe installed by the 30 June 2013 | km of Sewer Pipe constructed | N/A | 3 300 000 | N/A | MIG | 0.5km of Sewer Pipe constructed | Site estabishment and purchase and delivery of materials. Exploritory work and exposing of existing services has been done | 1 | There had been wage disputes between the Principal Contractor and the Local Labourers. Hence there was a one week delay. | Contractor has updated programme of works commiting to more focus on pipeline construction and to increase the labour force, hence improving day task productivity. A total 2km sewer pipe to be constructed in the 4th quarter | Payment certificate and BoQ. Technical minutes.
[8 empty] | N/A | 2026081302 | N/A |  | 1470000 | 953120 | N/A | N/A | N/A | N/A
W&S 08 | Basic Service Delivery and Infrastructure Development | Water | Basic Water Supply | 1 to 11, 14 | 0.5km | Install 0.5km of water pipe by the 30 June 2013. | km of Water Pipe installed | N/A | 2 000 000 | N/A | MIG | 0.2km of Water Pipe installed | 284 meters of water pipe installed including 2 Jojo tanks. | 3 | N/A | N/A | Progress Monitoring Spreadsheet, Email from Umgeni Water.
[8 empty] | N/A | 7876051304 | N/A |  | 750000 | 365891 | N/A | N/A | N/A | N/A
W&S 09 | Basic Service Delivery and Infrastructure Development |  | Masons Reservoir & Pipeline | 26 | N/A | Completed Final Design and Tender Documentation for Masons reservoir and Pipeline by 30 June 2013 | Date | N/A | 800 000 | N/A | MIG | Completed Prelim Design Phase | Completion of : - Preliminary design (Res & Pipelines) | 3 | N/A | N/A | Prelim drawings Submitted with correspondence.
[8 empty] | N/A | 7876061301 | N/A |  | 635000 | 117000 | N/A | N/A | N/A | N/A
W&S 10 | Basic Service Delivery and Infrastructure Development |  | Copesville Reservoir | 29 | 0 | Cast 100% Floor, Cast 50% Reservoir Walls, Started Roof reinforcing. | % Complete | N/A | 21 219 450 | N/A | MIG | Casted 70% floor Slab, Cast reservoir walls 60% | Floor panels cast 86%, reservoir wall cast 64% | 3 | N/A | N/A | minutes of progress meeting dated 12 March 2013.
[8 empty] | N/A | 7876061205 | N/A |  | 5200000 | 8234687 | N/A | N/A | N/A | N/A
W&S 11 | Basic Service Delivery and Infrastructure Development |  | Reduction - Non Revenue Water | ALL | Non -Revenue Water for the 2010/11 financial year is 46.7% | Non-Revenue Water reduced by 4% from 54.10% in order to achieve 50.1% by 30 June 2013 | % reduction of Non-Revenue Water | N/A | 15 000 000 | N/A | MIG | Reduced Non Revenue Water by 3% from 50.1% | Reduced Non Revenue Water to 45.2% (February 2013) | 3 | N/A | N/A | IWA Balance Spreadsheet dated 18 March 2013.
[8 empty] | N/A | 7876051301 | N/A |  | 4500000 | 5725292 | N/A | N/A | N/A | N/A
W&S 12 | Basic Service Delivery and Infrastructure Development |  | Elimination of Conservancy Tanks-Water | 20,21 | N/A | Install 0.1km of water pipe by the 30 June 2013. | km of Water Pipe installed | N/A | 250 000 | N/A | MIG | Install 0.05km of water pipe. | No water pipe has been installed yet. | Not Applicable | This amount was initially budgeted for in the event of water pipes been damaged during construction, however Design and Planning of the new water pipeline extentions is currently been completed. | Complete design and planning for water pipeline extention to be constructed in 4th quarter. | Email Correpondence to consultant
[8 empty] | N/A | 7876051302 | N/A |  | 100000 | 0 | N/A | N/A | N/A | N/A
W&S 13 | Basic Service Delivery and Infrastructure Development |  | Service Midblock Eradication | 23 | N/A | 0.06 km of water pipe installed by the 30 June 2013. | km of water Pipe constructed | N/A | 200 000 | N/A | MIG | 0.01km of water pipe constructed | No water pipe has been installed. | Not Applicable | This amount was initially budgeted for in the event of water pipes been damaged during construction, however Design and Planning of the new water pipeline extentions is currently been completed. | Complete design and planning for water pipeline extention to be constructed in 4th quarter. | Email Correpondence to consultant
[8 empty] | N/A | 7876051303 | N/A |  | 40000 | 0 | N/A | N/A | N/A | N/A
W&S 14 | Basic Service Delivery and Infrastructure Development |  | Edendale Proper | 20, 11, 12 | 3.9km | Appoint Contractor, completed 1.2km of Water Pipe by the 30 June 2013. | km of water Pipe | N/A | 1 200 000 | N/A | MIG | Start Exploratory Excavations, Completed 0.2km Water Piping | 0.3km of piping installed | 4 | N/A | N/A | Payment certificates with BoQ.
[8 empty] | N/A | 7876051202 | N/A |  | 370000 | 108747 | 386482 | N/A | N/A | N/A

## ELEC overview
ELECTRICITY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | ELECTRICITY UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 11
| 1.1.1 | OPERATING PROJECTS | 1
| 1.1.2 | CAPITAL PROJECTS | 10
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS
| 2.1 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Electricty
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.2 ELECTRICITY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
EL 03 | Basic service delivery |  | Electrification | 30 | istalled 200 connections | Ezinketheni (Copesville)-200 connections installed | Number of connections installed | N/A | 5 million | N/A | DOE | 100 electricity connections installed | 129 Poles installed | 2 | Project started late | Site inspection | Consultant documents
[8 empty] | N/A | 7136091301 | N/A |  | 1 000 000 | N/A | N/A | N/A | N/A | N/A
EL 04 | Basic service delivery |  | High mast lights | 1-13; 15-18 | N/A | 20 high mast lights installed | Number of high mast lights installed | N/A | 4 082 960 | N/A | Capex MIG. Opex Council | 10 high mast lights installed | 30 Highmast orderd | 2 | Portifolio put project on hold | In progress | Consultant documents
[8 empty] | N/A | 7136181301 | N/A |  | 2 000 000 | N/A | N/A | N/A | N/A | N/A
EL 05 | Basic service delivery | Electricity Maintenance | Mini sub-stations | All | Replacement of 10 Mini substations | Replacement of 10 mini substations | Number of mini substations replaced | N/A | 4 000 000 | N/A |  | 3 mini substations replaced | 1 mini substations replaced | 2 | Awaiting delivery | N/A | Requisition books
[8 empty] | N/A | 7136541302 | N/A |  | 2 000 000 | N/A | N/A | N/A | N/A | N/A
EL 06 | Basic service delivery |  | Pole mounted transformers | 1 & 2 | Replacement of 12 pole mounted transformers | Replacement of 12 pole mounted transformers | Number of pole mounted transformers replaced | N/A | 2 000 000 | N/A |  | 3 pole mounted transformers replaced | 1pole mounted transformers replaced | 2 | No cross arms available | Ordered cross arms | Requisition books
[8 empty] | N/A | 7136541302 | N/A |  | 1 000 000 | N/A | N/A | N/A | N/A | N/A
EL 07 | Basic service delivery |  | Switchgear | All | Replacement of 40 switch gear & accessorie | Replacement of 40 switch gear & accessories | Number of switch gear replaced | N/A | 12 500 000 | N/A |  | 20 replaced | 19 switchgear replaced | 2 | Based on demand on site | N/A | TSM & CER books
[8 empty] | N/A | 7136541302 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EL 08 | Basic service delivery |  | Ground Mounted Transformers & ring main units | All | Replacement of 6 transformers & 10 ring main units | Replacement of 6 transformers & 10 ring main units | Number of transformers & ring main units replaced | N/A | 2 000 000 | N/A | Council | replaced 3 transformers and 5 ring main units | replaced 1 transformers and 1 ring main units | 2 | Awaiting delivery | Ordered more | Requisition books
[8 empty] | N/A | 7136541302 | N/A |  | 1 000 000 | N/A | N/A | N/A | N/A | N/A
EL 09 | Basic service delivery |  | Streetlights | All | Obsolete | Replacement of 900 streetlights | Number of street lights replaced | N/A | N/A | N/A | DoE | 250 street lights replaced | 1543 street lights replaced | 5 | N/A | N/A | Requisition books
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EL 10 | Basic service delivery | Electricity Upgrade | Hilton Overhead Line | 1 & 2; Hilton | Design completed | Construct 33kV overhead line to Hilton | Completed construction of line | N/A | 13 500 00 | N/A | Council | Line Completion | 70% completion (poles installed, earthwire installed, half of phase wires installed) | 3 | Contractor abandoned site due to late payments | Paid | Consultant documents and site visits
[8 empty] | N/A | 7135211301 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EL 11 | Basic service delivery | Protection Rectification | Protection testing & Maintenance | All | Assessment of sub-stations complete | Protection study, testing, maintenance and updating- 132/11kV | Completion of protection setting and grading | N/A | 2 500 000 | N/A | Council | N/A | All primary substations completed | 3 | N/A | N/A | Consultant documents
[8 empty] | N/A | 7136541303 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EL 12 | Basic service delivery |  | Electricity Maintenance Plan | All | N/A | Adopt maintenance plan by 30/06/2013 | Date of adopted maintenance plan | N/A | N/A | N/A | Nil | Draft Plan submitted to MANCO | Plan adopted by EXCO | 4 | N/A | N/A | Drafted plan
[7 empty] | Date | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
EL 13 | Basic service delivery | Electricity Maintenance | Electricity upgrade & protection | All | obsolete equipment | replacement of obselete equipment | number of equipment replaced | N/A | 34 492 442 | N/A | Council | installation of equipment | 19 switchgear replaced | 3 | N/A | N/A | Requisition books
[8 empty] | N/A | 7136541301 | N/A |  | 14 492 442 | N/A | N/A | N/A | N/A | N/A

## PMU overview
PROJECT MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | PROJECT MANAGEMENT & FLEET UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 4
| 1.1.1 | OPERATING PROJECTS | 4
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## PMU
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.3 PROJECT MANAGEMENT UNIT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
PMU 01 | Basic Service Delivery | Project Management support | Monthly programme/ project monitoring reports for MIG/OGF/CNL Budget | All | Reports compiled & submitted by 5th of every month. Ensure 100% of budget is spent. | Reports compiled & submitted by 5th of every month. Ensure 100% of budget is spent. | Date of report compiled monthly | N/A | N/A | N/A | Nil Required | 3 X monthly reports submitted by the 5th of every month to OMC/OGF/CNL | Reports for Jan, Feb and March 2013 have been submitted for noting. | 3 | N/A | N/A | Monthly report on infrastructure capital projects, expenditure, progress plan.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PMU 02 | Basic Service Delivery | Project Management support | Weekly programme/project monitoring reports for MIG/OGF/CNL Budget | All | Minutes/ reports compiled every second Wednesday. Ensure 100% of budget is spent. | Minutes/ reports compiled every second Wednesday. Ensure 100% of budget is spent. | Weekly reports compiled | N/A | N/A | N/A | Nil Required | 6 X weekly reports sent out every second Wednesday to PM's | A total of five meetings (Jan One meeting - Feb Two meetings - Mar Two meetings) have been held in quarter 3. | 2 | First meeting of January not held as a result of holiday period and construction industry shutdown. | Better planning required during the month of January to cater for the holiday period and construction industry shut down. | Minutes of PM's Project Progress meetings.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PMU 04 | Basic Service Delivery | Project Management Support | Administration of payment process and ongoing monitoring | All | All invoices packaged and submitted to client departments within 48 hours | All invoices packaged and submitted to client departments within 48 hours | Turn-around time for submission of invoices | N/A | N/A | N/A | Nil Required | All invoices packaged and submitted to client departments within 48 hours | All invoices packaged and submitted to user departments within 48 hours for the months of Jan, Feb and Mar 2013. | 3 | N/A | N/A | Copy of invoice approval tracking sheets and proof of payments schedule.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PMU 06 | Basic Service Delivery | Project Management Support | Administration Support and reporting to MIG (Provincial) and reporting to OGF/CNL/EPWP | All | Ensure project documentation completion to report expenditure to MIG/Funding Source by the 15th of every Month | Ensure project documentation completion to report expenditure to MIG/ Funding Source by the 15th of every Month | Date of submission of monthly reports | N/A | N/A | N/A | Nil Required | 3 X monthly reports by the 15th of every month | Reports for Jan, Feb and March 2013 have been submitted before 15 th of the month. | 3 | N/A | N/A | Monthly Dora reports for MIG and EPWP.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## Fleet Overview
FLEET MANAGEMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | PROJECT MANAGEMENT & FLEET UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 5
| 1.1.1 | OPERATING PROJECTS | 5
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Fleet
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.4 FLEET MANAGEMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
FLT 01 | Basis Service Delivery | FLEET | Vehicle monitoring system | NA | Service provider contract | Number of vehicles fitted by 31-03-2013 | Number of vehicles and date |  | N/A | N/A | Council | 100% vehicles fitted on the number received. | 45 vehicles fitted in quarter 3 | 2 | Non availability of vehicles | Vehicles to be done over the weekend | monitoring system register
[7 empty] | Number | 160 | N/A | N/A |  | NA | NA | NA | NA | NA | NA
FLT 02 | Basis Service Delivery |  | Vehicle and Plant service plan | NA | Inadequate service plan | Number of vehicles serviced against received. | All the vehicles and plant serviced | 13 000 000 | N/A | N/A | internal | 216 of vehicle and plant serviced | 71 vehicles and plant serviced. | 1 | Non availability of vehicles | Developing a system of speeding up order numbers | job cards
[8 empty] | 215 3200 | N/A | N/A |  | 107 000 | NA | NA | NA | NA | NA
FLT 03 | Basis Service Delivery |  | Fleet Policy | NA | Draft fleet policy in place | Fleet policy adopted by 30/12/2012 | date of adopted fleet policy | N/A | N/A | N/A | Nil Required | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
FLT 04 |  |  |  |  | Nil | All relevant people workshoped by 30-06-2013 | % implementation of fleet policy | N/A | N/A | N/A | Nil Required | 100% Implementation of fleet Policy | Invitations sent to all business units | 2 | Non availability of bigger venue | Workshop on smaller groups through out the month | Workshop attendent register
[8 empty] | N/A | N/A | N/A |  | NA | NA | NA | NA | NA | NA
FLT 05 | Basic Service delivery |  | Accident Review Committee | all | No committee | Establish committee by 31-03 2013 | Date of established accident review committee and monthly meetings | N/A | N/A | N/A | Nil Required | 3 monthly meetings | NA | NOT APPLICABLE | NA | NA | NA
[7 empty] | Number of monthly meetings | N/A | N/A | N/A |  | N/A | NA | NA | NA | NA | NA

## ROADS overview
ROADS & STORMWATER UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | ROADS & STORMWATER UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 31
| 1.1.1 | OPERATING PROJECTS | 0
| 1.1.2 | CAPITAL PROJECTS | 31
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Roads & Stormwater
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.5 ROADS & STORMWATER
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
RSW 01 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Horse Shoe Access Road | 15 & 19 | Gravel horse shoe and passages in need of upgrade to all weather surface access. | Upgrading of 1.2 km Horse Shoe Access Rds in Wards 15 & 19 Imbali by 31 March 2013. | km of road upgraded | N/A | 2200000 | N/A | MIG | Completed preparation of black-base for the balance of the access roads | Preparation is 50% Complete | 2 | 3 weeks delays with Reallocation of MIG funds | The programme will be expedited | Payment Certificate
[8 empty] | N/A | 125 625 1305 | N/A |  | 375 000 | N/A | N/A | N/A | N/A | N/A
RSW 02 | Basic Service Delivery and Infrastructure Development |  | Moscow Roads | 12 | Grav-seal and gravel roads with limited access levels in need of upgrade to all weather access | Upgrading of 1.3 km to Moscow Roads up to base layer and 60% swd completed by 30 June 2013. | km of road upgraded | N/A | 4 000 000 | N/A | MIG | Appointed contractor. Construction commenced. | Contractor appointed. Construction commenced Progress 15% complete. | 3 | N/A | N/A | Consultants 1st Progress report.
[8 empty] | N/A | 125 625 1307 | N/A |  | 1 800 000 | N/A | N/A | N/A | N/A | N/A
RSW 03 | Basic Service Delivery and Infrastructure Development |  | Ashdown Roads | 23 | Grav-seal and gravel roads with limited access levels in need of upgrade to all weather access | Rehabilitation of 1.5 km to Ashdown Roads by 30 June 2013 | km of road rehabilitated | N/A | 2780000 | N/A | MIG | Contractor appointed and preparation of sub-base completed. Construction commenced. | 2nd Contractor appointed. Site handed-over on 20 March 2013 | 2 | Recommended contractor failed to raise Sureties in terms of the tender. A months delay experienced. | 2nd contractor has been appointed to undertake the works | Appointment letter.
[8 empty] | N/A | 125 625 1315 | N/A |  | 1 000 000 | N/A | N/A | N/A | N/A | N/A
RSW 04 | Basic Service Delivery and Infrastructure Development |  | Machibisa/Dambuza Roads | 21 | Grav-seal and gravel roads with limited access levels in need of upgrade to all weather access | Upgraded of 1.3 km Machibisa / Dambuza Roads (i.e.Manana Rd) up to sub-base layer & 40% of SWD by 30 June 2013. | milestone by date | N/A | 4000000 | N/A | MIG | Appointed Contractor and Construction commenced | Contractor appointed and commenced construction on site. | 3 | N/A | N/A | Appointment letter.
[8 empty] | N/A | 125 625 1316 | N/A |  | 1 000 000 | N/A | N/A | N/A | N/A | N/A
RSW 05 | Basic Service Delivery and Infrastructure Development |  | D1128 Road - Ph1 | 5 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgrade of 3.25 km gravel road into all weather access by 30 September 2012. | km of road upgraded | N/A | 3 000 000 | N/A | MIG | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | 125 625 1301 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
| Basic Service Delivery and Infrastructure Development |  | D1128 Road - Ph2 | 5 | Gravel roads with limited access levels in need of upgrade to all weather access | Commenced with the upgrading a culvert structure and 1.0 km gravel road section by 30 June 2013 | km of | N/A | 2000000 | N/A | MIG | Spec approved, tender advertised and awarded by BAC | Specs approved and tender advertised on the 28th March. Report prepared for BAC to reaffirm the appointment of a consultant. | 3 | N/A | N/A | Copy of advert
[8 empty] | N/A | 125 625 1301 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
RSW 06 | Basic Service Delivery and Infrastructure Development |  | Station Road Bridge | 11 | 0 | Design Report and lodge draft EIA report with DAEARD by 31 January 2013 | Date of approved EIA | Nil | 100 000 | N/A | MIG | Final EIA Report submitted to DAERD by 31 March 2013 | Draft EIA Report completed approved. Comments period completed .Submission to be effected by March 2013. | 3 | N/A | N/A | EIA Report
[8 empty] | Nil | 125 625 1313 | N/A |  | 45000 | N/A | N/A | N/A | N/A | N/A
RSW 07 | Basic Service Delivery and Infrastructure Development |  | Haniville Internal Roads | 29 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.2km internal gravel roads in Haniville Township by 31 January 2013. | km of road upgraded | N/A | 1 500 000 | N/A | MIG | Complete upgraded 1.2km internal gravel roads in Haniville Township | 1.2km completed | 3 | N/A | N/A | Completion Certificate
[8 empty] | N/A | 1256251311 | N/A |  | 562 500 | N/A | N/A | N/A | N/A | N/A
RSW 08 | Basic Service Delivery and Infrastructure Development |  | Mbucwana Road | 1 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.3km of Mbucwana Road by 30 June 2013 | km of road upgraded | N/A | 2100000 | N/A | MIG | Completed SWD. Contractor for black base commenced | 50% of swd complete. Contractor appointed | 2 | Poor performance of SWD contractor. Contractor for black base struggled to raise Sureties and Insurances for the works | SWD Contractor has been warned & instructed to fastrack the works. The contractor has since raised sureties and insurances | Appointment letter.
[8 empty] | N/A | 125 625 1309 | N/A |  | 800 000 | N/A | N/A | N/A | N/A | N/A
RSW 09 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Ward 22 Roads | 22 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 2.3km of Gravel Roads in Ward 22 by 30 June 2013 | km of road upgraded | N/A | 4500000 | N/A | MIG | Complete internal preparation of 1.0km sub-base layer works. | 1.0km complete. | 3 | N/A | N/A | Completion Certificate
[8 empty] | N/A | 125 625 1306 | N/A |  | 1 000 000 | N/A | N/A | N/A | N/A | N/A
RSW 10 | Basic Service Delivery and Infrastructure Development |  | Esigodini Roads. Upgrading of gavel road to all weather surface | 12 | 0 | Completed 1st design report for Ntshingila, Shezi Majozi Rds by 31 Dec 2012 and completed 2nd design for Ntombela Mpungose and Nkosi Roads by 31 May 2013. | Completed design report | N/A | 400 000 | N/A | MIG | Completed 1st Design. Approved Spec, Tender advertised and Service Provider appointed for 2nd Design. | 1st Phase Design has been completed. Tender for 2nd phase design was advertised on 28 Feb and closed on 18 March 2013. | 2 | Delay in advertising of 2nd phase design | To fastrack evaluation. | Copy of an Advert for 2nd phase.
[8 empty] | N/A | 125 625 1312 | N/A |  | 175 000 | N/A | N/A | N/A | N/A | N/A
RSW 11 | Basic Service Delivery and Infrastructure Development |  | Ward 16 Roads | 16 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 0.87km of gravel roads in Ward 16 by February 2013 | km of road upgraded | N/A | 1700000 | N/A | MIG | Completed upgraded 0.7km of gravel roads in Ward 16 by December 2012 | 0.87 km completed | 3 | N/A | N/A | Completion Certificate
[8 empty] | N/A | 125 625 1310 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
RSW 12 | Basic Service Delivery and Infrastructure Development |  | KwaNyamazane Roads | 13 | Damaged roads by uncontrolled water in need of investigation and rehabilitation | Completed Investigation of stormwater and design by 30 April 2013 | Completed investigation and design report | N/A | 300000 | N/A | MIG | Completed Investigation of SWD and commence with design. | SW investigation Complete and design commenced | 3 | N/A | N/A | Marc progress report
[8 empty] | N/A | 125 625 1308 | N/A |  | 250 000 | N/A | N/A | N/A | N/A | N/A
RSW 13 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Tafuleni Road | 11 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 2.4km of Tafuleni gravel road sub-base level with 40% of swd completed by 30 June 2013. | km of road upgraded | N/A | 4000000 | N/A | MIG | Appointed contractor. Commenced construction. | Contractor appointed and commenced with construction on site. | 3 | N/A | N/A | Lette of appointment.
[8 empty] | N/A | 125 625 1304 | N/A |  | 1 500 000 | N/A | N/A | N/A | N/A | N/A
RSW 14 | Basic Service Delivery and Infrastructure Development |  | Willowfountain (Main, Khuzwayo and Kwa-Phupha Roads) | 14 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 4.2km of gravel roads in Willowfountain (i.e. Khuzwayo Rd, KwaPhupha Rd and a 80% section of Willowfountain main Rd) by 30 June 2013 | km of road upgraded | N/A | 8500000 | N/A | MIG | 100% completion of swd in Khuzwayo and KwaPhupha. Commenced with construction for remaining 1.2km of gravel roads. | 50% with swd in KwaPhupha and Khuzwayo Rds. Contractor has moved on site for the 1.2km Main Rd | 2 | Delays with Reallocation of MIG funds | To expedite construction on site | Appointment letter.
[8 empty] | N/A | 125 625 1302 | N/A |  | 1 800 000 | N/A | N/A | N/A | N/A | N/A
RSW 15 | Basic Service Delivery and Infrastructure Development |  | Roads in Ward 17 | 17 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 0.85 km by 30 April 2013 | km of road upgraded | N/A | 1 500 000 | N/A | MIG | Completed preparation of 0.29km 2013 | 50% complete with preperation | 2 | Delays with the Supply material. | Service Provider to be paid twice a month | Photos
[8 empty] | N/A | 1256251317 | N/A |  | Nil | N/A | N/A | N/A | N/A | N/A
RSW 16 | Basic Service Delivery and Infrastructure Development |  | Mbanjwa Road | 20 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 1.9km of Mbanjwa Rd in Siyamu to subbase layer and 40% of swd by 30 June 2013 | km of road upgraded | N/A | 4000000 | Nil | MIG | Appointed Contractor and Construction commenced | Contractor appointed and commenced with construction on site. | 3 | N/A | N/A | Lette of appointment.
[8 empty] | N/A | 125 625 1303 | Nil |  | 1000000 | N/A | N/A | N/A | N/A | N/A
RSW 17 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Footpaths in Sobantu | 35 | Unsafe and gravel footpaths in need of upgrade. | Constructed 0.2km footpaths in Sobantu by 31 January 2013 | km of footpath constructed | N/A | 200 000 | Nil | MIG | Completed constructed 0.2km footpaths in Sobantu by 31 January 2013 | Completed | 3 | N/A | N/A | Completion Certificate
[8 empty] | N/A | 125 625 1314 | Nil |  | 150 000 | N/A | N/A | N/A | N/A | N/A
RSW 18 | Basic Service Delivery and Infrastructure Development |  | Upgrading Shembe, Joe Ngidi, Ndwendwe, Mavimbela, Stebhisi Link, Shandu & Ntombela Roads | 12 | Gravel roads with limited access levels in need of upgrade to all weather access | Upgraded 0.5km of swd concrete channels in Ward 12 Roads by December 2012. Upgraded 2.5km of Ward 12 gravel roads to blacktop surfacing with associated SWD by 31 May 2013 | km of road upgraded | N/A | 3818536 | N/A | MIG | Complete internal preparation of sub-base layer works | Commenced with the internal preparation of sub-base | 2 | Delays with Reallocation of MIG funds | This process must be shortened by Finance | Photos
[8 empty] | N/A | 125 625 1318 | N/A |  | 1500000 | N/A | N/A | N/A | N/A | N/A
RSW 19 | Basic Service Delivery and Infrastructure Development |  | N3/Chota Motala Interchange | 32, 33, 35 | Main Road operating at low Level Of Service (LOS) in need of upgrade | Completion of Municipal additional 1.5 km road lanes and associated bridge in Chota Motala Road by 28 February 2013. | Completion date of Chota Motala Rd | N/A | 16 790 000 | Nil | Council | Completed 1.5 km of road works and associated Dorpspruit bridge. | Project complete as per specification | 3 | N/A | N/A | Completion Cetrificate
[8 empty] | N/A |  | Nil |  | 16 790 000 | N/A | N/A | N/A | N/A | N/A
RSW 20 | Community and Social Services | Cemeteries | Hollingwood Cemetery (Multi-year project) | 35 | Open land for development into a new cemetery | Building works completed - Road works completed up to sub-base level - Commenced with the Rehabilitation of waste site by 30 June 2013 | milestone by date | N/A | 9100000 | N/A | MIG | Appointed Service provider. Fencing around cemetery - Building renovation commenced - Access roads commenced | Long objection has not been resolved. | 1 | Objection was received. Attempts to resolved outside the Arbitration failed | Arbitrators decision to re-advetise will be implemented. To re-advertize on 3rd March 2013. | Copy of the decision of the Arbitrator
[8 empty] | N/A | 392 630 1301 | N/A |  | 3000000 | N/A | N/A | N/A | N/A | N/A
RSW 21 | Community and Social Services | Cemeteries | Cremators | 35 | Old and dysfunctional cremators in need of replacement | 2 newly Installated of cremators by 31 May 2013 | Project milestone completion date | Nil | 2 800 000 (additional R2.6m is required for this purpose) | Nil | MIG | Appoint Service Provide and commenced with installation and connections of 2 cremators | Service Provider appointed and commenced with works. | 3 | N/A | N/A | Appintment letter
[8 empty] | Nil | 392 630 1302 | Nil |  | 2 800 000 | N/A | N/A | N/A | N/A | N/A
RSW 22 | Community and Social Services | Public ablutions | Public Ablution Facilities | 27, 32, 23, 35 | Endless problems with existing ablutions in need of upgrading | 12 rehabilitated various public ablution facilities in Wards 23, 27, 32 & 35 by 30 June 2013 | Number of ablutions rehabilitated | N/A | 1 500 000 | Nil | MIG | Commenced with all 12 ablutions | 2 complete. 7 ablutions commenced and are 90% complete. 3 to be advertized | 2 | Delays with advert of the other three | To apply Contract 57 -Artisans contract | Payments certs and Orders
[8 empty] | N/A | 141 632 1301 | Nil |  | 1 500 000 | N/A | N/A | N/A | N/A | N/A
RSW 23 | Community and Social Services | Community Hall | Unit 18 Community Hall - Phase 1 | 15 | Non-existence of hall in Ward 15. New Hall needed. | 100% completed structure for Unit 18 Hall Phase 1 with exception of internal and external finishes by 30 June 2013 | Date of completion of phase 1 of community hall | N/A | 2 500 000 | N/A | MIG | 100% completion foundation and 20% super structure | 100% completion foundation and 40% top structure | 3 | N/A | N/A | Payment Certificate
[8 empty] | N/A | 243 632 1304 | N/A |  | 1 200 000 | N/A | N/A | N/A | N/A | N/A
RSW 24 | Community and Social Services | Sports facility | Caluza Sports facility - Phase 1 | 20 | Non-existence of the sport facility. New facility needed. Construction of portal frames structure and installation of concrete palisade fencing. | 100% completed structure for Caluza Sport Facility Phase 1 with exception of internal and external finishes by 30 June 2013 | Date of completion of phase 1 of Caluza sport facilities | N/A | 5 500 000 | N/A | MIG | 100% completion foundation and 20% super structure | 80% completion foundation and top structure not commenced. | 2 | Delays due to soil conditions | Casting of foundationsto be accelerated. | Payment Certificate
[8 empty] | N/A | 431 632 1301 | N/A |  | 3 000 000 | N/A | N/A | N/A | N/A | N/A
RSW 25 | Local Economic Development | Economic Developments Facilities | Informal Trade Structures | 32 | 18 structures needed to boost the second economy | 18 Installed informal trade structures in CBD by June 2013. | No. of installed informal trade structures by Date | N/A | 500 000 | N/A | MIG | Re-submit for spec approval based on new requirements, advertised and awarded by BAC | Specs developed | 2 | There is no way forward in the project | Reallocation of funds. However SMC did not approve | Minutes of Project Progress meetings
[8 empty] | N/A | 241 630 1301 | N/A |  | 250 000 | N/A | N/A | N/A | N/A | N/A
RSW 26 | Basic Service Delivery and Infrastructure Development | Public Transport Network System - Multi Year Project | IRPTN - DoT (Multi-year project) | 12,21,22,23,27,32, etc. | Uncoordinated public transport in need of upgrade to safe, cost-effective and efficiency | Completed planning and preliminary design report by 30/6/13 | Date of completed design report | N/A | 45000000 | N/A | DOT | 80% Model to be completed by 31 March 2012 | 80% model development completed | 3 | N/A | N/A | March Monthly report
[8 empty] | N/A | 131 631 1301 | N/A |  | 7063259 | N/A | N/A | N/A | N/A | N/A
RSW 27 | Local Economic Development | Economic Developments Facilities | Widening of Thwala Rd to incorporate parking & mini taxi rank and trading facilities. (Multi-year project) | 22 | Congested Road with limited parking for business, no trading facilities for second economy businesses and no facilities for passenges. | Completed Thwala Road design report, specs and services plan by 31 January 2013. 40% construction works completed by June'13 | % of construction works completed | N/A | 6600000 | N/A | DOT | Tender advertised, adjudicated and Contractor appointed by 30 Mar'13. | Tender advertised. | 2 | Delays at BSC due to funding requirements. | The matter was raised with the Head: SCM and resolved. Tender to be advertised on the 3rd March 2013 | Copy of Advert
[8 empty] | N/A | To be advised by Finance | N/A |  | 1500000 | N/A | N/A | N/A | N/A | N/A
RSW 28 | Local Economic Development | Economic Developments Facilities | Widening of New England Road by adding 2.1km of roadway / lanes. (Multi-year project) | 33 | Congested Road during traffic peak-hour period, limiting ease of access into the CBD | Completed widening of 2.1km of additional roadway. | km of completed roadway. | N/A | 8000000 | N/A | COGTA and CNL | Completed reallocation of services, and 90% completion of outstanding earthworks | 70% rellocation of services and 60% completion of outstanding works. | 2 | Delays with relocation of wate main pipe. | Contractor is receiving assistance from Water Section. | Progress site minutes
[8 empty] | N/A | Vote number to be advised by Finance | N/A |  | Nil | N/A | N/A | N/A | N/A | N/A
RSW 29 | Community and Social Services | Sports facility | Construction of 8 lanes Atletics Tracks | 27 | Open soccer field | Completed earthworks and Master Plan drainage by June 2013 | Completed earthworks for 8 lanes Athletic facility | N/A | 2100000 | N/A | DS&R | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | 390 889 0600 | N/A |  | Nil | N/A | N/A | N/A | N/A | N/A
RSW 30 | Local Economic Development | Economic Developments Facilities | Construction of the Tourism Hub Building | 32 | Old bus, taxi terminus and roadway | Completed double story, state of the art tourism facility by 30 June 2013 | 100% completed building | N/A | 6 500 000 | N/A | COGTA and CNL | 100 % completion of the structure with exception of final finishes and fittings. | All defective works completed | 2 | INDO and Sub contractors refused to release already paid for materials by Council | Court interdict obtained to force them to comply | March Progress Report and Interdict
[8 empty] | N/A | 101 200 3005 | N/A |  | 7000000 | N/A | N/A | N/A | N/A | N/A
RSW 31 | Basic Service Delivery and Infrastructure Development | Access to Roads and Stormwater | Upgrading of D2069 Rd | 2 | Gravel roads with limited access levels in need of upgrade to all weather access | Commenced with the upgrade 3.5km of D2069 Rd | Completed subgrade and sub-base | N/A | 2000000 | N/A | DS&R | Approved Spec, advertised, and awarded by BEC. | Advertized on the 28th March 2013 | 2 | Delays in the advert | Shorter advert period | Copy of an Advert for 2nd phase.
[8 empty] | N/A | New | N/A |  | Nil | N/A | N/A | N/A | N/A | N/A

## Landfill Overview
LANDFILL SITE OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | LANDFILL SITE OVERVIEW
| 1.1 | TOTAL PROJECTS: | 8
| 1.1.1 | OPERATING PROJECTS | 0
| 1.1.2 | CAPITAL PROJECTS | 8
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: CAPITAL PROJECTS

## Landfill
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
4.6. LANDFILL SITE
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LFS 01 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed construction of containment berms i.t.o. license requirements. | Completed containment berms by 31/12/12 | N/A | 2 053 000 | 7 500 000 | MIG | N/A | Completed in the previous Quarter | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | 185 100 1680 | 185 469 8556 |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 02 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed construction of access ramps i.t.o. license requirements | Completed access ramps by 31/12/12 | N/A | N/A | N/A | MIG | N/A | Completed in the previous Quarter | NOT APPLICABLE | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 03 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed construction of staff changerooms i.t.o. OHSA requirements | Completed onstruction of staff changerooms by 31/12/12 | N/A | N/A | N/A | MIG | N/A | Completed in the previous Quarter | NOT APPLICABLE | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 04 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed installation of new weighbridge i.t.o. license requirements | Completed weighbridge installation by 31/12/12 | N/A | N/A | N/A | MIG | N/A | Completed in the previous Quarter | NOT APPLICABLE | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 05 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Upgraded leachate pump system i.t.o. license requirements | Completed upgrade of leachate pump system by 31/12/12 | N/A | N/A | N/A | MIG | N/A | Completed in the previous Quarter | NOT APPLICABLE | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 06 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed installation of fence and gates i.t.o. license requirements | Completed installation of fence and gates by 31/12/12 | N/A | N/A | N/A | MIG | N/A | Completed in the previous Quarter | NOT APPLICABLE | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 07 | Basic Service Delivery & Infrastructure Devel. | Increase lifespan of Landfill site | Infrastructure Upgrade | All | Non-compliance with permit | Completed road rehabilitation and creation of firebreak i.t.o. license requirements | Completed road rehabilitation and firebreaks by 31/12/12 | N/A | N/A | N/A | MIG | N/A | Completed in the previous Quarter | NOT APPLICABLE | N/A | N/A | N/A
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LFS 08 | Basic Service Delivery & Infrastructure Devel. | Minimize waste to Landfill | Materials Recovery Facility | All | Non-recycling of waste | Obtian Council authority iro co-operation agreement with District Mun. | MRF construction commenced with | N/A | 20 000 000 (COGTA) 3 000 000 (UDM) 1 000 000 (CNL) | N/A | COGTA/UDM/CNL | Commence with design and engineering layout of MRF | This project is handled entirely by the district Municipality. It has been included on the SDBIP as Council is required to Commit 1 million towards the project. | NOT APPLICABLE | N/A | N/A | N/A
[10 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## CORP SERV COVER
ANNEXURE 1(I): CORPORATE SERVICES BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## CORP SERV overview
CORPORATE SERVICES BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
1 | CORPORATESERVICES BUSINESS UNIT OVERVIEW
1.1 | TOTAL PROJECTS: | 58
1.1.1 | OPERATING PROJECTS | 58
1.1.2 | CAPITAL PROJECTS | 0
1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## SOUND GOV overview
SOUND GOVERNANCE UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | SOUND GOVERNANCE UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 14
| 1.1.1 | OPERATING PROJECTS | 14
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Sound Governance
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.1 SOUND GOVERNANCE
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
SG 01 | Good Governance and Public Participation | Secretariat Services | Agendas | N/A | Council & Portfolios Agenda closed 10 working days prior to meeting | Council & Portfolios Agenda closed 10 working days prior to meeting | Number of Days prior closure of agenda | N/A | N/A | N/A | Council | Council & Portfolios Agenda closed 10 working days prior to meeting | Council & Portfolios Agenda closed 10 working days prior to meeting | 3 | N/A | N/A | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SG 02 | Good Governance and Public Participation |  |  |  | Exco agenda closed 4 working days prior to meeting | Exco agenda closed 4 working days prior to meeting |  | N/A | N/A | N/A |  | Exco agenda closed 4 working days prior to meeting | Exco agenda closed 4 working days prior to meeting | 3 | N/A | N/A | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SG 03 | Good Governance and Public Participation |  | Agendas | N/A | Draft Council and Portfolio agenda to Chairperson 9 working days prior to meeting | Draft Council and Portfolio agenda to Chairperson 9 working days prior to meeting | Number of Days prior closure of agenda | N/A | N/A | N/A | Council | 9 days | 9 days | 3 | N/A | N/A | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SG 04 | Good Governance and Public Participation |  |  |  | Draft Exco agenda not seen by Chairperson prior to meeting | Draft Exco agenda to Chairperson 4 working days prior to meeting | Number of Days prior meeting | N/A | N/A | N/A |  | Weekly appointment with Chairperson 4 working days prior to meeting | Weekly appointment with Chairperson 4 working days prior to meeting | 3 | N/A | N/A | Agenda
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SG 07 | Good Governance and Public Participation |  |  |  | Draft Minutes dispatched 7 days after meeting | Draft Minutes dispatched 7 days after meeting | Number of Days within which minutes are dispatcehd | N/A | N/A | N/A | Council | DraftMinutes dispatched 7 days after meeting | DraftMinutes dispatched 7 days after meeting | 3 | N/A | N/A | Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SG 08 | Good Governance and Public Participation |  |  |  | DraftMinutes posted on L - Drive 7 working days after meeting | DraftMinutes posted on L - Drive 7 working days after meeting | Number of Days within which minutes are posted on the intranet | N/A | N/A | N/A | N/A | DraftMinutes posted on L -Drive 7 working days after meeting | DraftMinutes posted on L -Drive 7 working days after meeting | 3 | N/A | N/A | L-Drvie
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SG 09 | Good Governance and Public Participation |  |  |  | Internal Minutes sent for implementation 8 working days after meeting. | Internal Minutes sent for implementation 8 working days after meeting | Number of Days within which minutes are sent for implementation | N/A | N/A | N/A | Council | Internal Minutes sent for implementation 8 working days after meeting | Internal Minutes sent for implementation 8 working days after meeting | 3 | N/A | N/A | Internal Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
SG 11 | Good Governance and Public Participation |  | Calendars | N/A | Annual, monthly, weekly calendar of meetings | 12 weekly calendar of meetings circulated per quarter | Number of weekly calendars |  | N/A | N/A | Council | 12 weekly calendar of meetings circulated | 12 weekly calendar of meetings circulated | 3 | N/A | N/A | Calendar
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SG 12 | Good Governance and Public Participation |  | Public Participation | All | Secretariat support to public meetings | Secretariat support to public meetings as per demand | meetings attended and Minuted | N/A | N/A | N/A | Council | Secretariat support to public meetings as per demand | Secretariat support to public meetings as per demand | 3 | N/A | N/A | Minutes
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SG 13 | Good Governance and Public Participation | Secretariat Services | Public Participation | All | Minutes finalized 10 working days after the meeting | Minutes finalized 10 working days after the meeting | days |  | N/A | N/A | Council | Minutes finalized 10 working days after the meeting | Minutes finalized 10 working days after the meeting | 3 | N/A | N/A | Minutes
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SG 16 | Good Governance and Public Participation |  |  |  | Outdated ICT infrastructure | 2 New Workstations by 30/12/12 | Number of new workstations by date |  | N/A | N/A | Council | update infrastuscture | N/A | NOT APPLICABLE | N/A | N/A | Correspodence on file
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SG 17 | Good Governance and Public Participation |  | Council/ Internal Mail | N/A | Dysfunctional system | 100% effective, efficient internal mail system: adopted plan by manco by 30 August. | date / % | N/A | N/A | N/A | Council | Internal Mail dispatched within 24 hours of receipt | Internal Mail dispatched within 24 hours of receipt | 3 | N/A | N/A | Mail Register
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SG 18 | Good Governance and Public Participation | Printing Services | Digital Copy Print Production | N/A | Printing completed within 24 hours. | Printing completed within 24 hours of receivng requisition from business units | Number of Hours |  | N/A | N/A | Council | Printing completed within 24 hours of receivng requisition from business units | Printing completed within 24 hours of receivng requisition from business units | 3 | N/A | N/A | Requisition Book
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SG 19 | Good Governance and Public Participation |  | Lithographic print production | N/A | Print Production job completed within 10 working days | Printing completed 10 working days after receivng requisition from business units | Number of Days | N/A | N/A | N/A | Council | Printing completed 10 working days after receivng requisition from business units | Printing completed 10 working days after receivng requisition from business units | 3 | N/A | N/A | Record Book
[12 empty] | N/A | N/A | N/A | N/A | N/A | N/A

## LEGAL overview
LEGAL SERVICES UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | LEGAL SERVICES UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 3
| 1.1.1 | OPERATING PROJECTS | 3
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Legal Services
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.2 LEGAL SERVICES
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LGL 01 | Good Governance and Public Participation | Bylaws | Bylaws Revision | All | Outdated Bylaws | Five specified bylaws submitted to government printers : electricity; cemeteries; environmental health; informal trading; public amenities. | Specified bylaws submittes to government printers | 300 000 | N/A | N/A | Council | One Bylaw submitted to government printers, Namely informal trading bylaws by 30 March 2013 | Drafted Street Trading Bylaws. Report submitted. | 1 | Drafting and discussions with Planning Unit took longer than anticipated . | Bylaws to follow committee system. | Draft Bylaws
[8 empty] | 5021001056 | N/A | N/A |  | 75 000 | N/A | N/A | N/A | N/A | N/A
LGL 02 | Good Governance and Public Participation | Prosecutions | Review of fines | All | Amounts and penalties have to be reviewed in accordance with inflation/monetary value | Fines for all business units have to be reviewed | % of fines reviewed per quarter | N/A | N/A | N/A | N/A | 100% of fines reviewed for Economic Development by 30 March 2013 | Fines submitted to Chief Magistrate | 3 | N/A | N/A | Fines.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LGL 03 | Good Governance and Public Participation | Claims | Risk Guidance | All | Management and staff do not have sufficient knowledge of delictual liability | Key Managers & staff in all Business Units trained on delictual liability | Specified managers & staff from business units trained per quarter | N/A | N/A | N/A | N/A | Key Managers and staff in Economic Development trained on delictual liability | Key Managers and Staff in Economic Development trained. | 3 | N/A | N/A | Powerpoint Presentation Hard copy.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## ICT overview
INFORMATION COMMUNICATION TECHNOLOGY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | INFORMATION COMMUNICATION TECHNOLOGY UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 12
| 1.1.1 | OPERATING PROJECTS | 12
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## ICT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.3 INFORMATION COMMUNICATION TECHNOLOGY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
| Institutional Development and Transformation | ICT | Financial Management System |  | 38 un-integrated systems | Purchase of Financial Management System that will replace PROMIS 30 June 2013 | Date |  | 526 |  | Council | Implementation and training of basic modules and data take on by 31 Dec 2012
15000000
ICT 01 | Institutional Development and Transformation | Adoption of A Governance Framework | ICT Charter | N/A | None | Submission of the Draft ICT Charter by 31 March 2013 to the Operational Management Committee | 2013-03-31 | N/A | N/A | N/A | Nil Required | Submission of ICT Charter to EXCO | ICT Charter submitted to EXCO and approved by Full Council on the 27th Feb | 4 | N/A | N/A | Full Council Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 02 | Institutional Development and Transformation |  | Master Systems Plan | N/A | None | Submission of the Reviewed Master Systems Plan to the Operational Management Committee | 2013-04-30 | N/A | N/A | N/A | Nil Required | ICT Strategy Terms of Reference Developed | ICT Strategy Terms of Reference have been developed and submitted to Council | 3 | N/A | N/A | BSC Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 03 | Institutional Development and Transformation |  | ICT Steering Committee | N/A | A Committee is in place but attendance is erratic | Fully functional ICT Steering Committee Meetings | 1 ICT Steercom Meeting per month | N/A | N/A | N/A | Nil Required | 3 Meetings per quarter | The last ICT Steercom meetings was on the 22 March 2013 and was not fully attended. | 2 | ICT Steercom meetings cannot fully quorate . | Sound Governance to include ICT Steering Committee in the official Calendar meetings | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 04 | Institutional Development and Transformation | Policies and Procedures | Physical Security Policies | N/A | None | Submission of the Draft of 2 Physical Security Policies to the Operational Management Committee | 2012-10-31 | N/A | N/A | N/A | Nil Required | Submission of Draft Phyisical Security Policies to EXCO | Phyisical Security Policies have been submitted to EXCO and approved by Council | 4 | N/A | N/A | Full Council Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 05 | Institutional Development and Transformation |  | Logical Security Policies | N/A | None | Submission of the Draft 11 Logical Security Policies to the Operational Management Committee. | 2012-10-31 | N/A | N/A | N/A | Nil Required | Submission of Logical Security Policies to EXCO | Logical Security Policy have been submitted to EXCO and already approved by Council | 4 | N/A | N/A | Council's Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 06 | Institutional Development and Transformation |  | Minimum Operating Standards | N/A | None | Submission of the Draft 14 Minimum Operating standards for Unix and Windows to Operational Management Committee. | 2012-10-31 | N/A | N/A | N/A | Nil Required | Submission of Minimum Operating Standards to EXCO | Submitted to EXCO and have been already been approved by the Full Council | 4 | N/A | N/A | Full Council Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 07 | Institutional Development and Transformation |  | Environmental Control Policy for Data Centre | N/A | None | Submission of the Draft of 2 Environmental Controls Policies in Data Centre to the Operational Management Committee | 2012-10-31 | N/A | N/A | N/A | Nil Required | Submission of Environmental Control Policies to EXCO | Submitted to EXCO and have been already been approved by the Full Council | 4 | N/A | N/A | Council's Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 08 | Institutional Development and Transformation | Policies and Procedures | Enterprise Architecture | N/A | None | Submission of the Enterprise Architecture to the Operational Management Committee | 2013-04-30 | N/A | N/A | N/A | ICT Budget | Development of the Enterprise Architecture Specifications and Terms of Reference | Terms of Reference and Specifications developed and submitted to BSC | 3 | N/A | N/A | BSC Submission/Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 09 | Institutional Development and Transformation | Policies and Procedures | IT Governace Framework | N/A | None | Submission of the IT Governance Framework to the Operational Management Committee. | 2013-04-30 | N/A | N/A | N/A | ICT Budget | Development of the IT Governance Specifications and Terms of Reference | Terms of Reference and Specifications developed and submitted to BSC | 3 | N/A | N/A | BSC Submission/Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 10 | Institutional Development and Transformation | Policies and Procedures | Replacement and Implementing of IT Server Infrastructure | N/A | Reached end of life | Refreshed IT Server environment | 2013-06-30 | N/A | N/A | N/A | ICT Budget | Develop Terms of References and Specifications | Terms of Reference and Specifications developed and submitted to BSC | 3 | N/A | N/A | BSC Minutes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 11 | Institutional Development and Transformation | Policies and Procedures | Replacement and Implementing of IT Network Switches Infrastructure | N/A | Reached end of life | Refreshed IT Network and Switches environment | 2013-06-30 | N/A | N/A | N/A | ICT Budget | Develop Terms of References and Specifications | 80% of the Terms of References and Specifications have been developed. Technical info is outstanding to complete the Document | 2 | Critical information could not be abtained because of the five (5) main switches and routers failed and stopped working | Emergency Requisition has been approved. This will assist to replace the faulty switches so that we can collect the entire Network information. | Approved Emergency Order and Motivation.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
ICT 12 | Institutional Development and Transformation | Policies and Procedures | Contracts Management | N/A | All exisitng ICT contracts expired | Renewal of all ICT expired contracts | 2013-06-30 | N/A | N/A | N/A | ICT Budget | Develop terms and objectives | The Terms of References for contracts have been developed. Secondly will be advertised and appoint service providers to relevant contracts | 2 | Not all Terms of Reference are finalized. Two of the IT contracts are not complete due to Technical glitches experienced. | Emergency Motivation and Requisition have been approved to address Technical Problems experienced. Once the equipment have been replaced, then Terms of Reference will be finalized. | Approved Emergency Order and Motivation.

## HRM, OH, SD, OD overview
HUMAN RESOURCE MANAGEMENT, OCCUPATIONAL HEALTH, ORGANIZATIONAL DEVELOPMENT & SKILLS DEVELOPMENT UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | HRM, OCCUPATIONAL HEALTH, OD & SD UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 29
| 1.1.1 | OPERATING PROJECTS | 29
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## HRM, OD, SD, OH
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
5.4 HUMAN RESOURCES MANAGEMENT, ORGANIZATIONAL DEVELOPMENT, SKILL DEVELOPMENT & OCCUPATIONAL HEALTH
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
HR 01 | Good Governance and Public Participation | Legislation, Policies and Collective Agreements | Submit policies to SMC 30 June 2013 .Approve Policy Manual, Employment Policy and Employment Procedure Manual, Parking Policy, Transfer Policy, Staff in Political Offices Policy, Acting Policy, Allocation/ Placement policy, EAP Policy, HIV Policy, Incapacity Policy, Dress Code/ Uniform Policy, Memorial Services and Funerals of Employees Policy, Training and Development Policy, Learnership Policy, Internship Policy, AET Policy, Career & Succession Policy | N/A | Draft Policy | Submit outstanding policies to SMC by the end of the 4th Quarter | Date | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
HR 02 | Good Governance and Public Participation |  | Communicate the Policy Manual, Employment Policy and Employment Procedure Manual, Parking Policy, Transfer Policy, Staff in Political Offices Policy, Acting Policy, Allocation/ Placement policy, EAP Policy, HIV Policy, Incapacity Policy, Dress Code/ Uniform Policy, Memorial Services and Funerals of Employees Policy, Training and Development Policy, Learnership Policy, Internship Policy, AET Policy, Career & Succession Policy | N/A | Draft Policy | Communicate All Polices | Date | N/A | N/A | N/A | N/A | Implementation of all approved Policies | Draft Policies | 2 | Policies not yet approved | Approved Policies | Draft Policies
HR 03 | Good Governance and Public Participation |  | Sensitisation of Employees on the Policy Manual, Employment Policy and Employment Procedure Manual, Parking Policy, Transfer Policy, Staff in Political Offices Policy, Acting Policy, Allocation/ Placement policy, EAP Policy, HIV Policy, Incapacity Policy, Dress Code/ Uniform Policy, Memorial Services and Funerals of Employees Policy, Training and Development Policy, Learnership Policy, Internship Policy, AET Policy, Career & Succession Policy | N/A | Nil | Employees Sensitised | Date | N/A | N/A | N/A | N/A | All Employees sensitised on all Policies | Nil Achieved | 1 | Policies not yet approved | Approved Policies | Draft Policies
HR 04 | Good Governance and Public Participation | Human Resources Management | Restructuring of Organisation | N/A | 2008 Re-aligned Structure | Develop and submit organisational structure 30/09/2012 | Date of approval | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
HR 05 |  |  |  | N/A | Job Descriptions for existing Structure Graded but not released | Evaluated JD's for all posts by the end of 4th quarter | Percentage | N/A | N/A | N/A | R160 800 to be funded at Mid-year review | 50% of all JD's to be evaluated by end of 3rd Quarter | Nil Achieved | 1 | Structure not approved | Approve Structure | Draft Structure
HR 06 | Good Governance and Public Participation |  | Staff Service Charter (HR) | N/A | Nil | Develop and submit Service Charter (HR) 30/04/2013 | Date of approval | N/A | N/A | N/A | Nil Required | Submit Service Charter to SMC 30/04/2013 | Service Charter reviewed. | 2 | Submission by Finance | Compile Policy and submit | Reviewed Charter
HR 07 | Good Governance and Public Participation |  | Employee Workshops on Collective agreements | N/A | Nil | Workshops on Collective agreements to all Business Units | Number of workshops | N/A | N/A | N/A | N/A | Workshops on Collective agreements to all Business Units | Workshops on Collective agreements to 4 Business Units | 2 | Poor Attendance. Revisit Units | Manditory Attendance | Workshop Program, presentation
HR 08 | Good Governance and Public Participation |  | Industrial Action Strategy (Strike Management Strategy) | N/A | Nil | Develop and Submit Industrial Action Strategy | Date | N/A | N/A | N/A | Nil Required | 1 x Industrial Action Quarterly Report | No Industial Action | NOT APPLICABLE | N/A | N/A | N/A
HR 09 | Good Governance and Public Participation |  | Develop Staff Retention Policy and Strategy | N/A | No of employees | employees interviewed on exit & quarterly reports and Implementation of Policy and Strategy | exit interviews; quarterly reports and Implementation of Policy and Strategy | N/A | N/A | N/A | N/A | Exit interviews ; identify scarce skills and 1 quarterly report | Exit interviews, scarce skills identified | 2 | Poor Process Planning | Update Process | Exit Interviews
HR 10 | Good Governance and Public Participation |  | Recruitment and selection strategy | N/A | None | Develop and Submit Recruitment and selection strategy 30/04/2013 | Date | N/A | N/A | N/A | N/A | Draft Recruitment and selection strategy 28/2/2013 | Draft Recruitment & Selection policy | 2 | Approval of Policy | Approved Policy | Draft Policy
HR 11 | Good Governance and Public Participation |  |  |  |  | Annual Leave Sick-leave & overtime uploaded to payday 31/12/2012 | % annual sickleave & overtime uploaded to payday | 5261001539 | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
HR 12 | Municipal Transformation & Institutional Development | Skills Development | Implement Workplace Skills Plan | N/A | 30 % of 2011/ 2012 WSP Implemented | 100% implementation of 2012/ 2013 WSP | % implementation of WSP | 2 750 000 | N/A | N/A | Internal and SETA | 25% implementation of WSP | 25% implementation of WSP | 3 | N/A | N/A | Training Registers
[8 empty] | 5301301415 | N/A | N/A |  | 700 000 | N/A | N/A | N/A | N/A | N/A
HR 13 | Municipal Transformation & Institutional Development |  | Develop 2013/ 2014 Workplace Skills Plan | N/A | 2012/ 2013 Work Place Skills Plan | Adopted Workplace Skills Plan | Date of adoption of 2012/ 2013 WSP | N/A | N/A | N/A | SETA | Completed Draft WSP | PDP's prepared for all employees | 2 | N/A | N/A | PDP's
HR 14 | Municipal Transformation & Institutional Development | Skills Development | Provision of Learnership | All | Implementation of learnerships | 30 Learners on Learnership Programme | Number of learners | 600 000 | N/A | N/A | Internal and SETA | Monitoring and Evaluation Completed on the 2 Learnerships | Monitoring and Evaluation Completed on the 2 Learnerships | 3 | N/A | N/A | learnership Report
[8 empty] | 5301301422 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HR 15 | Municipal Transformation & Institutional Development | Skills Development | Provision of Skills Programmes for Community Members | All –1 per Zone | 4 Skills Programme | 4 Community Skills Programmes Implemented | Number of skills programme implemented | 350 000 | N/A | N/A | Internal and SETA | Needs of Communities Identified and 1 Training programme implemented per Zone | Needs of Communities Identified and 1 Training programme implemented per Zone | 3 | N/A | N/A | Reports
[8 empty] | 5301301420 | N/A | N/A |  | 87 500 | N/A | N/A | N/A | N/A | N/A
HR 16 | Municipal Transformation & Institutional Development | Skills Development | Trained Councillor's | All | 20 Trained Councillors | 45 Councillor's Trained | Number of Councillors trained | 680 000 | N/A | N/A |  | 45 Councillors Trained | 20 Councillors Trained | 2 | Problem with Service Provider | Conducting training in-house | Correspondance to University
[8 empty] | 5301301421 | N/A | N/A |  | 175 000 | N/A | N/A | N/A | N/A | N/A
HR 17 | Municipal Transformation & Institutional Development | Skills Development | Appoint Interns | All | 32 Interns | 35 Interns Appointed | Number of interns appointed | 1 000 000 | N/A | N/A | Internal | 35 Interns are monitored and assessments undertaken | 35 Interns are monitored and assessments undertaken | 3 | N/A | N/A | Contracts of Interns
[8 empty] | 5301301413 | N/A | N/A |  | 330 000 | N/A | N/A | N/A | N/A | N/A
HR 18 | Municipal Transformation & Institutional Development | Skills Development | Develop and advertise study assistance for employees | N/A | 49 | 15 Study Assistance Awarded and 49 Bursaries carried over | Number | 500 000 | N/A | N/A | Internal | All Registrations with Educatioanl Institutions Completed. | Submission of recommendation to SMC | 2 | Awaiting SMC Resolutions to be amended | Relook at interal processes, follow up with reports. | Minutes of SMC and Reports
[8 empty] | 5301001050 | N/A | N/A |  | 200 000 | N/A | N/A | N/A | N/A | N/A
HR 19 | Municipal Transformation & Institutional Development |  | Develop and advertise External bursaries | All | 7 External Bursaries Awarded | 10 External Bursaries Awarded | Number of external bursaries awarded | 600 000 | N/A | N/A | Internal | All Registrations with Educatioanl Institutions Completed. | All Registrations with Educatioanl Institutions Completed. | 3 | N/A | N/A | Registration letters
[8 empty] | 5301001055 | N/A | N/A |  | 250 000 | N/A | N/A | N/A | N/A | N/A
HR 20 | Municipal Transformation & Institutional Development | Skills Development | Section 28 Apprenticeships and RPL in Critical and Scarce Skills Areas. | All | 10 Section 28 Apprenticeships | 15 Section 28 Apprenticeships Awarded and RPL conducted | Number of Section 28 Apprenticeships Awarded and RPL conducted | 150 000 | N/A | N/A | Internal and SETA | Section 28 Apprenticeships and RPL implemented | Section 28 Apprenticeships and RPL implemented | 3 | N/A | N/A | Reports to SCM
[8 empty] | 5301001404 | N/A | N/A |  | 50 000 | N/A | N/A | N/A | N/A | N/A
HR 21 | Municipal Transformation & Institutional Development | Occupational Health and Safety | Occupational Health awareness events | N/A | 2 Occupational Health Events 2011/2012 | 2 Occupational Health awareness events | Number of occupational health awareness events | 200 000 | N/A | N/A | Council | Event Planning | Event Planning | 3 | N/A | N/A | Report
[8 empty] | 3461001670 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HR 22 | Municipal Transformation & Institutional Development |  | Risk employee medicals | N/A | Nil | 100% Risk Employee Database | % Risk Employee Database | N/A | N/A | N/A | Nil Required | Maintain Database | Database Maintained | 3 | N/A | N/A | Database
HR 23 |  |  |  |  | 10% | 50% of identified high risk employees medicals conducted | % Risk employees medicals conducted |  | N/A | N/A | Council | 10% of identified high risk Employee medicals conducted | 10% of identified high risk Employee medicals conducted | 3 | N/A | N/A | Medical Statistics
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HR 24 | Municipal Transformation & Institutional Development |  | Risk Assessments of work environments | N/A | Nil | Risk Environment database | % of Database Complete | N/A | N/A | N/A | Nil Required | Maintain Database | Database Maintained | 3 | N/A | N/A | Database
HR 25 |  |  |  |  | 50% | 100% Risk Assessments of Work environments | % | 100 000 | N/A | N/A | Council | 75% Risk Assessments of Work environments | 75% Risk Assessments of Work environments | 2 | Re-active and not Pro-Active Assessment | Routine Inspection and reporting Programme | Assessment Reports
[8 empty] | 3461001670 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HR 26 | Municipal Transformation & Institutional Development | Organisational Development | Conduct climate survey in order to determine baseline | N/A | Climate Survey 2007 | Climate survey Outcomes Report 30/03/2012 | Date of outcomes report | 100 000 | N/A | N/A | Council | Survey Staff - Field work | Outcomes Report Complete. Implementation Plan Development | 4 | N/A | N/A | Outcomes Report. Implementation Plan
[8 empty] | 5301001612 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HR 27 | Municipal Transformation & Institutional Development |  | Process Mapping | N/A | No Written Processes | Approved Process Manuals (4) | Number of approved process manuals | N/A | N/A | N/A | Council | Finance Processes mapped | Std Operating Manual Template Developed | 2 | Poorly Defined Processes | Manual to assist in developing Maps | Draft Std operating Manual
HR 28 | Municipal Transformation & Institutional Development |  | Team Building | N/A | None | Team Building for Senior Managers 28/02/2013 | Date | 100 000 | N/A | N/A | Council | Team Building 28/02/2013 | Procurement Processes | 2 | Awaiting date from MM | Confirmation of dates from MM | Quotations. Procurement forms
[9 empty] | N/A | N/A |  | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
OTS 01 | Good Governance/To ensure participation of all stakeholders in the decision making of the municipality and efficient functioning of ward committees, complying at all times with the provisions of the System Act | Capacity Enhancement | Ward Committee Training | All | N/A | 20 ward committee training sessions | Number of sessions held | 350 000 | N/A | N/A | MSIG | N/A | Procurement Processes | 2 | Awaiting to appoint service provider | Closed Tender via SCM | Reports to SCM
[8 empty] | 201001643 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## ECON DEV COVER
ANNEXURE 1(J): ECONOMIC DEVELOPMENT BUSINESS UNIT
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013

## Econ Dev Overview
ECONOMIC DEVELOPMENT BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | DEVELOPMENT SERVICES BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 38
| 1.1.1 | OPERATING PROJECTS | 38
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## LOCAL Eco DEV Overview
LOCAL ECONOMIC DEVELOPMENT BUSINESS UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | LOCAL ECONOMIC DEVELOPMENT BUSINESS UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 12
| 1.1.1 | OPERATING PROJECTS | 12
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Local Economic Development
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
6.1 LOCAL ECONOMIC DEVELOPMENT
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
LED 01 | Social and Economic Development | Job Creation | Job Creation and income opportunities | All wards | 1000 job opportunities | 1000 job opportunities created by 31 July 2012 | Number of job opportunities created | 2 000 000 | N/A | N/A | Cogta funding | N/A | 250 Jobs created | NOT APPLICABLE | N/A | N/A | CWP Report
[9 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 02 | Social and Economic Development | Municipal wide LED strategy development | Review of LED strategy | N/A | 2008 LED Strategy | Reviewed strategy submitted to SMC by 28 February 2013; implementation of strategy as per action plan | Date of approval and % of implementation of strategy | N/A | N/A | N/A | No funding required | Strategy submitted to SMC by 28 February 2013 | LED Benchmark report and implementation plan presented at ED Portfolio Committee | 2 | To review time frames of milestones | To discuss the issue with the Acting DMM: Economic Development for the wayforward | LED implementation plan report
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 03 | Social and Economic Development | Business retention and expansion | Business retention and expansion (BR&E) survey | All wards | 0 | Completed BR&E programme, and submission of action plan to SMC by 30 June 2013 | Close out report to SMC | nil | N/A | N/A | TIKZN | Volunteers trained and business visitation completed | Nil. | 1 | No clarity yet from MIDI re co-ordinating role. | Meeting being scheduled with MIDI, PCN and TIKZN. | N/A
[9 empty] | N/A | N/A | 20000 | N/A | N/A | N/A | N/A | N/A | N/A
LED 04 | Social and Economic Development |  | Facilitate registration and mentorship of co-operatives | All wards | 0 | Facilitate registration and mentorship of 8 co-operatives by 30 June 2013 | number of co-operatives established | N/A | N/A | N/A | No funding required | 6 co-operatives registered by 31 March 2013 | 4 Cooperatives registered | 3 | CIPC is experiencing backlog of issuing certificates | N/A | Copy of certificates from CIPC
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LED 05 | Social and Economic Development | SMME infrastructure development | Upgrading of 2 satellite markets (Kwa-Shange & Kwa Mncane) | 4 and 8 | 0 | Completed business plan and funding application by 31 December 2012 | Completed business plan; funding application | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LED 06 | Social and Economic Development | Compilation of informal economy database | Compilation and review of informal economy data base | All wards | 0 | completed informal economy data base by 30 June 2013 | Completed informal economy database | N/A | N/A | N/A | No funding required | Survey of all Informal economy actors completed by 31 March 2013 | Completed Informal economy actors: Shoe makers | 3 | N/A | N/A | Questionnaire of informal economy actors dealing in shoes
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LED 07 | Social and Economic Development | SMME Development | Training workshops: Health and safety, basic business, finance | All wards | 6 workshops | 8 training workshops conducted by 30 June 2013 | Number of workshops conducted | N/A | N/A | N/A | No funding required | 6 training workshops conducted by 31 March 2013 | 6 Workshops conducted | 4 | N/A | N/A | Attandance registers
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LED 08 | Social and Economic Development | AirPort Development | Develop an Airport Master Plan | N/A | N/A | Complete airport masterplan and submit to SMC by 31 March 2013 | Completed airport masterplan | 250 000 | N/A | N/A | KZN TREASURY | Reviewed masterplan circulated for stakeholder consultation by 28 February 2013; Final masterplan submitted to SMC by 31 March 2013 | Materplan reviewed by Provincial Crack Team; presentation to Technical Team on 26 March 2013. | 3 | N/A | Presentation to DFC scheduled for 3 April 2013 | Minutes of Technical Committee
[9 empty] | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LED 09 | Social and Economic Development | Municipal Market Operations | Maintain relations with Agents through monthly meetings | N/A | Monthly meetings | 10 monthly meetings to be held by 30 June 2013 | number of monthly meetings | N/A | N/A | N/A | N/A | 8 monthly meetings held by 31 March 2013 | 8 meeting held | 3 | N/A | N/A | minutes of meetings held
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LED 10 | Social and economic development | Job creation and expansion of rates base | Sale of commercial land | All | 2 commercial sites | 2 (commercial) land sales by 30/06/2013 | Number of commercial land sales | 50 000 | N/A | N/A | Council | Bid spec and advert for Polocrosse site31/03/2013 | Bid Spec report and advert reviewed, and confirmed as accurate. Minute sent to SCM to advertize proposal call | 3 | N/A | N/A | Bid Spec report and advert.
[8 empty] | 2401001000 | N/A | N/A |  | 50 000 | N/A | N/A | N/A | N/A | N/A
LED 11 | Social and Economic Development | Job creation and expansion of rates base | Sale of industrial land | All | 4 industrial sites | 4 (industrial) land sales by 30/06/2013 | Number of industrial land sales | N/A | N/A | N/A | Council | Dept. circulation by 31 March 2013 | Circulated application for Portion A of Erf 1935 Mkondeni | 3 | N/A | N/A | Minute to business units.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
LED 12 | Social and Economic Development | Compliance with MPRA | New GV for July 2014 | All | Previous GV in 2008 | 60% of GV completed by 30 June 2013 | Percentage of properties valued | 11200000 | N/A | N/A | Council | Appointment of Gv consultants by 01 March 2013; completion of market reports by 31 March 2013 | Evaluation report for appointment of service provider was submitted to the BEC; Report stood - BEC requested assistance from Cogta; appointment delayed | 2 | BEC stood report down pending assistance from Cogta. | Requested MM to secure assistance from Cogta | Report to the BEC
[8 empty] | 242 100 1575 and 242 100 3090 | N/A | N/A |  | 2 300 000 | N/A | N/A | N/A | N/A | N/A

## Infra Planing overview
INFRASTRUCTURE PLANNING & SURVEY UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | INFRASTRUCTURE PLANNING & SURVEY UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 19
| 1.1.1 | OPERATING PROJECTS | 19
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## Infra Plan & Survey
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
6.2 INFRASTRUCTURE PLANNING & SURVEY
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDING SOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
HS 01 | Basic Service Delivery | Housing Delivery | Edendale J2 & Quarry | 15 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies by 30 Sept. 2012 | Date of submission of application to DOHS. | N/A | N/A | N/A | DOHS | N/A (Completed Q 1) | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 02 | Basic Service Delivery |  | Willowfountain: Bulwer | 14 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies by 30 Sept. 2012 | Date of submission of application to DOHS. | N/A | N/A | N/A | DOHS | N/A (Completed Q 1) | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 03 | Basic Service Delivery |  | Khalanyoni | 12 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies by 30 Sept. 2012 | Date of submission of application to DOHS. | N/A | N/A | N/A | DOHS | N/A (Completed Q 1) | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 04 | Basic Service Delivery |  | Kwa Thirty | 10 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies by 30 Sept. 2012 | Date of submission of application to DOHS. | N/A | N/A | N/A | DOHS | N/A (Completed Q 1) | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 05 | Basic Service Delivery |  | Hollingwood | 35 | Nil | Applied to DOHS for appointment of IA for Stage 1 Feasibility Studies by 30 Sept. 2012 | Date of submission of application to DOHS. | N/A | N/A | N/A | DOHS and NHFC | N/A (Completed Q 1) | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 06 | Basic Service Delivery |  | Edendale S - 8 Ext | 10 | IA appointed | Monitoring and Management of IA for completion of feasibility Studies by 31/03/2013 | Date of completion of Stage 1 feasibility studies. | N/A | N/A | N/A | DOHS | Feasibility Studies 100% complete by 31/03/13. | Feasibility Studies are 100% completed. EIA submitted to DAEA, awaiting approval. | 3 | N/A | N/A | Project Status Report
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 07 | Basic Service Delivery |  | Edendale S - 3 to 8 | 10 & 15 | Incomplete Services | Management of I.A. to complete outstanding services for 2,010 Sites by 30/06/13 | No. of Sites completed with services | N/A | N/A | N/A | DOHS | 1 500 Sites completed with services by 31/03/13 | 1233 sites completed with Services | 2 | Excavation of rock material underground and labour problems. | Use of chemical composition for breaking rock. | Payment Certificates
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 08 | Basic Service Delivery |  | Edendale T2 & T3 | 15 | Incomplete Services | Management of I.A. to complete outstanding services for 231 Sites by 31/03/13 | No. of Sites completed with services | N/A | N/A | N/A | DOHS | 231 Sites completed with services by 31/03/13 | 70 | 2 | IA not performing ito of contract. IA placed in Breach. | Currently in negotiation with parties to resolve and review completion date. | Letter to IA.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 09 | Basic Service Delivery |  | Msunduzi Wirewall | Various | 1100 | Management of IA for the completion of 340 Units by 30/06/2013. | No. of Houses completed | N/A | N/A | N/A | DOHS | 220 Houses completed by 31/03/13 | 0 | NOT APPLICABLE | Awaiting approval from MEC. | Project under audit. | Correspondence from DOHS.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 10 | Basic Service Delivery |  | Willowfountain EE - Phase1 | 14 | 127 | Management of IA to Construct 73 units completed by 31/03/2013 | No. of Houses completed | N/A | N/A | N/A | DOHS | 73 units to be completed by IA by 31/03/13 | 0 | NOT APPLICABLE | Awaiting IA to submit building Plans. Communicated with IA in this regard. | To meet further with IA in this regard to achieve progress. | Email correspondence.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 11 | Basic Service Delivery | Housing Delivery | Lot 182 Snating | 11 | 0 | Management of IA to construct 133 Units completed by 30/06/2013 | No. of Houses completed | N/A | N/A | N/A | DOHS | 80 houses constructed by IA by 31/03/13 | N/A | NOT APPLICABLE | Building Plans submitted and being circulated for comment. | Fast track approval of plans. | Building Plans and comment sheet.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 12 | Basic Service Delivery |  | Edendale T2 & T3 | 15 | 113 | Management of IA to construct 357 Units completed by 30/06/2013 | No. of Houses completed | N/A | N/A | N/A | DOHS | 300 Houses completed by 31/03/13 | N/A | NOT APPLICABLE | Building Plans submitted and being circulated for comment. | Fast track approval of plans. | Building Plans and comment sheet.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 13 | Basic Service Delivery |  | Transfer of Houses | Various Wards | Nil | Land Legal issues resolved by 30/09/2012 | Date | N/A | N/A | N/A | DOHS | N/A | Rates Clearance impasse resolved. | 3 | N/A | N/A | Minutes of OMC/SMC meeting?
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 14 | Basic Service Delivery |  | Cleaning of ablutions for Masukwane Emergency Housing Scheme | 33 | Nil | Ablutions cleaned weekly | Weekly cleaning | 560 000 | N/A | N/A | Council | Masukwane Ablutions Cleaned weekly | No Progress | 1 | Resident Communityhave refused to comply with Council resolution. | Elevate to next level - not able to comply with Council resolution. | Council resolution. Minutes of meeting of 28 Nov 2012.
[8 empty] | 5601001195 | N/A | N/A |  | 120000 | N/A | N/A | N/A | N/A | N/A
HS 15 | Basic Service Delivery | Rental Housing | Maintenance of rental stock | 24, 33 | Maintenance Plan for 2012/13 & supplied in July 2012 | Maintenance Plan for 2013/14 & supply to I.S. Building & Facilities Section by 30/06/2013 | Compilation of Maintenance Plan |  | N/A | N/A | Council | N/A | N/A | NOT APPLICABLE | N/A | N/A | N/A
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | . | N/A | N/A | N/A
HS 16 | Basic Service Delivery | Rental Housing | Transfer of Rental Stock under EEDBS Policy | All Wards | Nil | Quarterly Progress reports on Investigation on transfer of flats submitted to SMC & Council | Quarterly Progress Reports | N/A | N/A | N/A | DOHS | Report submitted to SMC & Council by 31/03/13 | Quarterly report submitted. | 3 | N/A | N/A | Report.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 17 | Basic Service Delivery | Housing Needs | Housing Needs Register (Waiting List) | All Wards | Inefficient operations | Operational Housing Needs Register in place by 31/12/2012 | Date of operational register in place | 33 106 | N/A | N/A | Council | Operational Housing Needs register in place by 31.12.2012 | Done everything we can, but HNR not yet connected by NDOHS. | 3 | Delays at National Level | Ensure link up with National Database provided, to begin capturing names starting with Informal Settlements as a "Mini census". | Emails between Housing Unit, NDoHS, and Buffalo City metro.
[8 empty] | 265-100-1195 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 18 | Basic Service Delivery |  |  | All Wards | Nil | 5,000 names captured on Housing Register by 30/06/2013 | Number of names captured on Register | N/A | N/A | N/A | Nil Required | 3 500 names captured on Housing Register by 31/03/13 | Nil names captured due to no link-up above. | NOT APPLICABLE | Awaiting link-up above. | Liaising with Buffalo City Metro to assist with speeding up process. | Emails to NDoHs and Buffalo City.
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
HS 19 | Basic Service Delivery | Building Plan Approval / Archival | Installation of Electronic Plan Approval System | All Wards | Inefficient operations | New Electronic Plan Approval system installed by 30/06/2013 | Date of installed system | 1 500 000 | N/A | N/A | CNL / COGTA | System installed, scanning commenced by 31/03/13 | Procurement Process in place. | 2 | Delays with Bid Spec process (new date for Bid Spec Comm meeting 28 /3/2013). | Fast-track through rest of procurement process. | Bid Spec. reports (3).
[8 empty] | 547-100- | N/A | N/A |  | 830 000 | N/A | N/A | N/A | N/A | N/A

## Gedi overview
GEDI, PLANNING, ENVIRONMENTAL & LICENSING UNIT OVERVIEW
SDBIP 2012/2013 QUARTER 3 (JANUARY - MARCH 2013) PROGRESS REPORT
|  |  | TOTAL PROJECTS | KEY
1 NIL ACHIEVED
2 TARGET PARTIALLY MET
3 TARGET MET
4 TARGET EXCEEDED
5 TARGET EXCEEDED BY 100 %
NOT APPLICABLE
| 1 | GEDI, PLANNING, ENVIRONMENTAL & LICENSING UNIT OVERVIEW
| 1.1 | TOTAL PROJECTS: | 7
| 1.1.1 | OPERATING PROJECTS | 7
| 1.1.2 | CAPITAL PROJECTS | 0
| 1.2 | GRAPHICAL REPRESENTATION OF PERFORMANCE: OPERATING PROJECTS

## GEDI, EH, Plan & Lic
SERVICE DELIVERY & BUDGET IMPLEMENTATION PLAN 2012/2013
6.3 GEDI, PLANNING, ENVIRONMENTAL & LICENSING
SDBIP REFERENCE | NATIONAL KPA | PROGRAMME | PROJECT | WARD | BASELINE/ STATUS QUO | ANNUAL KPI: OUTPUT | KPI MEASURE | ANNUAL BUDGET INFORMATION |  |  |  | PERFORMANCE REPORTING - QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | OPEX | CAPEX | REV. | FUNDINGSOURCE | QUARTER 3 - QUARTER ENDING MARCH 2013
[8 empty] | VOTE | VOTE | VOTE |  | Q3 PERFORMANCE TARGET | QUARTER 3 PROGRESS | ACTUAL (1,2,3,4,5, Not Applicable) | REASON FOR DEVIATION | CORRECTIVE MEASURE | SOURCE DOCUMENT
PLN 01 | Social & Economic Development | Tenure upgrades and anomaly rectification | Property tenure upgrades | All wards | 21762 | 1500 properties upgradable to full Title Tenure | Number Of Properties upgradable to full title by 30 June 2013 | 20 000 | N/A | N/A | DoHS / DRDLR | Begin survey work for tenure upgrades | Donation Agreement still not signed by Public Works | 2 | Donation Agreement still not signed by Public Works | pressure public works to sign Agreement | Signed Donation Agreement
[8 empty] | 2851001643 | N/A | N/A |  | 10000 | 5000 | 2 | N/A | N/A | N/A
PLN 02 | Social & Economic Development | Land Expropriation | Private Property expropriation | All wards | No properties expropriated as yet | 63 properties expropriated by 30 June 2013 | Number Of Properties expropriated by 30 June 2013 | 0 | N/A | N/A | DoHS / DRDLR | Legal matters dealt with prior to expropriation | Final Designation notice ready. Docs with LTAC's | 3 | N/A | N/A | Designation notices
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PLN 03 | Spatial Planning | LOCAL AREA PLANS | South Eastern District Local area Plan | 18 | No local area plans yet completed | Inception Report for South Eastern District completed by 30th June 2013 | Date of completed inception report | 600000 | N/A | N/A | COGTA, Council | Draft inception report | Draft inception report | 3 | N/A | N/A | Draft inception report
[9 empty] | N/A | N/A |  | 150000 | no invoice received yet |  | N/A | N/A | N/A
PLN 04 | Spatial Planning |  | Inner City Development and Regeneration Plan | 37 | No local area plans yet completed | Inception Report for Inner City Development completed by 30th June 2013 | Date of completed inception report | 600000 | N/A | N/A | Council | Draft inception report | Draft inception report | 3 | N/A | N/A | Draft inception report
[8 empty] | 5481001316 2851001195 | N/A | N/A |  | 150000 | no invoice received yet |  | N/A | N/A | N/A
PLN 05 | Spatial Planning | TOWN PLANNING SCHEME EXTENSION | Edendale & Sobantu Town Planning Scheme | 18, 21, 33 | No Town Planning schemes for these two areas | Inception Report for Town Planning scheme extension completed by 30th June 2013 | Date of completed inception report | 320000 | N/A | N/A | Council | Receipt of inception report from Consultant | Inception report received | 3 | N/A | N/A | Inception report
[8 empty] | 5481001316 | N/A | N/A |  | 40000 | 40000 | N/A | N/A | N/A | N/A
PLN 06 | Spatial Planning | Climate change | Climate change adaptation policy | All wards | No policy | Policy submitted to SMC by 30 June 13 | Date of policy submitted to SMC | N/A | N/A | N/A | Nil Required | Final draft of policy completed by 31st March 2013 | synergising policy with that of uMDM outstanding | 2 | more work than expected to synergise information | attempt to catch up on information synergy | Draft Policy document
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
PLN 07 | Spatial Planning | Ecosystem Services Plan | Interim Ecosystem Services Plan | All wards | No Ecosystems Plan in place | 3 zonal reports completed and submitted to SMC by 30th June 2013 | Date of completed zonal reports submitted to SMC | N/A | N/A | N/A | Nil | Research second zone in detail, report completed | report is completed | 3 | N/A | N/A | Draft Eco-systems plan
[8 empty] | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A

## Sheet5
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 4.02% | 8.36% | 3.58%
2 TARGET PARTIALLY MET | 25.83% | 21.73% | 18.63%
3 TARGET MET | 47.31% | 42.8% | 42.65% | organisational rep - operating projects
4 TARGET EXCEEDED | 7.38% | 9.36% | 6.81%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 2.5%
NOT APPLICABLE | 15.43% | 17.72% | 25.8%
NO INFORMATION RECEIVED | 0.68%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 1.49% | 11.94% | 4.61%
2 TARGET PARTIALLY MET | 38.9% | 32.83% | 30.76%
3 TARGET MET | 47.76% | 34.22% | 38.46% | organisational rep - capital projects
4 TARGET EXCEEDED | 10.44% | 19.4% | 1.53%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 1.53%
NOT APPLICABLE | 1.49% | 1.49% | 23.07%
NO INFORMATION RECEIVED | 1.09%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 7.24% | 7.24% | 1.56%
2 TARGET PARTIALLY MET | 23.18% | 20.28% | 12.5%
3 TARGET MET | 36.23% | 34.78% | 32.81% | business unit rep - cbu - operating
4 TARGET EXCEEDED | 2.89% | 1.44% | 1.56%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 30.43% | 36.23% | 51.56%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 6.66% | 1.33% | 0%
2 TARGET PARTIALLY MET | 20% | 6.66% | 18.18%
3 TARGET MET | 6.66% | 33.33% | 18.18% | sub unit rep - internal audit - operating
4 TARGET EXCEEDED | 13.3% | 6.66% | 9.09%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 53.3% | 40% | 54.54%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 5.4% | 2.7% | 0%
2 TARGET PARTIALLY MET | 24.32% | 21.62% | 13.88%
3 TARGET MET | 43.24% | 35.13% | 33.33% | sub unit rep - office of the mm - operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 27.02% | 40.54% | 52.77%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100%
NIL ACHIEVED | 18.18%
TARGET PARTIALLY MET | 9.1%
TARGET MET | 72.72% |  |  | sub unit rep - mayoral special projects - capital
TARGET EXCEEDED | 0%
NOT APPLICABLE | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 18.18% | 18.18% | 10%
2 TARGET PARTIALLY MET | 0% | 18.18% | 0%
3 TARGET MET | 54.54% | 27.27% | 20% | sub unit rep - IDP - Operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 27.27% | 36.36% | 70%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 66.66% | 50% | 16.66%
3 TARGET MET | 33.33% | 50% | 83.33% | sub unit rep - marketing - operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 2.08% | 0% | 0%
2 TARGET PARTIALLY MET | 22.91% | 20.83% | 19.04%
3 TARGET MET | 45.83% | 50% | 52.38% | business unit rep - finance - operating
4 TARGET EXCEEDED | 2.08% | 6.25% | 9.52%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 27.08% | 22.91% | 19.04%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 9.09% | 0% | 0%
2 TARGET PARTIALLY MET | 27.27% | 18.18% | 18.18%
3 TARGET MET | 18.18% | 36.36% | 36.36% | sub unit rep - budget & treasury - operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 45.45% | 45.45% | 45.45%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 23.07% | 0% | 20%
3 TARGET MET | 53.84% | 69.23% | 80% | sub unit rep - expenditure - operating
4 TARGET EXCEEDED | 0% | 23.07% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 23.07% | 7.69% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 15.38% | 46.15% | 23.07%
3 TARGET MET | 46.15% | 53.84% | 46.15% | sub unit rep - revenue management - operating
4 TARGET EXCEEDED | 7.69% | 0% | 30.76%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 30.76% | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 27.27% | 18.18% | 12.5%
3 TARGET MET | 63.63% | 36.36% | 50% | sub unit rep - SCM - operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 9.09% | 45.45% | 37.5%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 4.05% | 8.1% | 7.46%
2 TARGET PARTIALLY MET | 27.02% | 21.62% | 20.89%
3 TARGET MET | 43.24% | 45.94% | 41.79% | business unit rep - community services - operating
4 TARGET EXCEEDED | 20.27% | 20.27% | 8.95%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 10.44%
NOT APPLICABLE | 5.4% | 4.05% | 11.94%
NO INFORMATION RECEIVED | 3.5%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 50% | 50% | 0%
3 TARGET MET | 50% | 50% | 0% | business unit rep - community services - capital
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 100%
NO INFORMATION RECEIVED | 3.03%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 16.16% | 0%
2 TARGET PARTIALLY MET | 8.33% | 16.16% | 0%
3 TARGET MET | 66.66% | 41.66% | 75% | sub unit rep - ABM - operating
4 TARGET EXCEEDED | 8.33% | 8.33% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 16.66% | 16.66% | 25%
NO INFORMATION RECEIVED
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 8.33% | 0% | 4.34%
2 TARGET PARTIALLY MET | 8.33% | 33.33% | 8.69%
3 TARGET MET | 28% | 20.83% | 39.13% | sub unit rep - HSS - operating
4 TARGET EXCEEDED | 44% | 41.66% | 17.39%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 26.08%
NOT APPLICABLE | 8.33% | 4.16% | 4.34%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 4% | 16.16% | 8.69%
2 TARGET PARTIALLY MET | 40% | 16.16% | 43.47%
3 TARGET MET | 52% | 68% | 21.73% | sub unit rep - community development - operating
4 TARGET EXCEEDED | 4% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 26.08%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 50% | 50% | 0%
3 TARGET MET | 50% | 50% | 0% | sub unit rep - community development - capital
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 100%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 53.84% | 15.38% | 30% | sub unit rep - psdm - operating
3 TARGET MET | 30.7% | 53.84% | 40%
4 TARGET EXCEEDED | 15.38% | 30.76% | 10%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 20%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 16.66% | 33.33% | 30%
3 TARGET MET | 75% | 58.33% | 40% | business unit rep - ISF - operating
4 TARGET EXCEEDED | 0% | 0% | 10%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 8.33% | 8.33% | 20%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 1.53% | 12.3% | 4.76%
2 TARGET PARTIALLY MET | 38.46% | 32.3% | 31.74%
3 TARGET MET | 47.69% | 33.84% | 39.68% | business unit rep - ISF - capital
4 TARGET EXCEEDED | 10.76% | 20% | 1.58%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 1.58%
NOT APPLICABLE | 1.78% | 1.53% | 20.63%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 21.42%
2 TARGET PARTIALLY MET | 7.14% | 57.14% | 7.14%
3 TARGET MET | 64.28% | 35.71% | 42.85% | sub unit rep - water & sanitation - capital
4 TARGET EXCEEDED | 21.42% | 7.14% | 7.14%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 7.14% | 0% | 14.28%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 0% | 0% | 0%
3 TARGET MET | 100% | 100% | 0% | sub unit rep - Electricity - operating
4 TARGET EXCEEDED | 0% | 0% | 100%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 8.33% | 8.33% | 0%
2 TARGET PARTIALLY MET | 41.66% | 33.33% | 50%
3 TARGET MET | 41.66% | 8.33% | 40% | sub unit rep - Electricity - capital
4 TARGET EXCEEDED | 8.33% | 50% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 10%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 20%
2 TARGET PARTIALLY MET | 40% | 60% | 40%
3 TARGET MET | 40% | 20% | 0% | sub unit rep - Fleet - operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 20% | 20% | 40%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 0% | 16.16% | 25%
3 TARGET MET | 100% | 83.83% | 75% | sub unit rep - PMU - operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 23.33% | 3.22%
2 TARGET PARTIALLY MET | 53.33% | 30% | 45.16%
3 TARGET MET | 36.66% | 23.33% | 48.38% | sub unit rep - roads & stormwater - capital
4 TARGET EXCEEDED | 10% | 20% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 3.33% | 3.22%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 6.89% | 3.44%
2 TARGET PARTIALLY MET | 26.31% | 24.13% | 24.13%
3 TARGET MET | 64.91% | 50% | 48.27% | business unit rep - corporate services - operating
4 TARGET EXCEEDED | 0% | 6.89% | 10.34%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 8.77% | 12.06% | 13.79%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 15.78% | 0%
2 TARGET PARTIALLY MET | 15.78% | 5.26% | 0%
3 TARGET MET | 84.21% | 63.15% | 92.85% | sub unit rep - sound governance - operating
4 TARGET EXCEEDED | 0% | 15.78% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 7.14%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 33.33%
2 TARGET PARTIALLY MET | 66.66% | 33.33% | 0%
3 TARGET MET | 33.33% | 66.66% | 66.66% | sub unit rep - legal - operating
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 71.42% | 100% | 25%
3 TARGET MET | 28.57% | 0% | 33.33% | sub unit rep - ICT - operating
4 TARGET EXCEEDED | 0% | 0% | 41.66%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 3.44% | 3.44%
2 TARGET PARTIALLY MET | 17.85% | 17.24% | 37.93%
3 TARGET MET | 64.28% | 51.72% | 31.03% | sub unit rep - HRD, OCC H, SD, OD - operating
4 TARGET EXCEEDED | 0% | 3.44% | 3.44%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 17.85% | 24.13% | 24.13%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 7.89% | 26.31% | 5.26%
2 TARGET PARTIALLY MET | 34.21% | 18.42% | 18.42%
3 TARGET MET | 42.1% | 26.31% | 39.74% | business unit rep - economic development - operating
4 TARGET EXCEEDED | 10.52% | 13.15% | 2.63%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 5.26% | 15.78% | 34.21%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 16.66% | 8.33%
2 TARGET PARTIALLY MET | 33.33% | 8.33% | 16.66%
3 TARGET MET | 50% | 33.33% | 50% | sub unit rep - ED - operating
4 TARGET EXCEEDED | 16.66% | 41.66% | 8.33%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 16.66%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 15.78% | 42.1% | 5.26%
2 TARGET PARTIALLY MET | 26.31% | 21.05% | 15.78%
3 TARGET MET | 42.1% | 5.26% | 21.05% | sub unit rep - housing - operating
4 TARGET EXCEEDED | 5.26% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 10.52% | 31.57% | 57.89%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 57.14% | 28.57% | 28.57%
3 TARGET MET | 28.57% | 71.42% | 71.42% | sub unit rep - Gedi, EH, Plan & Licensing - operating
4 TARGET EXCEEDED | 14.28% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 0%
NO INFORMATION RECEIVED | 0%
TOTAL PROJECTS | 100% | 100% | 100%
1 NIL ACHIEVED | 0% | 0% | 0%
2 TARGET PARTIALLY MET | 33.33% | 0% | 0%
3 TARGET MET | 66.66% | 100% | 0% | sub unit rep - landfill capital
4 TARGET EXCEEDED | 0% | 0% | 0%
5 TARGET EXCEEDED BY 100 % | 0% | 0% | 0%
NOT APPLICABLE | 0% | 0% | 100%

## Sheet1 (hidden)
.
1
2
3
4
5
NOT APPLICABLE

## Sheet6 (hidden)
Organisational Representation - 344
| Capital Projects |  | 65 | Operating Projects |  | 279
| Colour | Number | % | Colour | Number | %
| Red | 3 | 4.61% | Red | 10 | 3.58%
| Orange | 20 | 30.76% | Orange | 52 | 18.63%
| Green | 25 | 38.46% | Green | 119 | 42.65%
| Blue | 1 | 1.53% | Blue | 19 | 6.81%
| Purple | 1 | 1.53% | Purple | 7 | 2.5%
| Yellow | 15 | 23.07% | Yellow | 72 | 25.8%
Business Unit Representation - CBU 64
|  |  |  | Operating Projects |  | 64
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 1.56%
|  |  |  | Orange | 8 | 12.5%
|  |  |  | Green | 21 | 32.81%
|  |  |  | Blue | 1 | 1.56%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 33 | 51.56%
Sub Unit Representation - Internal Audit 11
|  |  |  | Operating Projects |  | 11
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 18.18%
|  |  |  | Green | 2 | 18.18%
|  |  |  | Blue | 1 | 9.09%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 6 | 54.54%
Sub Unit Representation - Office of the MM - 37
|  |  |  | Operating Projects |  | 37
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 5 | 13.88%
|  |  |  | Green | 12 | 33.33%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 19 | 52.77%
Sub Unit Representation - IDP 10
|  |  |  | Operating Projects |  | 10
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 10%
|  |  |  | Orange | 0 | 0%
|  |  |  | Green | 2 | 20%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 7 | 70%
Sub Unit Representation - Marketing 6
|  |  |  | Operating Projects |  | 6
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 1 | 16.66%
|  |  |  | Green | 5 | 83.33%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Business Unit Representation - Finance 42
|  |  |  | Operating Projects |  | 42
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 8 | 19.04%
|  |  |  | Green | 22 | 52.38%
|  |  |  | Blue | 4 | 9.52%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 8 | 19.04%
Sub Unit Representation - Budget & Treasury 11
|  |  |  | Operating Projects |  | 11
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 18.18%
|  |  |  | Green | 4 | 36.36%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 5 | 45.45%
Sub Unit Representation - expenditure management 10
|  |  |  | Operating Projects |  | 10
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 20%
|  |  |  | Green | 8 | 80%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - Revenue Management 13
|  |  |  | Operating Projects |  | 13
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 3 | 23.07%
|  |  |  | Green | 6 | 46.15%
|  |  |  | Blue | 4 | 30.76%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - supply chain Management 8
|  |  |  | Operating Projects |  | 8
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 1 | 12.5%
|  |  |  | Green | 4 | 50%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 3 | 37.5%
Business Unit Representation - Community Services 69
| Capital Projects |  | 2 | Operating Projects |  | 67
| Colour | Number | % | Colour | Number | %
| Red | 0 | 0% | Red | 5 | 7.46%
| Orange | 0 | 0% | Orange | 14 | 20.89%
| Green | 0 | 0% | Green | 28 | 41.79%
| Blue | 0 | 0% | Blue | 6 | 8.95%
| Purple | 0 | 0% | Purple | 6 | 10.44%
| Yellow | 2 | 100% | Yellow | 8 | 11.94%
Sub Unit Representation - ABM 8
|  |  |  | Operating Projects |  | 8
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 0%
|  |  |  | Orange | 0 | 0%
|  |  |  | Green | 6 | 75%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 2 | 25%
Sub Unit Representation - HSS 23
|  |  |  | Operating Projects |  | 23
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 4.34%
|  |  |  | Orange | 2 | 8.69%
|  |  |  | Green | 9 | 39.13%
|  |  |  | Blue | 4 | 17.39%
|  |  |  | Purple | 6 | 26.08%
|  |  |  | Yellow | 1 | 4.34%
Sub Unit Representation - comm dev - 25
| Capital Projects |  | 2 | Operating Projects |  | 23
PKS 08 | Colour | Number | % | Colour | Number | %
PKS 10 | Red | 0 | 0% | Red | 2 | 8.69%
| Orange | 0 | 0% | Orange | 10 | 43.47%
| Green | 0 | 0% | Green | 5 | 21.73%
| Blue | 0 | 0% | Blue | 0 | 0%
| Purple | 0 | 0% | Purple | 0 | 0%
| Yellow | 2 | 100% | Yellow | 6 | 26.08%
Sub Unit Representation - PSDM - 13
|  |  |  | Operating Projects |  | 13
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 7.69%
|  |  |  | Orange | 2 | 15.38%
|  |  |  | Green | 8 | 61.53%
|  |  |  | Blue | 2 | 15.38%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Business Unit Representation - Infrastructure Services 73
| Capital Projects |  | 63 | Operating Projects |  | 10
| Colour | Number | % | Colour | Number | %
| Red | 3 | 4.76% | Red | 0 | 0%
| Orange | 20 | 31.74% | Orange | 3 | 30%
| Green | 25 | 39.68% | Green | 4 | 40%
| Blue | 1 | 1.58% | Blue | 1 | 10%
| Purple | 1 | 1.58% | Purple | 0 | 0%
| Yellow | 13 | 20.63% | Yellow | 2 | 20%
Sub Unit Representation - water & sanitation 14
| Capital Projects |  | 14
| Colour | Number | %
| Red | 3 | 21.42%
| Orange | 1 | 7.14%
| Green | 6 | 42.85%
| Blue | 1 | 7.14%
| Purple | 0 | 0%
| Yellow | 3 | 14.28%
Sub Unit Representation - fleet 5
|  |  |  | Operating Projects |  | 5
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 20%
|  |  |  | Orange | 2 | 40%
|  |  |  | Green | 0 | 0%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 2 | 40%
Sub Unit Representation - PMU 4
|  |  |  | Operating Projects |  | 4
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 1 | 25%
|  |  |  | Green | 3 | 75%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - Roads & Stormwater 31
| Capital Projects |  | 31
| Colour | Number | %
| Red | 1 | 3.22%
| Orange | 14 | 45.16%
| Green | 15 | 48.38%
| Blue | 0 | 0%
| Purple | 0 | 0%
| Yellow | 1 | 3.22%
Sub Unit Representation - Electricity 11
| Capital Projects |  | 10 | Operating Projects |  | 1
| Colour | Number | % | Colour | Number | %
| Red | 0 | 0% | Red | 0 | 0% | EL 12 oper
| Orange | 4 | 40% | Orange | 0 | 0%
| Green | 5 | 50% | Green | 0 | 0%
| Blue | 0 | 0% | Blue | 1 | 100%
| Purple | 0 | 0% | Purple | 0 | 0%
| Yellow | 1 | 10% | Yellow | 0 | 0%
|  |  | Sub Unit Representation - Landfill Site |  | 8
| Capital Projects |  | 8
| Colour | Number | %
| Red | 0 | 0%
| Orange | 0 | 0%
| Green | 0 | 0%
| Blue | 0 | 0%
| Purple | 0 | 0%
| Yellow | 8 | 100%
Business Unit Representation - Corporate Services 58
|  |  |  | Operating Projects |  | 58
|  |  |  | Colour | Number | %
|  |  |  | Red | 2 | 3.44%
|  |  |  | Orange | 14 | 24.13%
|  |  |  | Green | 28 | 48.27%
|  |  |  | Blue | 6 | 10.34%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 8 | 13.79%
Sub Unit Representation - Sound Governance 14
|  |  |  | Operating Projects |  | 14
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 0 | 0%
|  |  |  | Green | 13 | 92.85%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 1 | 7.14%
Sub Unit Representation - legal 3
|  |  |  | Operating Projects |  | 3
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 33.33%
|  |  |  | Orange | 0 | 0%
|  |  |  | Green | 2 | 66.66%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - ICT - 12
|  |  |  | Operating Projects |  | 12
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 3 | 25%
|  |  |  | Green | 4 | 33.33%
|  |  |  | Blue | 5 | 41.66%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%
Sub Unit Representation - HRM, OD, SD, OC 29
|  |  |  | Operating Projects |  | 29
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 3.44%
|  |  |  | Orange | 11 | 37.93%
|  |  |  | Green | 9 | 31.03%
|  |  |  | Blue | 1 | 3.44%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 7 | 24.13%
Business Unit Representation - Economic Development 38
|  |  |  | Operating Projects |  | 38
|  |  |  | Colour | Number | %
|  |  |  | Red | 2 | 5.26%
|  |  |  | Orange | 7 | 18.42%
|  |  |  | Green | 15 | 39.74%
|  |  |  | Blue | 1 | 2.63%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 13 | 34.21%
Sub Unit Representation - LED 12
|  |  |  | Operating Projects |  | 12
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 8.33%
|  |  |  | Orange | 2 | 16.66%
|  |  |  | Green | 6 | 50%
|  |  |  | Blue | 1 | 8.33%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 2 | 16.66%
Sub Unit Representation - Housing 19
|  |  |  | Operating Projects |  | 19
|  |  |  | Colour | Number | %
|  |  |  | Red | 1 | 5.26%
|  |  |  | Orange | 3 | 15.78%
|  |  |  | Green | 4 | 21.05%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 11 | 57.89%
Sub Unit Representation - GEDI etc 7
|  |  |  | Operating Projects |  | 19
|  |  |  | Colour | Number | %
Red
Orange
Green
Blue
Yellow
Brown
| KPI |  | 2
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
| KPI |  | 3
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
| KPI |  | 4
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
| KPI |  | 5
| Colour | Number | %
Red
Orange
Green
Yellow
Brown
Comparative summary 3rd Quarter 2010/11 & 2011/12
| Capital Projects |  | 91 | Operating Projects |  | 291
| Colour | 2010/11 | 2011/12 |  | 2010/11 | 2011/12
| Red | 81% | 37.3% | Red | 32% | 17.52%
| Orange | 15% | 30.7% | Orange | 25% | 39.86%
| Green | 2% | 28.5% | Green | 36% | 25.77%
| Blue | 2% | 2.1% | Blue | 7% | 5.84%
| Yellow | 0% | 1% | Yellow | 0% | 10.99%
| Brown | 0% | 0% | Brown | 0% | 0%
|  |  |  | Operating Projects |  | 7
|  |  |  | Colour | Number | %
|  |  |  | Red | 0 | 0%
|  |  |  | Orange | 2 | 28.57%
|  |  |  | Green | 5 | 71.42%
|  |  |  | Blue | 0 | 0%
|  |  |  | Purple | 0 | 0%
|  |  |  | Yellow | 0 | 0%